## Staff Name
Date | Name | Task | Start time | End time | Status | Comment
12.05.16 | Sivaramakannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Learning AJAX concept | 10.00 AM | 11.00 AM
|  | Implementing ajax concept task for thalapakktu like adding parameters dynamically | 11.00 AM | 5.00 PM | In progress
|  | Auto suggestion in jquery | 5.00 PM | 7.00 PM | Completed
13.05.16 | Sivaramakannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Fixing validation issues in ETS | 10.00 AM | 11.00 AM | Completed
|  | Adding scroll option for Technologies logo | 11.00 AM | 1.30 PM | Completed
|  | Changing images in index and portfolio page of ETS | 2.30 PM | 6.30 PM | Completed
|  | Adding content in ETS and links for social icons | 6.30 PM | 7.30 PM | Completed
17.05.16 | Sivaramakannan
|  | Typing test | 3.45 PM | 4.15 PM | Completed
|  | Fixed issues in bug sheet of ETS like validation,design break issues | 4.30 PM | 7.00 PM | In progress
18.05.16 | Sivaramakannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Fixed issues in bug sheet of ETS like validation,design break issues,adding images to slider | 10.00 AM | 1.30 PM | Completed
|  | Adding table to database for yii framework and discussed with kalai about django framework | 2.30 PM | 4.45 PM | Completed
|  | Fixing issues in oozaaoo responsive | 5.00 PM | 7.30 PM | Completed
19.05.16 | Sivaramakannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Learning django and how to install it. | 10.00 AM | 11.00 AM | Completed
|  | Fixing issues in header part for responsive | 11.00 AM | 1.30 PM | Completed
|  | Fixing mobile num validation issues and image slider issues in oozaaoo | 2.30 PM | 4.:30 PM | Completed
|  | Fixing email validation issues in oozaaoo | 4.30 PM | 5.:00 PM | In progress
|  | Meetnig with Deepak | 5.00 PM | 7.30 PM | Completed
20.05.16 | Sivaramakannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Fixing mail function issues in oozaaoo and slider issues for responsive | 10.00 AM | 1.00 PM | Completed
|  | Learning about python like how to set enviromental variables,and installing supporting packages | 1.00 PM | 1.30 PM | In progress
|  | Implementing hover function in services section of index page for ETS | 2.30 PM | 3.00 PM | Completed
|  | Adding images to slider in index page for ETS | 3.00 PM | 3.30 PM | Completed
|  | Implementing technologies in aboutus section of index page for ETS | 3.30 PM | 10.00 PM | Completed
Removing Technologies slider in contactus form of index page for ETS