## 26.05.2016
Date | Name | Task | Start time | End time | Status | Comment
2016-05-26 | Akila | Typing Lesson | 09.45am | 10.15am | Completed
|  | Standup Meeting & Bus fixing in OWC project | 10.15am | 11.35am | Completed
|  | Desktop fix in OCW for -Home & Site map | 11.55am | 01.50pm | Completed
|  | Responsive fix in OCW for -Home & Site map | 02.45pm | 04.00pm | Pending
|  | Responsive fix for OCW for century,education,ethical,historic pages | 04.00pm | 05.30pm | Completed
|  | Responsive fix for OCW for innovation,sustainable & unsustainable pages | 05.30pm | 07.00pm | Completed
|  | Site Map responsive fix | 07.00pm | 08.00pm | Pending
2016-05-26 | Balasubramaniam
Absent
2016-05-26 | Barath | Worked on Cotton House logo | 10.00Am | 8.00PM | Completed
I create 4 sample for cotton house logo… send to 2 logo for approval
|  | Worked on RICSCO WEBSITE | 12.00PM | 1.30PM | Completed
Worked on ricsco footer part
Changing color Themes also on that
2016-05-26 | Kalai | Attended standup meeting, Started to fix issues in image uploading process while posting ads, (when i overwrite the plugin for this, it affects on some other pages, traced out that and tried to fix | 11.45am | 1.30pm | pending
|  | Guided siva about django basic concepts in fixido models.py and admin.py, Tried to fix the issues in resell manageprofile page | 2.35 pm | 4.30 pm | completed
|  | Continued to fix the issues in image uploading form and finally fixed it with overwrite the plugin without affecting others, created github account for invoice generation & guided velpandi to merge html files, guided siva relationship concepts in django | 4.45 pm | 7.20 pm | completed
2016-05-26 | Madhivanan
Forenoon Absent
2016-05-26 | Muthu | Task allocation to team | 10:00 | 10:30 | Completed
|  | Fixing issues in scrollbar issue | 10:30 | 12:00 | Completed
|  | Make responsive to IWC Project site | 12:00 | 13:30 | Pending
|  | Make responsive to IWC Project site | 14:30 | 19:30 | Completed
|  | Code move to development server | 19:30 | 19:45 | Completed
|  | File share via we transfer to atomicka team and fix slider issue | 19:45 | 20:45 | Completed
2016-05-26 | Santosh | OWC site testing Chrome and firefox | 10.00am | 12.00pm | Completed
|  | Springloops analyzation | 12.00pm | 1.40pm | Pending
|  | Owc testing in laptop(chrome and firefox) | 3.00pm | 5.00pm | Completed
|  | Create a UML diagram for XYGET | 5.30pm | 8.00pm | Pending
2016-05-26 | Siva Rama Kannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Learned about relationship like onetoone relationship,forignkey,manytomanyrelationshipl for form in django | 10.00 AM | 11.30 AM | Completed
|  | Learned form fields,how to add validation and Implemented form validation in django admin interface | 11.30 AM | 3.00 PM | Completed
|  | Learned about meta tag fields and Implemented some functions like unicode,queryset in django | 3.00 PM | 7.00 PM | Completed
2016-05-26 | Thangamariappan
Absent
2016-05-26 | Velpandi | Typing Test | 9:30 | 10:30 | Completed
|  | Working on the content part in the Blogs in InvoiceGenerator | 10:30 | 11:30 | Completed
|  | Working on the side bar in the blogs in invoice generator. | 11:30 | 13:30 | Completed
|  | working on the footer part in the blogs in invoice generator. | 14:30 | 16:30 | Completed
|  | Working on the navigation bar in the login page in invoice generator. | 16:30 | 17:30 | Completed
|  | Working on the banner part for the login page. | 17:30 | 19:00 | Completed
2016-05-26 | Vignesh | Attended typing test | 9.50am | 10.10am | completed
|  | Worked in Home page of OWC for responsive issue | 10.10am | 3.00pm | completed
|  | Worked in vision page, origin page, vision page, cross page | 3.00pm | 7.30pm | completed

## 25.05.2016
Date | Name | Task | Start time | End time | Status | Comment
2016-05-25 | Akila | Typing Lesson | 09.40am | 10.10am | Completed
|  | Standup Meeting ,OCW project page 4 design | 10.25am | 11.50am | Completed
|  | OCW project page 4 design | 12.10pm | 01.40pm | Completed
|  | OCW project page 5 design | 02.30pm | 04.00pm | Completed
|  | OCW project page 6 design | 04.00PM | 05.00pm | Completed
|  | OCW project page6 layout correction | 05.20pm | 06.40pm | Completed
|  | Gt issue fix | 06.45pm | 07.32pm | Pending
2016-05-25 | Balasubramaniam
Absent
2016-05-25 | Barath | Worked on RICSCO WEBSITE | 10.00AM | 6.00PM | Completed
designing home page with searching option
Login options
filter options
header and footer
banner part
|  | Worked on Chemknowcourse Wesite | 6.00PM | 8.00PM | Completed
Designer imahes for 4 images
2016-05-25 | Kalai | Attended standup meeting, Prepared the timeline report for ricsco project and discussed with our team, Guided siva for configuring fixido project and creating actors modules in django 1.8 version | 10.45 am | 1.30 am | completed
|  | Fixed the issues(image upload while edit post ad) in resell with overwrite the plugin | 2.45 pm | 6.00 pm | completed
|  | Fixed the issues from bug report | 6.15 pm | 7.55 pm | pending
2016-05-25 | Madhivanan
Absent
2016-05-25 | Muthu | Fixing safari issue for IWC | 12:00 | 14:00 | Completed
|  | Fixing issue for IWC | 15:00 | 17:00 | Completed
|  | Saturday session | 17:00 | 18:00 | Completed
2016-05-25 | Santosh | XYGET documentation | 9.00am | 1.30pm | Pending
|  | XYGET documentation | 2.30pm | 6.30pm | Completed
|  | OWC site testing | 6.30pm | 7.50pm | Completed
2016-05-25 | Siva Rama Kannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Fixing issues in ETS site like slider and alignment issues | 10.00 AM | 10.30 AM | Completed
|  | Dicussed with kalai | 10.30 AM | 11.00 AM | Completed
|  | Implemented actor module in admin interface and analysed project flow and studied about some functionality | 11.00 AM | 7.00 PM | In progress | form validation and relationship are pending in admin interface
2016-05-25 | Thangamariappan
Absent
2016-05-25 | Velpandi | Typing Test | 9:30 | 10:30 | Completed
|  | Working on footer part of Pricing in InvoiceGenerator. | 10:30 | 12:30 | Completed
|  | Working on the Header part and navigation bar in Blogs in invoice generator | 12:30 | 13:30 | Completed
|  | Working on banner part in Blogs in invoice generator. | 14:30 | 16:30 | Completed
|  | Working on the content part in the Blogs in InvoiceGenerator | 16:30 | 19:00 | InProgress
2016-05-25 | Vignesh | Attended typing test | 9.35am | 9.50am | completed
|  | Worked in One world Chemistry site(OCW) vision page | 10.00am | 1.30pm | completed
for content editing and responsive
|  | Worked in OCW need page origin abt the orginiator | 2.30pm | 3.30pm | completed
|  | Worked in OCW origin page | 3.30pm | 5.30pm | completed

## 24.05.2016
Date | Name | Task | Start time | End time | Status | Comment
2016-05-24 | Akila | Typing Lesson | 09.40am | 10.20am | Completed
|  | Standup meeting & Invoice code Generator project evaluation | 10.25am | 12.30am | Completed
|  | OCW project page1 design | 12.45pm | 01.40pm | Pending
|  | OCW project page1 design | 01.45pm | 04.30pm | Completed
|  | OCW project page2 design | 04.30pm | 07.00pm | Completed
|  | OCW project page3 design | 07.00pm | 08.30pm | Completed
2016-05-24 | Balasubramaniam
Absent
2016-05-24 | Barath | LOGO DESIGNING FOR SYNUNOW | 10.30Am | 6.00PM | Completed
I done more than 6 sample for synunow logo.
with Different color basis. Flat and gradient
|  | Wire fram design for Ricsco | 2.30PM | 3.00PM | Completed
Studying Module on Ricsco and discussion with KALAI
|  | LOGO DESIGNIG FOR MOBILE |  |  | HAVE TO DO
Analysing WEB TEMP for FREAKWENGCY
2016-05-24 | Kalai | Started to fix issues in resell which is given by prabhu, Had discussion with sastha about ricsco first phase modules and timeline | 11.00 am | 12.45 pm | completed
|  | Guided siva for installing python 2.7 version and app creation using django, fixed resell issues from bug report | 12.45 pm | 2.00 pm | completed
|  | Had call with prabhu for resell updation, he said again some issues in resell and noted it, tried to fix that issues | 3.00 pm | 5.30 pm | completed
|  | Discussion with sastha and deepak about ricsco timeline and with our team | 5.45 pm | 8.00 pm | completed
2016-05-24 | Madhivanan
2016-05-24 | Muthu | Templatecode analyse and one world chemistry project content integration to I medica templete-Homepage | 10:00 | 13:30 | Pending
|  | Change Home page modification | 14:30 | 18:30 | Completed
|  | Team members code integration | 18:30 | 19:30 | Completed
|  | Code move to development server | 19:30 | 20:00 | Pending
2016-05-24 | Santosh | XYGET document | 9.30am | 1.30pm | Pending
|  | XYGET document | 2.30pm | 7.20pm | Pending
2016-05-24 | Siva Rama Kannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Fixing issues in ETS site like slider and alignment issues | 10.00 AM | 1.30 PM | In progress | Only three issues are pending.it needs some images from designer.
|  | Django configuration in ubuntu and Configuring Fixido project | 2.30 PM | 7.30 PM | Completed
2016-05-24 | Thangamariappan
Absent
2016-05-24 | Velpandi | Typing Test | 9:30 | 10:30 | Completed
|  | Rearranging the fonts in the invoice generator | 10:30 | 13:30 | Completed
|  | Changing the hover color to the invoice generator pages. | 14:30 | 15:30 | Completed
|  | Working on the header part for the home page in the invoice generator. | 15:30 | 17:15 | Completed
|  | Discussion with new technology in IT field. | 17:30 | 18:30 | Completed
2016-05-24 | Vignesh
Not Received

## 23.05.2016
Date | Name | Task | Start time | End time | Status | Comment
2016-05-23 | Akila | Typing skill | 09.40am | 10.30am | Completed
|  | Standup meeting & Fixed image issues in technology page | 10.35am | 01.45pm | Completed
|  | Fixed issues like word alignment & page alignment for responsive | 01.55pm | 06.30pm | Completed
|  | Reviwed some doubts in bootstrap documentation | 06.35pm | 07.30pm | Completed
2016-05-23 | Balasubramaniam
Absent
2016-05-23 | Barath | LOGO DESIGNING FOR SYNUNOW | 10.30Am | 6.00PM | Completed
I done more than 6 sample for synunow logo.
with Different color basis. Flat and gradient
|  | Wire fram design for Ricsco | 2.30PM | 3.00PM | Completed
Studying Module on Ricsco and discussion with KALAI
LOGO DESIGNIG FOR MOBILE
Analysing WEB TEMP for FREAKWENGCY
2016-05-23 | Kalai | Attended standup meeting, Fixed video supported issues, image loading, social login issues in resell | 11.00 am | 12.30 pm | completed
|  | Guided python and django basics to siva, Fixed some low priority issues tested by santhosh | 12.30 pm | 1.45 pm | completed
|  | Fixed phone number series restriction, logical issues while post ad without login | 2.50 pm | 5.30 pm | completed
|  | Analyzed the python and django version document and differences of each version, Continued to fix the image uploading issues while edit ads in resell, discussed latest resell updation with prabhu on phone call | 5.45 pm | 8.00 pm | completed
2016-05-23 | Madhivanan
2016-05-23 | Muthu | Typing test | 10:00 | 10:30
|  | Making python library for paypal-anakysing paypal flow | 10:30 | 11:50 | Completed
|  | Python django configuration in my system and installing my sql server with xampp server | 11:50 | 13:30 | Completed
|  | installing supporting tools for python django and write views of paypal libray | 14:30 | 16:45 | Pending
|  | One world chemistry project analysing and download required files | 17:00 | 19:30 | Completed
2016-05-23 | Santosh | ETS site Testing | 10.00am | 1.30pm | Pending
|  | ETS site Testing | 2.30pm | 4.00pm | Completed
|  | XYGET document for 1st phase (Search option) | 4.30pm | 7.10pm | Pending
2016-05-23 | Siva Rama Kannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Learned ORM concept and MVC ,MVT in django | 10.00 AM | 1.30 PM | Completed
|  | Learned about how to connect mysql to python | 2.30 PM | 3.30 PM | Completed
|  | Configuring mysql to python | 3.30 PM | 7.30 PM | In progress
2016-05-23 | Thangamariappan | Typing test | 9:30 | 10:30 | completed
|  | Quikr Responsive, | 10:30 | 18:30 | In progress
radio button,comment box,text alignment
2016-05-23 | Velpandi | Typing Test | 9:30 | 10:30 | Completed
|  | Working on banner part content in Pricing in InvoiceGenerator | 10:30 | 13:30 | Completed
|  | Refer the startbootstrap.com to set the content in Pricing in invoice generator. | 14:30 | 16:30 | Completed
|  | Working on content part in Pricing in invoice generator. | 16:45 | 19:00 | Completed
2016-05-23 | Vignesh | Attended typing test | 10.30am | 10.45am | completed
|  | Learned bootstrap classes and its usage | 10.45am | 11.30am | completed
|  | Worked in alignment issues in portfolio page | 11.30am | 1.30pm | completed
|  | Worked in ETS reponsive | 2.30pm | 7.30pm | pending(responsive issues)

## 20.05.2016
Date | Name | Task | Start time | End time | Status | Comment
2016-05-20 | Akila | Typing Skill | 09.45am | 10.55am | Completed
|  | Standup Meeting & fixed client page on Gt and the footer section | 11.10am | 01.40pm | Completed
|  | Continued Gt task on fixing technology page | 02.40pm | 04.50pm | Pending
|  | Git installation, Technology page on Gt | 05.10pm | 08.00pm | Pending
2016-05-20 | Balasubramaniam | typingtest | 9:30AM | 10:30AM | Completed
|  | Fixed some issuse in the bootstrap | 10:45AM | 11:35AM | Completed
|  | applied container and logo | 12:10PM | 1:30PM | Completed
|  | set the nave bar | 2:40PM | 3:36PM | Completed
|  | applied hover tag and set the size | 3:40PM | 4:45PM | Completed
|  | add button tag in the nav bar | 5:00PM | 6:45PM | Completed
|  | create responsive for this page | 6:50PM | 7:35PM | Completed
2016-05-20 | Barath | Worked on ETS MULTIPLE PAGE PROFILE | 10.00Am | 7.50PM | 5 page complted
|  | Worked on ETS WEB SLIDER | 4.00PM | 6.30PM | COMPLETED
|  | Designing V-Card to Chandu(Marketing Manager) | 6.30PM | 6.40PM | COMPLETED
2016-05-20 | Kalai | Attended standup meeting, Started to analyze the fixido commerce modules and noted that concepts in document, guided django and python basics to siva | 11.15 am | 12.15 pm | completed
|  | Had call with prabhu for resell updation, he said some issues in resell and noted it | 12.15 pm | 1.45 pm | completed
|  | Analyzed the fixido remaining commerce models, control, paypal, logs, tracking,workers and noted that concepts in document | 2.50 pm | 4.00 pm | completed
|  | Shared knowledge about basic bootstrap to velpandi and bala, analzyed the fixido dependency for all the modules and noted it in document | 4.15 pm | 8.00 pm | completed
2016-05-20 | Madhivanan
2016-05-20 | Muthu | Typing test | 10:30 | 10:55 | Completed
|  | xyget admin - post advertisement view and delete option | 10:55AM | 11:20 | Pending
|  | standupmeeting and tea break | 11:20 | 11:40
|  | xyget admin - post advertisement view and delete option | 12:00 | 13:30 | Completed
|  | xyget admin - user product - view option | 14:30 | 18:45 | Completed
|  | Train to akila and madhi about version control | 18:45 | 20:00 | Completed
2016-05-20 | Santosh | Resell testing in admin side | 9.45am | 1.40pm | Pending
|  | Resell testing in admin side | 2.15pm | 5.30pm | Pending
|  | Oozaaoo responsive testing cycle 2 | 5.30pm | 6.30pm | Completed
|  | Resell testing in admin side | 6.30pm | 7.40pm | Pending
2016-05-20 | Siva Rama Kannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Fixing mail function issues in oozaaoo and slider issues for responsive | 10.00 AM | 1.00 PM | Completed
|  | Learning about python like how to set enviromental variables,and installing supporting packages | 1.00 PM | 1.30 PM | In progress
|  | Implementing hover function in services section of index page for ETS | 2.30 PM | 3.00 PM | Completed
|  | Adding images to slider in index page for ETS | 3.00 PM | 3.30 PM | Completed
|  | Implementing technologies in aboutus section of index page for ETS | 3.30 PM | 10.00 PM | Completed
Removing Technologies slider in contactus form of index page for ETS
2016-05-20 | Thangamariappan | Typing test | 9:30 | 10:30 | completed
|  | Bootstrap Nav bar | 10:30 | 13:30 | completed
|  | Bootstrap Responsive nav bar | 15:00 | 21:00 | completed
2016-05-20 | Velpandi | Typing Test | 9:30 | 10:30 | Completed
|  | Worked on banner part in pricing in invoice generator | 10:30 | 11:30 | In Process
|  | Study the predefined classes in bootstrap and see examples | 11:45 | 12:30 | Completed
|  | See the examples in media queries and understand the when to use | 12:30 | 13:30 | Completed
|  | Study the HTML,CSS,Bootstrap,Jquery Quiz questions. | 15:00 | 16:30 | Completed
|  | See the google I/O16 concepts | 16:45 | 18:30 | Completed
2016-05-20 | Vignesh | attended typing test | 9.45am | 10.00am | completed
|  | Learned bootstrap from tutorial point and worked out examples | 10.00am | 12.00pm | completed
|  | worked in issues in service page and about us page | 12.00pm | 1.30pm | completed
|  | worked in sample page using bootstrap and included ETS code to get responsiveness | 2.30pm | 7.00pm | pending | (responsive not coming in proper alignment)

## 19.05.2016
Date | Name | Task | Start time | End time | Status | Comment
2016-05-19 | Akila | Typing Lesson | 09.40am | 10.15am | Completed
|  | Standup Meeting & Bootstrap documentation review | 10.20am | 01.40pm | Completed
|  | Media Query documentation & Bootstrap review | 02.35pm | 05.10pm | Completed
|  | KT on Bootstrap from Deepak | 05.15pm | 07.40pm | Completed
2016-05-19 | Balasubramaniam | typingtest | 9:30AM | 10:30AM | Completed
|  | set the link for the bootstarp | 10:45AM | 11:30AM | Completed
|  | study meta tags,jumbotron | 12:05PM | 1:30PM | Completed
|  | studt nav bar fixed, nav bar satic | 2:45PM | 3:30PM | Completed
|  | study container class | 3:45PM | 4:45PM | Completed
|  | nav-bar-header | 5:00PM | 6:45PM | Completed
2016-05-19 | Barath | Worked on ETS PORTFOLIO 4th Page | 9.30Am | 11.30AM
|  | Add Content and Made Minnor Correction with Color Alingment |  |  | COMPLETED
|  | Worked on ETS MULTIPLE PAGE PROFILE | 11.3 | 5.00PM
Designing About Us Page with New Pattern
|  | Designing Web & DevelopmentPage with New Pattern |  |  | COMPLETED
|  | Worked On Cotton Logo | 5.00PM | 5.30PM
Making COTTON HOUSE Logo
|  | Preparing Logo list what are all We have created |  |  | COMPLETED
|  | Designing V-Card to Chandu(Marketing Manager) | 5.30PM | 6.00PM
|  | Worked on ETS MULTIPLE PAGE PROFILE | 6.00PM | 7.15PM | Pending
2016-05-19 | Kalai | Django: Configured django 1.4.3 version and pip requirements in already created virtual environment | 11.15 am | 12.30 pm | pending (because of error) | Got error in admin packages while run fixido project, django packages is not supported correctly
|  | Tried to clear the admin template error, followed some steps like moved the admin templates folder from one location to django contrib location, once cleared this template error, admin panel raises template tags error in all modules, then tried to fix that | 12.30 pm | 1.30 pm | pending (because of error) | Eventhough checked and corrected the django packages, still this error raises
|  | Created the new virtual environment and configured all the django packages with fixido pip requirements, while run fixido project getting GEO error and language translation error, tried to fix that | 3.00 pm | 5.30 pm | completed
|  | Analyzed the fixido actors and leads class modules for creating documentation and created document for ricso | 6.00 pm | 8.00 pm | completed | document created for actor and leads modules
2016-05-19 | Madhivanan
2016-05-19 | Muthu | Typing test and send thalapakattu file to vinoth. | 10:00 | 11:10 | Completed
|  | standupmeeting and tea break | 11:10 | 11:30
|  | Interview | 11.30 AM | 12:30 | Completed
|  | xyget admin - post advertisement add,edit and delete option | 12:30 | 13:30 | Pending
|  | xyget admin - post advertisement add,edit and delete option | 15:00 | 17:15 | Pending | Add completed with refresh
|  | Interview | 17:15 | 5.55 PM
|  | xyget admin - post advertisement add,edit and delete option and upload to server | 18:00 | 20:00 | Pending | Add and edit complete.view and delete is pending
2016-05-19 | Santosh | Resell testing | 9.30am | 11.30am | Pending
|  | Oozaaoo responsive testing cycle 2 | 12.00pm | 1.30pm | completed | But issues persist
|  | Resell testing | 3.00pm | 7.00pm | Pending
2016-05-19 | Siva Rama Kannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Learning django and how to install it. | 10.00 AM | 11.00 AM | Completed
|  | Fixing issues in header part for responsive | 11.00 AM | 1.30 PM | Completed
|  | Fixing mobile num validation issues and image slider issues in oozaaoo | 2.30 PM | 4.:30 PM | Completed
|  | Fixing email validation issues in oozaaoo | 4.30 PM | 5.:00 PM | In progress
|  | Meetnig with Deepak | 5.00 PM | 7.30 PM | Completed
2016-05-19 | Thangamariappan
|  | Typing test | 9:30 | 10:30 | completed
|  | Bootstrap Tutorial | 10:30 | 17:30 | pending | need more knowledge
|  | Bootstrap Examples | 18:00 | 2:00 | pending
2016-05-19 | Velpandi | Typing Test | 9:30 | 10:30 | Completed
|  | Study the some confused basics concepts in bootstrap | 10:30 | 11:30 | Completed
|  | Worked on navbar in pricing in invoicegenerator. | 11:30 | 13:30 | Completed
|  | Study the concept:Grid System,and see some examples | 14:30 | 16:30 | In Process
|  | Doubt Session with Deepak | 17:00 | 19:45 | Completed
2016-05-19 | Vignesh | Attended typing test | 10.00am | 10.15am | completed
|  | Learned bootstrap classes and nav bar functions | 10.15am | 1.30pm | completed
|  | Worked in slider function | 2.30pm | 4.30pm | completed
|  | Worked in mouse hover function in slider | 4.30pm | 5.15pm | pending
|  | Attended meeting with deepak sir | 5.15pm | 7.30pm | completed

## 18.05.2016
Date | Name | Task | Start time | End time | Status | Comment
2016-05-18 | Akila | Typing Lesson | 10.10am | 11.00am | Completed
|  | Standup Metting & Started Gt project task on fixing home banner slider and navigation menu | 11.10am | 01.55pm | Pending
|  | Done slider for home banner images | 03.10pm | 05.35pm | Completed
|  | Fixing Text wrap on home banner when window shrinks | 05.40pm | 06.25pm | Pending | As per the discussion will continue to work on GT responsive site from tomorrow
|  | KT from Deepak, Project review with Sastha & Madhivanan | 06.30pm | 07.15pm | Completed
2016-05-18 | Balasubramaniam | typingtest | 9:30AM | 10:30AM | Completed | Used to increase typing speed
|  | Fixed some issuse for this page | 10:45AM | 11:30AM | Completed
|  | refer the bootstarp for the tutorial | 12:00PM | 1:15PM | Completed
|  | study and try media query for the HTML&CSS | 2:45PM | 4:00PM | Completed
|  | study lg,sd,xs | 4:30PM | 6:00PM | Completed
|  | study minwidth,max width,desktop and mobile view | 6:05PM | 7:00PM | Completed
2016-05-18 | Barath | Working on Ricsco change has been done | 9.30Am | 11.30AM | COMPLETED
|  | Working on ETS PORTFOLIO change has been done | 11.30AM | 1.30PM | COMPLETED
|  | Working vector image for ETS SITE | 2.30PM | 5.00PM | COMPLETED
|  | Working on ETS PORTFOLIO NEW PAGE(4th) | 5.00PM | 8.30PM | COMPLETED
2016-05-18 | Kalai | Django: Configured django 1.4.3 version and pip requirements in already created virtual environment | 11.15 am | 12.30 pm | pending (because of error) | Got error in admin packages while run fixido project, django packages is not supported correctly
|  | Tried to clear the admin template error, followed some steps like moved the admin templates folder from one location to django contrib location, once cleared this template error, admin panel raises template tags error in all modules, then tried to fix that | 12.30 pm | 1.30 pm | pending (because of error) | Eventhough checked and corrected the django packages, still this error raises
|  | Created the new virtual environment and configured all the django packages with fixido pip requirements, while run fixido project getting GEO error and language translation error, tried to fix that | 3.00 pm | 5.30 pm | completed
|  | Analyzed the fixido actors and leads class modules for creating documentation and created document for ricso | 6.00 pm | 8.00 pm | completed | document created for actor and leads modules
2016-05-18 | Madhivanan
2016-05-18 | Muthu | Typing test and interview | 10:00 | 11:10 | Completed
|  | Business gateway international configuration with YII framework | 11:10 | 13:45 | Pending | Convert to multiple sql file into single sql file which is not supported. So that find out problem
|  | Went to atomicka for thalapakattu KT and printer configuration | 14:45 | 17:30
|  | Business gateway international configuration with YII framework | 17:30 | 20:00 | Completed | Configuration is finished but its throwing error.if I fix one error, raise another issue.
2016-05-18 | Santosh | Resell testing with banner added | 10.00am | 12.00pm | Pending
|  | Analyze the Springloops | 12.00pm | 1.45pm | Pending
|  | Analyze the Fixido site for document | 3.00pm | 6.30pm | completed
|  | Create a task status for my reference | 6.45pm | 7.45pm | completed
2016-05-18 | Siva Rama Kannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Fixed issues in bug sheet of ETS like validation,design break issues,adding images to slider | 10.00 AM | 1.30 PM | Completed
|  | Adding table to database for yii framework and discussed with kalai about django framework | 2.30 PM | 4.45 PM | Completed
|  | Fixing issues in oozaaoo responsive | 5.00 PM | 7.30 PM | Completed
2016-05-18 | Thangamariappan | Project Name: Task details
|  | Typing test | 9:30 | 10:30 | completed
|  | Quikr psd file to html | 10:30 | 20:30 | completed
Header,Logo,search box
2016-05-18 | Velpandi | Typing Test | 9:30 | 10:30 | Completed
|  | Refer the tutorialspoint.com for grid system in a bootstrap. | 10:30 | 11:30 | Completed
|  | Refer the tutorialspoint.com for bootstrap demos and grid options in a bootstrap. | 11:30 | 13:30 | Completed
|  | Study the media query and how to implement that in a bootstrap | 14:45 | 16:30 | Completed
|  | Working on Pricing in InvoiceGenerator | 16:30 | 19:00 | In Process
2016-05-18 | Vignesh | Attended typing test | 10.00am | 10.15am | completed
|  | worked in issues in service page | 10.15am | 1.30pm | completed
|  | Added plugin for slider in our team page | 2.30pm | 3.30pm | pending (getting issue)
worked in contact us page for map function using scroll
|  | and responsiveness | 3.30pm | 7.30pm | pending

## 17.05.2016
Date | Name | Task | Start time | End time | Status | Comment
2016-05-17 | Akila | Typing lesson | 10.00am | 11.00am | Completed
|  | Fixing technology page images for GT | 11.10am | 12.20pm | Completed
|  | Got updated code for GT from Sastha and started working on fixing home page | 12.30pm | 04.30pm | Pending
|  | Analysed and updates issues list in GT that need to be fixed | 04.55pm | 06.30pm | Completed
|  | Fixed home page banner for updated GT | 06.40pm | 07.40pm | Completed
2016-05-17 | Balasubramaniam | Permission
|  | typingtest | 3:30PM | 4:30PM | Completed | increase speed and control typing mistakes.
|  | Responsive Embeds,Creating a Jumbotron,Jumbotron Inside Container,Jumbotron Outside Container, | 5:00PM | 6:25PM | Completed | Used to create the Jumbotron.
|  | Rounded Corners,Circle,Thumbnail,Responsive Images,Image Gallery. | 6:30PM | 7:10PM | Completed | Used to set the image gallery.
2016-05-17 | Barath | Worked on ETS WEBSITE | 10.00Am | 3.30PM | COMPLETED
Making vector image for Math and Kumaran for ETS SITE
|  | Working on Ricsco PORT FOLIO NEW DEASIGN | 3.30PM | 7.30PM | COMPLETED
Here I have changed theme and color combination
2016-05-17 | Kalai | Resell: Fixed resell cycle2 high priority issues which is given by santhosh | 11.20 am | 2.00 pm | completed
|  | Resell: Fixed resell high priority issues which I found as my own in post ad and myprofile | 3.00 pm | 5.00 pm | completed
|  | Resell: Fixed cycle 1 issues low priority issues which is given by santhosh | 5.15 pm | 7.00 pm | completed
|  | Resell: Moved the updated code in server and tried to fix issues in userpofile admin module, refer fixido user module for trying to fix issues in resell user admin module | 7.00 pm | 8.00 pm | pending
2016-05-17 | Madhivanan
2016-05-17 | Muthu | discuss with bala about wellocity issue | 10.50 AM | 11.00 AM
|  | xyget remaining issue fixing as per last updated bug sheet | 11.00 PM | 1.30 PM | Complete | 2 issues fixed out of 9 issues
|  | xyget remaining issue fixing as per last updated bug sheet and upload to server | 2.45 PM | 7.30 PM | Complete | 6 issues fixed out of 9 issues
2016-05-17 | Santosh | Resell testing in premium added | 12.15am | 1.45pm | Pending
|  | Resell testing in premium added | 3.00pm | 4.30pm | completed
|  | ETS site Testing | 5.00pm | 7.20pm | completed
2016-05-17 | Siva Rama Kannan | Permission
|  | Typing test | 3.45 PM | 4.15 PM | Completed
|  | Fixed issues in bug sheet of ETS like validation,design break issues | 4.30 PM | 7.00 PM | In progress
2016-05-17 | Thangamariappan | Typing test | 9:45 | 10:45 | completed
|  | Quikr psd file to html | 11:00 | 19:00 | pending
Header to body content
Logo
2016-05-17 | Velpandi | Permission
|  | Typing Test | 15:30 | 16:30 | Completed | Useful to increase typing speed.
|  | Refer the getbootstrap.com for components in a bootstrap. | 16:45 | 17:30 | Completed | All icons require a base class and individual icon class
|  | See the Some examples for set the navigation bar with responsive. | 17:30 | 7.00 PM | Completed | This example shows how the default, static navbar and fixed to top navbar work
2016-05-17 | Vignesh | attended typing test | 9.30AM | 10.00AM | completed
|  | worked in service page for responsive | 10.00am | 1.30pm | pending
|  | worked in image slider function | 2.30pm | 5.30pm | completed
|  | worked in contact us page for user login | 5.30pm | 7.30pm | completed

## 13.05.2016
Date | Name | Task | Start time | End time | Status | Comment
2016-05-13 | Akila | Typing lesson | 09.50am | 10.50am | Completed
|  | Task on Technologies page in GT project | 11.00am | 11.30am | Pending
|  | Standup meeting | 11.25am | 11.50am | Completed
|  | Task on fixing technology page images for GT | 12.00pm | 05.30pm | Pending
2016-05-13 | Balasubramaniam | Study Bootstrap: Bootstrap Grid System,Grid Classes | 10:45AM | 11:30AM | Completed | some issuses are occuring the boostrap.
|  | Three Equal Columns,Bootstrap Text/Typography,Contextual Colors and Backgrounds. | 11:50AM | 12:30PM | Completed | fixed my issuse then try to study for this concepts.
|  | Bootstrap Basic Table,Striped Rows,Bordered Table,Hover Rows,Condensed Table. | 12:35PM | 1:30PM | Completed | this structure are hard.
|  | Responsive Tables,Contextual Classes, | 3:00PM | 3:50PM | Completed | its used to know the allignment of the tables.
|  | Bootstrap Image Shapes: Rounded Corners,Circle,Thumbnail,Responsive Images,Image Gallery. | 4:05PM | 5:15PM | Completed | its hard and try to learn this concepts.
|  | Responsive Embeds,Creating a Jumbotron,Jumbotron Inside Container,Jumbotron Outside Container, | 5:30PM | 6:25PM | Inprogress | Used to create the Jumbotron.
2016-05-13 | Barath | Corrections work on ETS PORTFOLLIA | 9.45AM | 11.30AM | Completed
Work on Etds Portfolio, Changing color Module
and align the text as proper setting
|  | WORKED ON ETS WEB SIT | 2.30PM | 6.15PM | Completed
Change the eventswat web site and add any other image
2.On hover the hexagon replace it as image
|  | WORKED ON RICSCO PORFILO | 6.15PM | 7.00PM | Completed
change the dummy name as Ricsco and did alignment correction
2016-05-13 | Kalai | General meeting with sastha, Resell: Fixed issues in post ad form | 10.50 am | 11.45 pm | completed
|  | Resell: Fixed cycle 1 issues which is given by santhosh | 11.45 pm | 1.55 pm | completed
|  | Resell: Validated the embedded video in post ad form and displayed in detail page with checking some conditions | 2.05 pm | 3.05 pm | completed
|  | Resell: Fixed cycle2 issues which is given by santhosh, Fixed issues in admin side banner module | 3.00 pm | 7.50 pm | completed
2016-05-13 | Madhivanan | Preparing tasks for the day | 10.10 AM | 10.30 AM | Completed
|  | Typing test | 10.30 AM | 11.00 AM | Completed
|  | Discussion with Kalai & Muthu about Wellocity issues | 11.00 AM | 11.30 AM | Completed
|  | Standup meeting | 11.30 AM | 12.00 PM
|  | Content Preparation for ETS | 12.00 PM | 1.15 PM | Pending
|  | Mail Sent to Devi mam about Infom atomicka site & zend framework | 1.15 PM | 1.30 PM | Completed
|  | Content Preparation for ETS | 1.30 PM | 2.30 PM | Pending
|  | Content Preparation for ETS | 3.30 PM | 4.30 PM | Pending
|  | Discussion with Deepak, Sastha & HR about Management | 4.30 PM | 5.30 PM
|  | Content Preparation for ETS | 5.30 PM | 6.40 PM | Completed
|  | Daily Report Sheet updation | 6.40 PM | 7.20 PM | Completed
|  | Had call with Cotton house client for appointment | 7.20 PM | 7.35 PM | Completed
|  | Prepared Project tracking sheet | 7.40 PM | 9.00 PM | Completed
2016-05-13 | Muthu | Typing test | 10.00 AM | 10.45 AM | Completed
|  | Discussion with Sastha about today task | 10.45 AM | 11.00 AM
|  | Change mail configuration to asai and gayathri | 11.00 AM | 11.30 AM | Completed
|  | standup meeting | 11.30 AM | 12.00 PM
|  | Xyget bug fixing as sended mail by sastha | 12.00 PM | 1.30 PM | Pending | 5 issues completed
|  | Xyget bug fixing as sended mail by sastha | 2.30 PM | 4.30 PM | Pending | 4 issues completed
Permission
2016-05-13 | Nithya | Typing test | 9:40 | 10:15 | Completed
|  | Standup meeting,GT banner design | 10:15 | 13:45 | Pending
|  | GT banner design | 15:00 | 16:15 | Pending | Location banner part is pending
Permission
2016-05-13 | Ramya
Absent
2016-05-13 | Santosh | ETS site Testing | 9.30am | 10.30pm | Pending | Site not completed
|  | Resell site testing with prevoius issues | 11.30am | 1.45pm | completed
|  | Resell site testing - cycle 2 | 3.00pm | 6.30pm | Pending
2016-05-13 | Thangamariappan | Header and image banner using Html and css | 12:00pm | 7:30pm | completed
Header-dropdown,hover
Logo,search Box
Static image
2016-05-13 | Siva Rama Kannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Fixing validation issues in ETS | 10.00 AM | 11.00 AM | Completed
|  | Adding scroll option for Technologies logo | 11.00 AM | 1.30 PM | Completed
|  | Changing images in index and portfolio page of ETS | 2.30 PM | 6.30 PM | Completed
|  | Adding content in ETS and links for social icons | 6.30 PM | 7.30 PM | Completed
2016-05-13 | Velpandi | Typing Test | 9:30 | 10:30 | Completed | Useful to increase Typing speed
|  | Study the Bootstrap: BS Gridbasic,BS Navbar,BS Tables | 10:30 | 11:30 | Completed | Know the Structure of that.
|  | Study BS Jumbotran,BS Buttons,BS Alerts | 11:30 | 12:30 | Completed | Attention to some extra content.
|  | Study the Media Query in BS | 12:30 | 13:40 | Completed | Used to set contents are visible for all screen display
|  | See the Some examples for creating Responsive web page. | 15:00 | 16:30 | Completed | Useful to know some basics.
|  | Create the header for the Responsive web page to Pricing in invoice generator | 16:30 | 18:30 | In Process
2016-05-13 | Vignesh | attended typing test | 10.00am | 10.15am | completed
|  | worked in contact us page | 10.15am | 1.30pm | completed
|  | worked in issue in service page responsive | 2.30pm | 4.30pm | pending
|  | worked in alignment issues in service and our team page | 4.30pm | 7.30pm | completed

## 12.05.2016
Date | Name | Task | Start time | End time | Status | Comment
2016-05-12 | Akila | Typing lesson | 09.50am | 11.00am | Completed
|  | Standup meeting & Done some alignment issues on previous task as insisted by Sastha for resubmission | 11.00am | 11.45am | Completed
|  | Started on Bootstrap documentation | 11.45am | 1.50pm | Pending
|  | Started on Bootstrap documentation with examples & tried out header part for mobile first style | 3.00pm | 04.00pm | Completed
|  | Started analyzing GT project code with nithya | 04.00pm | 06.30pm | Completed
|  | GT project work | 06.30pm | 07.30pm | Pending
2016-05-12 | Balasubramaniam | Typing Test | 9:30AM | 10:30AM | Completed
|  | xyget currection work | 10:45 | 11:10AM | Completed
|  | study css | 11:10AM | 11:30AM | Completed
|  | standup meating | 11:55Am | 12:10PM | Completed
|  | discuss with madhivanan | 12:20PM | 12:40PM | Completed
|  | study css | 12:45PM | 1:30PM | Completed
|  | study boostrap | 2:45PM | 6:25PM | Inprocess
2016-05-12 | Barath | LOGO DESIGN FOR RICSCO | 10.00Am | 6.30pm | Completed | Logo has been freezed, have to fine tune on that
|  | Corrections work on ETS PORTFOLLIA | 6.30PM | 7.15pm | Completed | CORRECTION MADE ON INNER PAGE
2016-05-12 | Kalai
Absent
2016-05-12 | Madhivanan | Typing Test | 10.45 AM | 11.10 AM | Completed
|  | Xyget retesting | 11.10 AM | 1.30PM | Pending
|  | Wellocity Call with Bala & correction checking | 1.30 PM | 2.30 PM | Completed
|  | Daily Report sheet updation | 3.30 PM | 4.00 PM | Pending
|  | Discuss with Deepak about Task details for resources | 4.00 PM | 5.00 PM
|  | Wellocity Retesting | 5.00 PM | 6.30 PM | Completed
|  | Task assign to Intent | 6.30 PM | 7.00 PM | Completed
|  | Daily Report sheet updation & format send to all | 7.00 PM | 8.00 PM | Completed
2016-05-12 | Muthu | typing test | 10.30 AM | 11.30 AM | Completed
|  | Thalapakattu admin side error fixing | 11.30 AM | 12.00 PM | Pending | Holded by Sastha
|  | Atomicka site performance testing and fixing site loading time | 12.00 PM | 1.30 PM | Completed
|  | Atomicka site performance testing and fixing site loading time | 2.30 PM | 7.00 PM | Completed
2016-05-12 | Nithya | Typing test | 11:00 | 11:30 | Completed
|  | Standup meeting,shared the basic concepts about ui with thangam,GT design | 11:30 | 14:00 | In Progress
|  | GT design | 15:00 | 18:50 | In Progress
2016-05-12 | Ramya | atteded typing test | 11.05am | 11.30am
|  | attended standup meeting | 11.35am | 11.45am
|  | fixed issues suggested by madhivanan and santhosh | 11.50am | 5.30pm | completed
|  | analyzed and started to implement positng products in admin side | 5.30pm | 6.30pm | in progress
2016-05-12 | Santosh | Resell testing with old issues | 11.00am | 1.45pm | Pending
|  | XYGET teested in Madhi's bug report | 3.00pm | 7.00pm | completed
2016-05-12 | Siva Rama Kannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Learning AJAX concept | 10.00 AM | 11.00 AM
|  | Implementing ajax concept task for thalapakktu like adding parameters dynamically | 11.00 AM | 5.00 PM | In progress
|  | Auto suggestion in jquery | 5.00 PM | 7.00 PM | Completed
2016-05-12 | Velpandi | Typing Test | 9:30 | 10:30 | Completed
|  | Register the details Xyget site | 10:30 | 12.00 PM | Completed
|  | Study the basics in bootstrap | 12:00 | 13:40 | Completed
|  | Enter the details for register company in Xyget | 15:00 | 16:30 | Completed
|  | Study the bootstrap in w3shcools web site | 16:30 | 18:30 | In Process
2016-05-12 | Vignesh | attended typing test | 10.00am | 10.15am | completed
|  | worked in alignment issues in portfolio page and services page | 10.15am | 1.30pm | completed
|  | learned how to add map in a site and add functions to it | 2.30pm | 4.30pm | completed
|  | workes on issue in portfolio page for mouse hover effects | 4.30pm | 7.00pm | pending

## 11.05.2016
Date | Name | Task | Start time | End time | Status | Comment
2016-05-11 | Akila | Typing lesson | 10.00am | 10.45am | Completed
|  | Started review on Bootstrap documentation | 11.00am | 01.45pm | Pending
|  | Tried out some examples in bootstrap | 3.00pm | 07.10pm | Completed
2016-05-11 | Balasubramaniam | Typing Test | 9:30AM | 10:30AM | Completed
|  | some currections for the page | 10:45AM | 11:10AM | Completed
|  | study css | 11:15AM | 12:00PM | Completed
|  | xyget work | 12:30PM | 5:30PM | Completed
|  | xyget work | 5:45PM | 7:15PM | Completed
2016-05-11 | Barath | LOGO DESIGN FOR RICSCO | 10.00Am | 4.00PM
|  | FB POST FOR FRESHERS | 4.00PM
2016-05-11 | Kalai | Fixed issues in post ad form video upload validation and logical issues | 11.00 am | 12.15 pm | completed
|  | Discussed the resell updation with prabhu on phone call and shared about it with sastha | 12.15 pm | 2.00 pm | completed
|  | Analyzed the issues except chat and send the timeline to sastha | 3.00 pm | 3.40 pm | completed
|  | Fixed issues in google banner module and also from bug report which is given by santhosh, Search the document to create webmail in exobytes cpanel for creating resell email account | 3.40 pm | 6.45 pm | pending
2016-05-11 | Madhivanan | Typing Test | 10.30 AM | 10.50 AM | Completed
|  | Xyget Testing | 10.50 AM | 11.40 AM | Pending
|  | Daily Report sheet updation | 11.40 AM | 12.10 PM | Pending
|  | Meeting with Sastha about projects status | 12.10 PM | 12.40 PM | Pending
|  | Xyget Testing | 12.40 PM | 1.45 PM | Pending
|  | Mail sent to Mr. Shunmuga about thalapakattu status | 1.45 PM | 2.15 PM | Completed
|  | Xyget Testing | 3.30 PM | 4.30 PM | Completed
|  | wellocity testing | 4.30 PM | 8.00 PM | Completed
|  | Daily Report sheet updation | 8.00 PM | 8.30 PM | Completed
2016-05-11 | Muthu | Typing Test | 10.00 AM | 10.45 AM | Completed
|  | Thalapakattu admin part analyzing | 10.45 AM | 11.30AM | Completed | Error occurred
|  | Correct Thalapakattu admin side code | 11.30 AM | 1.30 PM | Pending
|  | Correct Thalapakattu admin side code | 2.45 PM | 7.45 PM | Pending
2016-05-11 | Nithya | Typing test | 9:50 | 10:30 | Completed
|  | Stand up meeting,clarified the doubts for akila and verified her code,helped vignesh for design issues,GT html design | 10:30 | 13:45 | Pending | GT is in process
|  | GT html design,helped siva and vignesh,wellocity popup issues | 15:00 | 19:00 | Pending | GT is in process
2016-05-11 | Ramya | attended typing test | 10.05am | 10.30am
|  | fixed issues inbug report | 10.35am | 11.05am | completed
|  | attended standup meeting | 11.10am | 11.20am
|  | procceded with the issues listed by madhivanan in bugreport | 11.20am | 7.10pm | completed
2016-05-11 | Santosh | XYGET document with changes | 9.15am | 4.40pm | completed
|  | Resell testing cycle 2 | 5.15pm | 6.00pm | Pending
|  | wellocity testing for one issue | 6.00pm | 6.30pm | completed
|  | Resell testing cycle 2 | 6.30pm | 7.00pm | Pending
2016-05-11 | Siva Rama Kannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Implemened md5 option in login module for password field | 10.00 AM | 11.00 AM | Completed
|  | Implemented form validation in contactusform of ETS | 11.00 AM | 1.45 PM | Completed
|  | Implemented Mail sending function in contactusform of ETS | 2.45 PM | 6.00 PM | Completed
|  | Implenting ajax calling funtion with jquery | 6.00 PM | 6.30 PM | In progress
2016-05-11 | Velpandi | Typing Test | 9:30 | 10.30 AM | Completed
|  | Study the CSS | 10:30 | 12:00 | Completed
|  | Set the payments parts for pricing in invoice | 12:00 | 13:50 | Completed
|  | Set the freeplan content in pricing in invoice | 15:00 | 16:30 | Completed
|  | Set the footer part for Pricing in invoice | 16:30 | 18:30 | Completed
2016-05-11 | Vignesh | worked in ets site slider function for responsive | 10.00am | 1.00pm | completed
|  | worked on issues in home page | 1.00pm | 2.00pm | completed
|  | worked in about us page responsive using media query | 3.00pm | 7.00pm | completed
|  | Have to work on scroll function in ets site |  |  | pending

## 10.05.2016
Date | Name | Task | Start time | End time | Status | Comment
2016-05-10 | Akila | Typing lessons | 09.55am | 10.55am | Completed
|  | Task completion | 10.56am | 12.40pm | Pending
|  | Meeting with sastha | 12.40pm | 01.40pm | Completed
|  | Working on Task | 03.00pm | 06.30pm | Completed
|  | Meeting with HR | 06.30pm | 07.00pm | Completed
|  | Task completion | 07.00pm | 08.40pm | Completed
2016-05-10 | Balasubramaniam | Typing Test | 9:30AM | 10:30AM | Completed
|  | form creation | 10:45AM | 11:30AM | Completed
|  | 2nd task completed | 11:30AM | 12:15PM | Completed
|  | Meeting | 12:20PM | 1:50PM | Completed
|  | study to html and css | 3:10PM | 6:00PM | Inprocess
|  | change some currections for the tasks | 6:10 | 7:10PM | Completed
2016-05-10 | Barath | DESIGNING ETS PORTFOLLIO | 10.00Am | 7.29PM | completed
|  | Designing Correction on ETS WEBSITE | 11.00Am | 1.30PM | completed
2016-05-10 | Kalai | Fixed issues in resell advertisement own and google ads in all pages | 11.10 am | 1.45 pm | completed
|  | Fixed issues in resell from bug report which is given by santhosh, Fixed the issues in detail page embedded video display | 2.45 pm | 6.30 pm | pending
|  | General Meeting with HR and our team, discussed python and django basics with siva, helped to ramya to fix issues in XYGET, Moved the XYGET updated code in server, continued to fixed the issues in detail page embedded video display | 6.45 pm | 8.10 pm | completed
2016-05-10 | Madhivanan | Thalapakattu Discussion with Sastha & Muthu | 11.15 AM | 11.30 AM | Completed
|  | Xyget Testing | 11.30 AM | 12.30 PM | Pending
|  | Mail sent to Vinoth regarding Thalapakattu | 12.30 PM | 12.40 PM | Completed
|  | Xyget Testing | 12.40 PM | 2.00 PM | Pending
|  | Typing test | 2.30PM | 3.00PM | Completed
|  | Daily Report Sheet Updation | 3.00 PM | 3.40 PM | Completed
|  | Discussion with Deepak about Xyget Documentation | 3.40 PM | 4.30 PM | Completed
|  | Xyget Testing | 4.30 PM | 8.00 PM | Pending
|  | Daily Report Sheet Updation | 8.00 PM | 8.20 PM | Completed
2016-05-10 | Muthu | Typing Test | 10.00 AM | 10.30 AM | Completed
|  | Analysing and Make flow structor thalapakattu restaurent moudle | 10.30 AM | 2.00 PM | Pending
|  | Make DB structor for thalapakattu restaurant module | 3.00 PM | 4.30 PM | Completed
|  | Went to atomicka for meeting about thalapakattu new restaurant module | 5.10 PM | 8.30 PM
2016-05-10 | Nithya | Typing test | 10:00 | 10:40 | Completed
|  | Standup meeting,ETS responsive design | 10:40 | 14:00 | In Progress
|  | ETS responsive design,fixed resell design issues | 15:15 | 20:40 | Completed
2016-05-10 | Ramya | atteded typing test | 10.10am | 10.30am
|  | started to fix issues listed in the bugreport | 10.15am | 12.10pm | completed
|  | attended standup meeting | 12.10pm | 12.30pm
|  | started to fix remaining issues listed in the bugreport | 12.30pm | 5.30pm | completed
|  | proceeded with multiple image uploading | 5.30pm | 6.30pm
|  | attended a meeting with hr and team | 6.30pm | 7.25pm
|  | procceded with the issues listed by madhivanan | 7.30pm | 8.30pm | completed(multiple image uploading is in progress)
2016-05-10 | Santosh | Front end completed for XYGET document | 9.00am | 5.00pm | completed
|  | Starting new document with some changes in XYGET. | 5.00pm | 7.30pm | Pending
2016-05-10 | Siva Rama Kannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Fixing resposive issues in porfolio page of ETS | 10.00 AM | 10.30 AM | Completed
|  | Meeting with sastha and deepak | 10.30 AM | 1.40 PM | Completed
|  | Implementing Admin Login module for Thalapakattu | 2.40 PM | 4.00 PM | Completed
|  | Implementing textbox validation like accepts only alphabet,number | 4.00 PM | 4.45 PM | Completed
|  | Discuss with kalai about python and django | 5.00 PM | 6.30 PM | Completed
2016-05-10 | Velpandi | Typing Test | 9:30 | 10:30
|  | set the header part for my second task | 10:30 | 12:20
|  | Meeting | 12:20 | 13:50
|  | Set the background image for my second task | 15:00 | 16:30
|  | Study HTML | 16:30 | 18:30
2016-05-10 | Vignesh | worked in ets site menu hide/show function using jquery | 9.45am | 1.00pm | completed
|  | attended meeting with Sastha sir | 1.00pm | 2.15pm
|  | worked in service page for alignment and responsive | 3.15pm | 6.30pm | pending

## 09.05.2016
Date | Name | Task | Start time | End time | Status | Comment
2016-05-09 | Akila | Typing test | 09.50am | 10.15am | Completed
|  | Meeting with Nithya | 10.15am | 10.50am | Completed
|  | Standup Meeting | 11.20am | 11.30am | Completed
|  | Working on Task | 10.50am | 01.55pm | Pending
|  | Working on Task | 3.00pm | 07.00pm | Pending
|  | KT from Deepak | 07.00pm | 08.44pm | Completed
2016-05-09 | Balasubramaniam | Typing Test | 9:2AM | 10:00AM | Completed
|  | Meeting | 10:15AM | 10:55 | Completed
|  | remove scroller for the webpage | 11:30AM | 12:15PM | Completed
|  | start new task | 12:30 | 1:30PM | Inprocess
|  | set header page | 3:00PM | 4:00PM | Completed
|  | set background image | 4:00PM | 4:50PM | Completed
|  | form creation | 05:15PM | 6:00PM | Completed
|  | gradient botton creation | 6:00PM | 6:30PM | Completed
2016-05-09 | Barath
Absent
2016-05-09 | Kalai | Fixed issues in resell from bug report which is given by santhosh | 11.00 am | 1.45 pm | completed
|  | Continued to fix the resell logical issues in admin | 2.45 pm | 4.00 pm | completed
|  | Traced and tried to fix the issues on chat history appending process for each and every product in both sender and receiver side | 4.15 pm | 7.40 pm | pending
2016-05-09 | Madhivanan | Daily Report Sheet Updation | 9.35 AM | 9.50 AM
|  | Typing test | 9.50 AM | 10.20 AM | Completed
|  | Thalapakattu Testing | 10.20 AM | 12.15 PM | Pending
|  | Xyget Testing | 12.15 PM | 12.45 PM | Pending
|  | Discussion with Sastha & Deepak | 12.45 PM | 1.15 PM |  | About Thalapakattu & Mobile app
|  | Xyget Testing | 1.15 PM | 2.00 PM | Pending
|  | Xyget Testing | 3.00 PM | 6.00 PM | Pending | Data feed
|  | Wellocity Correction | 6.00 PM | 6.40 PM | Completed
|  | Thalapakattu Testing | 6.40 PM | 8.00 PM | Pending
|  | Daily Report Sheet Updation | 8.00 PM | 8.30 PM | Completed
2016-05-09 | Muthu | Typing test | 10.00 AM | 10.30 AM | Completed
|  | Thalapakattu-Restaurant-Item add issue | 10.30 AM | 1.30 PM | Pending
|  | Thalapakattu-Restaurant-Item add issue and Cancel item issue | 2.30 PM | 8.00 PM | Pending | If I fix add issue, cancel issue is arise, & vice versa
|  | Thalapakattu-Restaurant-Item cancel issue and add item issue | 9.30 PM | 1.00 AM | Pending | If I fix add issue, cancel issue is arise, & vice versa
2016-05-09 | Nithya | Typing test | 9:50 | 10:10 | Completed
|  | meeting with intent about ui | 10:15 | 10:55
|  | Standup meeting,portfolio html design(ETS) | 11:00 | 13:50 | Completed
|  | Home page alignment and contact us part design | 15:00 | 19:30 | responsive is pending
2016-05-09 | Ramya | atteded typing test | 10.00am | 10.35am
|  | fixed issue on saving category based items while adding product | 10.40am | 11.20am | completed
|  | attended standup meeting | 11.25am | 11.45am
|  | fixed issues on related search based on products | 12.00pm | 1.30am | completed
|  | fixed some issues when city based searching for both products and advertisement | 3.05pm | 5.15pm | completed
|  | multiple image uploading(pending process) | 5.20pm | 6.00pm
|  | fixed wct issues | 6.10pm | 8.00pm | completed
2016-05-09 | Santosh
Absent
2016-05-09 | Siva Rama Kannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Meeting with nithya | 10.00 AM | 10.30 AM | Completed
|  | Creating contactus section in index page of ETS | 10.30 AM | 1.30 PM | In progress
|  | Fixing resposive issues in porfolio page of ETS | 1.30 PM | 7.00 PM | Completed
2016-05-09 | Velpandi | Typing Test | 9:30 | 10:30 | Completed
|  | Meeting | 10:30 | 11:30 | Completed
|  | Set a atricle block for my task | 11:30 | 14:00 | Completed
|  | Set a Footer part for my tasks | 15:00 | 18:00 | Completed
2016-05-09 | Vignesh | Attended meeting with nithya | 10.30am | 11.00am | completed
|  | worked in ETS site for responsiveness | 9.45am | 3.30pm | pending( slider responsive is not coming)
|  | worked in about us page responsive | 3.30pm | 7.00pm | pending (issue in text responsive since text
are collapsed during responsive)
|  | attended meeting with deepak sir | 7.00pm | 8.45pm

## 07.05.2016
Date | Name | Task | Start time | End time | Status | Comment
2016-05-07 | Akila | Typing lessons | 09.40am | 10.20am | Completed
|  | Meeting with Nithya | 10.30am | 11.15am | Completed | She insisted me to design again using float property for the task
|  | Continued task again to make changes in design as per basic design structure | 11.30am | 01.45pm | Pending
|  | Continued task again to make changes in design as per basic design structure | 02.50pm | 06.15pm | Pending
2016-05-07 | Balasubramaniam | Typing Test | 9:15AM | 10:50AM | Completed
|  | Meeting | 10:30AM | 11:30AM | Completed
|  | linking to the all buttions and links in html to css | 11:30AM | 12:10AM | Completed
|  | My Laptop taking by HR | 12:15PM | 3:00AM | Completed
|  | currections for the background image | 3:15PM | 4:00PM | Completed
|  | form alignments | 04:15PM | 4:45PM | Completed
2016-05-07 | Barath
Not Received
2016-05-07 | Kalai
Absent
2016-05-07 | Madhivanan | Daily sheet report updation | 10.45 AM | 11.00 AM
|  | Thalapakattu Testing | 11.00 AM | 3.25 PM | Completed
|  | Name searched for Fixido & invoice generator | 4.30 PM | 5.30 PM
|  | Discussion with Deepak & Sastha | 7.00 PM | 8.15 PM |  | about Thalapakattu Issues
2016-05-07 | Muthu | Preparing thalapakattu code for demo and fixing some changes as testing | 11.00 AM | 1.30 PM | Complete
|  | went to atomicka for demo | 2.00 PM | 7.00 PM | Complete | They given 3 changes in thalapakattu
|  | meeting with deepaka,sastha,madhi | 7.00 PM | 8.15 PM | Complete
2016-05-07 | Nithya | Typing test | 9:50 | 10:20 | Completed
|  | meeting with intent about ui | 10:25 | 11:10
|  | Standup meeting,portfolio html design(ETS) | 11:10 | 13:45 | In progress
|  | Helped siva for home page design | 15:00 | 6:30
2016-05-07 | Ramya | attended typing test | 10.05am | 10.45am
|  | started to work on uploading multiple images for products | 10.55am | 1.30pm | Pending | partially completed(while storing ll get some difficulties)
|  | fixed some issues registration form validation | 3.00pm | 3.30pm | completed
|  | searched for multiple image uploading | 3.40pm | 4.00pm
2016-05-07 | Santosh
Not Received
2016-05-07 | Siva Rama Kannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Meeting with nithya | 10.00 AM | 10.30 AM | Completed
|  | Creating our module in index page of ETS and Implementing slider option in this page | 10.30 AM | 6.30 PM | Completed
2016-05-07 | Velpandi | Typing Test | 9:30 | 10:30 | Completed
|  | Meeting | 10:30 | 11:30 | Completed
|  | My laptop used by interview persons | 11:30 | 15:00 | Completed
|  | Set the article sesson for my task | 15:00 | 17:00 | Completed
|  | Study in CSS | 17:00 | 6:00 | Completed
2016-05-07 | Vignesh
using media queries
|  | attended meeting with nithya | 10.30am | 11.00am | completed
|  | worked on issue in scroll function in home page | 12.00pm | 1.30pm | completed
|  | worked in ets about us page | 2.30pm | 7.00pm | pending

## 06.05.2016
Date | Name | Task | Start time | End time | Status | Comment
2016-05-06 | Akila | Typing test | 09:35am | 10.15am | Completed
|  | Meeting with Nithya,Standup meeting | 10.30am | 11.40am | Completed
|  | Continued working on task assigned | 11.40am | 01.55pm | Pending
|  | KT from Deepak | 02.50pm | 03.50pm | Completed
|  | Continued working on task assigned | 04.00pm | 07.00pm | Pending | Facing design issue in structure, rectifying again from starting
|  | KT from Deepak | 07.00pm | 08.15pm
2016-05-06 | Balasubramaniam | Typing Test | 9:15AM | 10:45AM
|  | Meeting | 10:46AM | 11:30AM
|  | logo making | 11:33AM | 12:03AM
|  | set logo on the web page | 12:30PM | 1:15PM
|  | set the padding and morgin for this page | 1:30PM | 2:00PM
|  | form arrangements and set the page formats | 3:00PM | 4:30PM
|  | study CSS | 4:45PM | 6:30PM
|  | Meeting | 6:45PM | 8:15PM
2016-05-06 | Barath | Designing ETS PROFILE | 10.00Am | 1.45PM | COMPLETED
|  | DESIGNING ETS PORTFOLLIO | 2.40PM | 7.40PM | Pending
2016-05-06 | Kalai | Fixed issues in resell chat history appending process for each and every product | 11.00 am | 2.00 pm | completed
|  | Fixed image cropping issues in post ad form using server side code, moved the updated resell code in server | 3.05 pm | 6.00 pm | completed
|  | tried to fetch the chat history throughout all pages | 6.00 pm | 8.05 pm | pending
2016-05-06 | Madhivanan | Daily sheet report updation | 10.30 AM | 10.50 AM
|  | Typing skills | 10.50 AM | 11.20 AM | Completed
|  | Standup Meeting | 11.20 AM | 11.45 AM | Completed
|  | Mail sent to Vinoth | 11.45 AM | 12.40 PM | Completed | Function flow confirmation for thalapakattu
|  | Search for Roadmap concept | 12.45 PM | 1.00 PM | Completed
|  | ICICI Bank account open | 1.00 PM | 1.45 PM | Completed | About Roadmap and ETS site content
|  | Discussion with Deepak | 1.45 PM | 2.30 PM | Completed
|  | Multi page profile for ETS | 3.15 AM | 3.40 PM | Pending
|  | Name Suggestion for Invoice generator | 3.40 PM | 4.10 PM | Completed
|  | Multi page profile content searching | 4.20 PM | 5.30 PM | Completed | Mail sent to Devi Mam
|  | E-learning and Resell requirement & issues collected | 5.45 PM | 7.00 PM | Completed | Mail sent to Prabhu
|  | Daily sheet report updation | 7.10 PM | 7.35 PM | Pending
|  | Meeting with Deepak | 8.15 PM | 9.30 PM | Completed | About Fixido function flow phase 1
2016-05-06 | Muthu | typing test | 9.30 AM | 10.00AM | Completed
|  | Thalapakattu restaurant flow code analysing | 10.00 AM | 2.00 AM | Completed
|  | Workout restaurant flow as per mail | 3.00 PM | 0:00 | Completed
2016-05-06 | Nithya | meeting with intent about ui | 10:20 | 11:30
|  | Standup meeting,portfolio html design(ETS) | 11:30 | 14:00 | In Progress
|  | Helped siva for ets home page html design,Removed gl animation in Atomicka desktop,portfolio html design | 15:15 | 19:50 | Pop up part is pending
2016-05-06 | Ramya | attended typing test | 10.05am | 10.45am
|  | proceeded to fix issues listed in bugreport | 10.50am | 11.20am | completed
|  | attended standup meeting | 11.20am | 11.45am
|  | continued with issues listed in bugreport | 12.00pm | 8.00pm | Pending | out of 5 issues fixed 4(multiple file uploading is pending)
2016-05-06 | Santosh | XYGET site testing | 9.00am | 1.30pm | Pending
|  | Try to create a document for XYGET | 3.00pm | 7.45pm | Pending
2016-05-06 | Siva Rama Kannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Meeting with nithya | 10.00 AM | 10.30 AM | Completed
|  | Creating portfolio module in index page of ETS | 10.30 AM | 4.45 PM | Completed
|  | Adding hover function to particular images in portfolio page | 5.00 PM | 6.30 PM | In progress
|  | Meeting with Deepak | 6.30 PM | 8.00 PM | Completed
2016-05-06 | Velpandi | Typing Test | 9:30 | 10:30 | Completed
|  | Meeting | 10:30 | 11:30 | Completed
|  | set a sesson for my task | 11:30 | 13:30 | Completed
|  | Adding a navigation blocks for each sesson | 14:40 | 16:30 | Completed
|  | Adding a links to an buttons | 16:30 | 18:40 | Completed
|  | Meeting | 18:40 | 20:15 | Completed
2016-05-06 | Vignesh | worked in ETS slider functions | 10.00am | 1.30pm | completed
|  | attended meeting with nithya | 10.30am | 11.00am | completed
|  | worked in menu on click function in ets home page | 2.30pm | 4.00pm | completed
|  | permission | 4.00pm | 6.30pm

## 05.05.2016
Date | Name | Task | Start time | End time | Status | Comment
2016-05-05 | Akila | Typing Test | 09.40am | 10.30am | Completed
|  | Meeting with Nithya,Standup Meeting | 10:40am | 11:40am | Completed
|  | Tea Break,Continued working on Task | 11.50am | 01.00pm | Pending
|  | Meeting with Madhivanan | 01.00pm | 01.20pm | Completed
|  | Fixed issues noted by madhivanan & continued task | 01:20pm | 07.00pm | Pending | Working on
|  | Meeting with HR & Madhivanan | 07:00pm | 07:40pm | Completed
2016-05-05 | Balasubramaniam | Typing Test | 9:15AM | 10:45AM | Completed
|  | Meeting | 10:46AM | 11:30AM | Completed
|  | logo making | 11:33AM | 12:03AM | Completed
|  | set logo on the web page | 12:30 | 1:15PM | Completed
|  | allign the nav bar | 1:27PM | 2:00PM | Completed
|  | change the button color | 3:00PM | 3:30PM | Completed
|  | set the padding and morgin for this page | 3:30PM | 4:10PM | Completed
|  | form arrangements and set the page formats | 4:30PM | 6:30PM | Completed
|  | Meeting | 6:30PM | 7:30PM | Completed
2016-05-05 | Barath | Designing ETS PROFILE | 11.30AM | 6.00PM | COMPLETED | NEW DESIGN
|  | DESIGNING LETTERPAD to GTS | 6.00PM | 6.30PM | COMPLETED
2016-05-05 | Kalai | Worked in resell and fixed the issues in post ad form and detail page | 10.45 am | 1.30 pm | completed
|  | Worked in thalapakattu and traced out the menu generate issues while click and enter combobox | 2.30 pm | 8.10 pm | pending
2016-05-05 | Madhivanan | Discuss with Sastha about tasks for today | 10.30 AM | 11.00 AM | Completed
|  | Created account in Computerworld, for latest update | 11.00 AM | 11.30 AM | Completed
|  | Ets Profile content | 11.30 AM | 11.50 AM | Pending
|  | Conduct Interview to Shanmugam | 11.50 AM | 12.10 PM | Pending | Task assign for quality check(Designing Logo for Cotton House)
|  | Mail sent to Prabhu | 12.10 PM | 12.20 PM | Completed | About E-Learning issues
|  | Ets Profile Content | 12.20 PM | 1.40 PM | Pending
|  | Conduct Interview to Shanmugam | 1.40 PM | 2.15 PM | Completed
|  | Name suggestion for fixido and mobile invoice | 3.15 PM | 4.10 PM | Completed
|  | Portfolio Content preperation | 4.10 PM | 6.30 PM | Pending
|  | Meeting with Intent & Akila | 7.00 PM | 7.30 PM | Completed
|  | Discussion with Sastha and Deepak | 7.30 PM | 8.30 PM
|  | Function flow KT for thalapakattu from Vinoth through Call | 8.30 PM | 9.00 PM | Completed
|  | Daily report sheet updation | 9.00 PM | 9.30 PM | Pending
2016-05-05 | Muthu | Typing Test | 9.30. AM | 10.45 AM | Completed
|  | Thalapakattu updation previous day corrction | 10.45 AM | 12.55 PM | Pending
|  | Went to atomicka for thalapakattu demo | 2.00 PM | 7.00 PM
|  | Thalapakattu corrction | 7.00 PM | 8.45 PM | Pending
2016-05-05 | Nithya | Typing test | 9:50 | 10:30 | Completed
|  | meeting with intent about ui | 10:45 | 11:25
|  | Standup meeting,Resell responsive design issues(bug list) | 11:45 | 13:40 | In Progress
|  | Resell bug list issues,helped the intent for design issues(ui) | 15:00 | 19:10 | Completed
2016-05-05 | Ramya | attended typing test | 9.45am | 10.30am | completed
|  | started to fix issues while sending sms after admin approval for product as well as advertisement | 10.35am | 1.30am | completed
|  | attended standup meeting | 11.30am | 11.45am
|  | proceeded to fix issues listed in bugreport | 3.00pm | 7.00pm | out of 23 issues fixed 18 (5 is in progress)
2016-05-05 | Santosh | Resell Responsive testing in Validation part. | 9.30am | 1.30pm | completed
|  | Name suggestion for new site | 3.00pm | 4.00pm | completed
|  | XYGET site analyze for testing purpose | 4.15pm | 6.30pm | Pending
2016-05-05 | Siva Rama Kannan
2016-05-05 | Velpandi | Typing Test | 9:30 | 10:30AM | Completed
|  | Meeting | 10:30 | 11:30 | Completed
|  | Adding division blogs for my task | 11:30 | 13:30 | Completed
|  | Align a text for my task fonts require | 14:30 | 4:30 | Completed
|  | Design a button on my blogs | 17:00 | 18:30 | Completed
|  | Meeting | 18:30 | 19:30 | Completed
2016-05-05 | Vignesh | worked in ETS site home page for responsive in menu bar | 9.45am | 1.30pm | completed
|  | Attended meeting with nithya | 11.00am | 11.30am | completed
|  | worked in home page slider function for responsive | 2.30pm | 6.30pm | pending((having issue in slider )
|  | Attended meeting with HR | 6.30pm | 7.00pm | completed
|  | Attended meeting with madhivanan | 7.00pm | 7.30pm | completed

## 04.05.2016
Date | Name | Task | Start time | End time | Status | Comment
2016-05-04 | Akila | Typing lessons | 09.30am | 10.30am | Completed
|  | Contuinued task in fixing issues | 10.30am | 11.00am | On process
|  | Standup meeting, Meeting with Madhivanan | 11.00am | 12.10pm | Completed
|  | Contuinued designing | 12.10pm | 02.15pm | On process
|  | Contuinued designing | 03.00pm | 06.30pm | Completed
|  | Meeting with Madhivanan | 06.30pm | 07.30pm | Completed
2016-05-04 | Balasubramaniam | Typing Test | 9:30AM | 10:05 | Completed
|  | Meeting | 10:30AM | 11:30AM | Inprocess
|  | set background Images and forms | 12:00PM | 1:35PM | Completed
|  | Task:design HTML & logo arrange using CSS | 3:00PM | 4:45PM | completed
|  | set navbar and buttons | 4:45PM | 6:30PM | Completed
|  | Meeting | 6:30PM | 7:30PM | Completed
2016-05-04 | Barath | Designing FIXIDO PROFILE | 9.45 am | 6.35 pm | completed | 4 Pages Completed
2016-05-04 | Kalai | Worked in thalapakattu project and checked the condition for printing bill formats in all the scenarios(KOT & Invoice Order,Parcel & Cancel), discussed with muthu about that different bill format concept | 10.05 pm | 2.00 pm | completed
|  | Generated the menu list while press enter button in combobox, And fixed issues in cancel item | 2.30 pm | 4.30 pm | completed
|  | Started to fix issues in resell, Again Continued to trace out the problem in thalapakattu, prepared the document for changes i made today in thalapakattu | 4.45 pm | 8.10 pm | completed
2016-05-04 | Madhivanan | Daily report updation, Place change, Meeting arrangements | 10.00 AM | 11.00 AM | Completed
|  | Py-01.com mail sent to Dev | 11.00 AM | 11.30 AM | Completed
|  | Meeting conduct for intent & Akila, Siva, Vignesh | 11.40 AM | 12.10 PM | Completed | Meeting about task status
|  | Thalapakattu changes mail confirmation | 12.15 PM | 12.50PM | Pending | Content not clear
|  | ETS Profile content correction | 12.50 PM | 1.30 PM | Pending
|  | Thalapakattu Testing | 1.30 PM | 2.30 PM | Completed
|  | Name suggestion for Fixido | 3.15 PM | 3.45 PM | Completed | Not accepted
|  | ETS Profile content searching | 3.45 PM | 6.30 PM | Pending
|  | Meeting conduct for intent & Akila, Siva, Vignesh | 6.30 PM | 7.30 PM | Completed | About task and team Coordination
|  | Daily report sheet updation | 7.30 PM | 8.00 PM | Completed
2016-05-04 | Muthu | Typing Test | 10.00 AM | 10.45 AM
|  | Thalapakattu changes and printer format | 10.45 AM | 3.00 PM | Completed
|  | Went to atomicka for thalapakattu demo | 4.00 PM | 6.25 PM | Pending | Vinoth was not there.
|  | Check thalapakattu printer (Printer code not working when demo) | 6.25 PM | 2.00 AM | Completed
2016-05-04 | Nithya
Absent
2016-05-04 | Ramya
Absent
2016-05-04 | Santosh | Resell Responsive testing | 9.00am | 1.30pm | completed
|  | Resell Windows testing | 2.45pm | 4.30pm | completed
|  | oozaaoo Responsive testing | 4.35pm | 7.00pm | completed
2016-05-04 | Siva Rama Kannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Fixing issues in bug sheet of oozaaoo and Meeting with Mathi | 10.00 AM | 1.30 PM | Completed
|  | Created aboutus page in ETS and Meeting with Mathi | 2.30 PM | 7.00 PM | Completed
|  | Creating service page in ETS | 7.00 PM | 8.00 PM | In progress
2016-05-04 | Velpandi | Typing Test | 9:30 | 10:30 | Completed
|  | Meeting | 10:30 | 11:30 | Completed
|  | HTML Blogs and Pricing in INVOICE:Design a navigation bar for my task | 11:30 | 13:00 | Completed
|  | Set a Background image for my task | 13:00 | 14:00 | In Process
|  | Adding division blogs for my task | 15:00 | 18:30 | In Process
|  | Meeting | 18:30 | 7:30 | Completed
2016-05-04 | Vignesh | Worked in ETS site about us page responsive | 10.30am | 11.30pm | pending
|  | Attended meeting with madhivanan | 11.30am | 12.00pm | completed
|  | worked in ETS site home page for slider and on click | 12.00pm | 2.00pm | completed
function.
|  | Edited home page for responsive design | 3.00pm | 6.30pm | pending
|  | Attended meeting with madhivanan | 6.30pm | 7.30pm | completed

## 03.05.2016
Date | Name | Task | Start time | End time | Status | Comment
2016-05-03 | Akila | Typing Lessons, Standup Meeting | 09.20am | 10.40am | Completed
|  | Tried out designing | 10.45am | 12.30pm | Completed
|  | Project coordinator Meeting | 12.30pm | 12.40pm | Completed
|  | Started Work on task assigned | 01.00pm | 07.00pm | Pending
|  | Hr Meeting | 04.40pm | 05.00pm | Completed
2016-05-03 | Balasubramaniam | Typing Test | 09:30AM | 10:10AM | Completed
|  | prepare HTML and css | 10:15AM | 10:45AM | Completed
|  | prepare HTML links,image,Table,list,blocks | 10:45AM | 11:25AM | Completed
|  | prepare HTML forms,form elements,html input types,html attributes | 11:30AM | 12:06PM | Completed
|  | Task: design HTML & CSS login and register Page | 12:10PM | 6:30PM | Pending
2016-05-03 | Barath | Designing Correction and new Design in Xyget Web page | 10.00AM | 12.30PM | completed
|  | Designing FIXIDO PROFILE | 3.30PM | 6.00PM | completed
|  | discussion with DEEPAK | 6.00PM | 6.30PM
|  | discussion with Ram | 6.30PM | 6.45 PM
2016-05-03 | Kalai | Worked in resell and finished the issues in myprofile image and registration form | 10.30 am | 1.30 pm | completed
|  | Worked in resell and finished the issues image uploading and resizing, guided siva and ramya to fix their issues | 2.05 pm | 6.40 pm | completed
2016-05-03 | Madhivanan | Daily Report sheet Updation | 11.20 AM | 11.30 AM | Completed
|  | Meeting with Sastha & kalai, Santhosh | 11.30 AM | 11.45 AM |  | Regarding Resell Project
|  | Xyget Testing | 11.45 AM | 12.30 PM | Pending
|  | Conduct meeting with Akila & Intent | 12.30 PM | 12.40 PM |  | Task details
|  | Xyget Testing | 12.40 PM | 2.30 PM | Pending
|  | Xyget Testing | 3.30 PM | 7.00 PM | Pending | Mail sent upto completed
|  | Daily Report Sheet Updation | 7.00 PM | 8.00 PM
2016-05-03 | Muthu | Typing Test | 10.00 AM | 10.45 AM | Completed
|  | Thalapakattu remaining issue fixed | 10.45 AM | 2.00 PM | Pending
|  | Went to atomicka for thalalpakattu demo | 3.45 PM | 6.00 PM
|  | Thalapakattu item search issue fixing | 6.00 PM | 9.00 PM | Completed
2016-05-03 | Nithya | Typing test | 9:35 | 10:15 | Completed
|  | Standup meeting,etekchnoservices html conversion | 10:15 | 14:15 | In Progress
|  | etekchnoservices html conversion | 15:15 | 19:20 | Pending | Completed upto to carousel
2016-05-03 | Ramya | attended typing test and standup meeting | 9.40am | 10.20am | completed
|  | started with sms code integration after advertisement posted | 10.30am | 10.50am | completed
|  | did custom combobox functionality | 11.45am | 4.30pm | completed
|  | tried to fix issues after integrated sms code in advertisement module | 4.30pm | 5.45pm | in progress
|  | get kt from kalai about the printing concept in thalapakattu project and proceeded with that task | 5.55pm | 7.00pm | pending
2016-05-03 | Santosh | Resell testing in windows | 9.00am | 1.30pm | completed
|  | oozaaoo full testing - cycle 3 | 3.00pm | 4.30pm | completed
|  | Resell Responsive testing | 5.00pm | 7.15pm | Pending
2016-05-03 | Siva Rama Kannan | Typing test | 09.30 AM | 10.00 AM
|  | Move the oozaaoo code to git and send the report to tester | 10.00 AM | 10.30 AM | Completed
|  | Creating select box and append the html file to the same page for Thalapakattu | 10.30 AM | 3.30 PM | Completed
|  | Implementing autoscrolldown function for Thalapakattu | 3.30 PM | 6.45 PM | Completed
2016-05-03 | Velpandi | Typing Test | 9:30 | 10:30 | Completed
|  | Prepare HTML Colors,HTML CSS,HTML Links,HTML Images | 10:30 | 11:15 | Completed
|  | Prepare HTML Tables,HTML List, HTML Blocks,HTML Classes | 11:15 | 12:00 | Completed
|  | Task:Design BLOGS and PRICING in INVOICE | 12:00 | 18:30 | In Process
2016-05-03 | Vignesh | worked in ETS site respnsive design | 9.45am | 12.00pm | pending
downloaded free bootstrap template and customised it
|  | using ets code for responsive design | 12.00pm | 5.30pm | completed
|  | learned responsive and jquery function from nithya for ets | 5.30pm | 7.30pm | completed
site

## 02.05.2016
Date | Name | Task | Start time | End time | Status | Comment
2016-05-02 | Akila | Installed softwares | 12.00pm | 01.00pm | Completed
|  | KT from Nithya | 01.00pm | 02.00pm | Completed
|  | Learnt Photoshop | 03.00pm | 04.00pm | Completed
|  | HTML5 review | 04.00pm | 05.00pm | Completed
|  | Tried out designing | 05.30pm | 07.15pm | Pending
2016-05-02 | Balasubramaniam | Intent Meeting | 23:30 | 12.30 PM | Completed
|  | Prepare HTML: HTML OVERVIEW,HTML BASIC TAGS,HTML ELEMENTS, | 12:50 | 14:00 | Completed
|  | HTML ATTRIBUTES, HTML FORMATTING | 15:00 | 16:00 | Completed
|  | HTML META TAGS, HTML COMMENTS, HTML IMAGES | 4:15 PM | 18:30 | Completed
2016-05-02 | Barath | Designing Correction and new Design in Xyget Web page | 10.15 AM | 7.00PM | Pending
2016-05-02 | Kalai | Worked in thalapakattu project SMS sending code for different session(complete lunch, dinner and snacks) | 10.40 am | 1.30 pm | completed
|  | Worked in thalapakattu project SMS sending code for different session(end of the day) | 2.30 pm | 8.30 pm | completed
2016-05-02 | Madhivanan | Daily Report Sheet Updation | 10.50 AM | 11.10 AM | Pending
|  | Thalapakattu Testing | 11.10 AM | 12.50 PM | Pending | Partially Completed
|  | Globalen Solutions Testing | 12.50 PM | 2.30 PM | Pending
|  | Globalen Solutions Testing | 3.30 PM | 6.15 PM | Completed
|  | Meeting with Intent & Akila | 6.20 PM | 7.00 PM | Completed
|  | Wellocity Testing | 7.10 PM | 8.00 PM | Completed
2016-05-02 | Muthu | System arrangement | 9.30 AM | 10.20 AM | Completed
|  | Thalapakattu Keypressing issue | 10.20 AM | 1.30 PM | Pending
|  | Thalapakattu Demo to vinoth at atomicka office | 3.00 PM | 5.30 PM | Completed
|  | Thalapakattu new changes | 5.30 PM | 8.30 PM | Pending
2016-05-02 | Nithya | Typing test | 10:00 | 10:40 | Completed
|  | Standup meeting,Resell bug report design corrections | 10:45 | 14:00 | In Progress
|  | Resell design issues and chat design issue in chrome | 15:00 | 20:00 | Completed
2016-05-02 | Ramya | atteded typing test and statndup meeting | 10.10am | 11.20am | completed
|  | fixed wct issues | 11.30am | 1.30pm | completed
|  | did some minor corrections and proceeded with xyget sms code integration after product was posted and after admin approval for products | 3.20pm, | 8.00pm | completed
2016-05-02 | Santosh | Resell testing | 9.30am | 6.30pm | Pending
2016-05-02 | Siva Rama Kannan | Typing test | 9.30 AM | 10.00 AM
|  | Meeting with sastha | 10.00 AM | 11.00AM
|  | Fixing issues in bug sheet of oozaaoo | 11.15 AM | 7.00 PM | Completed
2016-05-02 | Velpandi | Intent Meeting | 23:30 | 12.30 PM | Completed
|  | Prepare HTML: HTML OVERVIEW,HTML BASIC TAGS,HTML ELEMENTS, | 12:50 | 14:00 | Completed
|  | HTML ATTRIBUTES, HTML FORMATTING | 15:00 | 16:00 | Completed
|  | HTML META TAGS, HTML COMMENTS, HTML IMAGES | 16:15 | 18:30 | Completed
2016-05-02 | Vignesh | Learned how to add bootstrap carousal | 10.00am | 12.00pm | completed
|  | leraned two-column blog layout | 12.00pm | 3.30pm | completed
|  | learned bootstrap grids jumbotron | 3.30pm | 7.00pm | completed