## Staff Name
Date | Name | Task | Start time | End time | Status | Comment
12.05.16 | Sivaramakannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Learning AJAX concept | 10.00 AM | 11.00 AM
|  | Implementing ajax concept task for thalapakktu like adding parameters dynamically | 11.00 AM | 5.00 PM | In progress
|  | Auto suggestion in jquery | 5.00 PM | 7.00 PM | Completed
13.05.16 | Sivaramakannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Fixing validation issues in ETS | 10.00 AM | 11.00 AM | Completed
|  | Adding scroll option for Technologies logo | 11.00 AM | 1.30 PM | Completed
|  | Changing images in index and portfolio page of ETS | 2.30 PM | 6.30 PM | Completed
|  | Adding content in ETS and links for social icons | 6.30 PM | 7.30 PM | Completed
17.05.16 | Sivaramakannan
|  | Typing test | 3.45 PM | 4.15 PM | Completed
|  | Fixed issues in bug sheet of ETS like validation,design break issues | 4.30 PM | 7.00 PM | In progress
18.05.16 | Sivaramakannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Fixed issues in bug sheet of ETS like validation,design break issues,adding images to slider | 10.00 AM | 1.30 PM | Completed
|  | Adding table to database for yii framework and discussed with kalai about django framework | 2.30 PM | 4.45 PM | Completed
|  | Fixing issues in oozaaoo responsive | 5.00 PM | 7.30 PM | Completed
19.05.16 | Sivaramakannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Learning django and how to install it. | 10.00 AM | 11.00 AM | Completed
|  | Fixing issues in header part for responsive | 11.00 AM | 1.30 PM | Completed
|  | Fixing mobile num validation issues and image slider issues in oozaaoo | 2.30 PM | 4.:30 PM | Completed
|  | Fixing email validation issues in oozaaoo | 4.30 PM | 5.:00 PM | In progress
|  | Meetnig with Deepak | 5.00 PM | 7.30 PM | Completed
20.05.16 | Sivaramakannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Fixing mail function issues in oozaaoo and slider issues for responsive | 10.00 AM | 1.00 PM | Completed
|  | Learning about python like how to set enviromental variables,and installing supporting packages | 1.00 PM | 1.30 PM | In progress
|  | Implementing hover function in services section of index page for ETS | 2.30 PM | 3.00 PM | Completed
|  | Adding images to slider in index page for ETS | 3.00 PM | 3.30 PM | Completed
|  | Implementing technologies in aboutus section of index page for ETS | 3.30 PM | 10.00 PM | Completed
Removing Technologies slider in contactus form of index page for ETS
21.05.16 | Sivaramakannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Installing python and django and its supportivity softwares | 10.00 AM | 11.00 AM | Completed
|  | Set environmental variables | 11.00 AM | 11.30 AM | Completed
|  | Django configuration and creating structure of project and app in Django | 11.30 AM | 1.30 PM | Completed
|  | Attened the online test | 2.30 PM | 3.15 PM | Completed
|  | Watching google IO video | 3.15 PM | 4.00 PM | Completed
|  | Discussion about Google IO | 4.00 PM | 7.00 PM | Completed
23.05.16 | Sivaramakannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Learned ORM concept and MVC ,MVT in django | 10.00 AM | 1.30 PM | Completed
|  | Learned about how to connect mysql to python | 2.30 PM | 3.30 PM | Completed
|  | Configuring mysql to python | 3.30 PM | 7.30 PM | In progress | Due to software version
24.05.16 | Sivaramakannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Fixing issues in ETS site like slider and alignment issues | 10.00 AM | 1.30 PM | In progress | Only three issues are pending.it needs some images from designer.
|  | Django configuration in ubuntu and Configuring Fixido project | 2.30 PM | 7.30 PM | Completed
25.05.16 | Sivaramakannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Fixing issues in ETS site like slider and alignment issues | 10.00 AM | 10.30 AM | Completed
|  | Dicussed with kalai | 10.30 AM | 11.00 AM | Completed
|  | Implemented actor module in admin interface and analysed project flow and studied about some functionality | 11.00 AM | 7.00 PM | In progress | form validation and relationship are pending in admin interface
26.05.16 | Sivaramakannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Learned about relationship like onetoone relationship,forignkey,manytomanyrelationshipl for form in django | 10.00 AM | 11.30 AM | Completed
|  | Learned form fields,how to add validation and Implemented form validation in django admin interface | 11.30 AM | 3.00 PM | Completed
|  | Learned about meta tag fields and Implemented some functions like unicode,queryset in django | 3.00 PM | 7.00 PM | Completed
27.05.16 | Sivaramakannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Analysed project flow of fixido | 10.00 AM | 2.30 PM | Completed
|  | Learned signals concept and its function in django. | 2.30 PM | 4.30 PM | Completed
|  | Leanred forms function and its purpose | 4.30 PM | 5.30 PM | Completed
|  | Learned tuple and list and some basic functionality in python | 5.30 PM | 7.30 PM | Completed
28.05.16 | Sivaramakannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Leanred object creation and some functions like save(),method | 10.00 AM | 10.45 AM | Completed
|  | Learned about how to add restriction in admin side | 10.45 AM | 1.30 PM | Completed
|  | Implemented form fields and its restriction in admin side fro actor module | 2.30 PM | 5.15 PM | In progress
|  | Session with team members | 5.30 PM | 6.30 PM | Completed