## Sheet1
Date | Name | Task | Star time | End time | Status | Comment
2016-04-06 | Asai | Atomicka Logo |  |  | Completed
|  | ID Card for Kumaran, Barath, Vignesh & Ramalingam |  |  | Photo required
|  | Cotton House Logo |  |  | Waiting for Clint reply
|  | Eventswat Logo & Color Corrections |  |  | Pending | Waiting for Name suggestion from Deepak
|  | Online Mobile Invoice |  |  | Invoice Layout postpond to tomorrow
| Barath | ID Card for staffs Design | 10.00 AM | 11.00 AM | Pending | Only Photo insertion is pending
|  | Logo design to where eventz.. One sample | 11.00 AM | 1.40 PM | Completed
|  | Seraching ae templates for animation | 3.00 PM | 6.00 PM | Completed
| Kalai | Wellocity: 4 Issues assigned | 11.00 AM | 1.50 PM | Completed | Fixed Wellocity issues in athletes, create_schedule and range from new requirements
|  | Wellocity: ramya validation part | 3.00 PM | 5.00 PM | Completed | Fixed date validation issues in athlete module which done by ramya already
|  | Resell: Responsive design | 5.30 PM | 7.30 PM | Completed | Worked in resell and displayed in detail page image in responsive design, gave link in some of the options in mobile responsive
|  | Wellocity dependency concept logic discussion | 7.30 PM | 8.00 PM
| Madhi | Daily Task Scheduling to Team | 9.30 AM | 10.30 AM | Completed
|  | Daily Task Sheet updation | 10.30 AM | 11.30 AM | Completed
|  | Collecting all Design issues | 11.30 AM | 288:00 | Completed
|  | Discussion with Muthu & Kalai about code extraction | 12.00 PM | 12.30 PM
|  | Discussion with Deepak and Asai about Domain Name for Eventswat | 12.30 PM | 1.00 PM
|  | Discussion with Deepak and Vignesh about Xampp | 1.00 PM | 1.30 PM
|  | Chennai Folder | 2.30 PM | 6.20 PM | Pending | 8 Folder Remaining
|  | Resell Product Updation | 6.20 PM | 8.00 PM | Pending
Getting Tomorrow Task details for Team
| Muthu | Wellocity: 6 Issues assigned |  |  | Completed
|  | E-Learning: Discuss with clint and update |  |  | Clint not responding
|  | Assign Wellocity testing to Santosh |  |  | Completed
| Santosh | Wellocity Testing |  |  | Pending
|  | Resell Testing |  |  | Pending
|  | Xyget Testing |  |  | Pending
|  | Atomicka Mobile Testing |  |  | Pending
| Vignesh | Oozaaoo: Inbond Responsive | 9.30 AM | 1.00 PM | Pending | Alignment issues
|  | Oozaaoo: Outbond Responsive | 2.00 PM | 7.00 PM | Completed | One doubt need to be clarify with Deepak
|  | Chennai Folder |  |  | Pending | 8 Folder Remaining