## Sheet1
S.NO | Task | Status | Comments
1 | Online Mobile Invoice for first 15days output | On process | 6 menus Pages competled and waiting for aproval
2 | Website Animation | On process | 24 seconds animation completed
3 | Cotton House Logo |  | Client not responding
4 | Eventswat Logo & Color Corrections |  | Waiting for loog Name
5 | Evinity Template (Add more Photo Slides) |  | Photos not received
6 | ETS Profile need in PDF formate | Completed
7 | Wall motivation theme |  | Yet to start
8 | Glass design stickers | Compelted
9 | Facebook & Linkedin, add related post and promote | Compelted
10 | Mail Signature for Deepak, HR, Sastha | Compelted