## Sheet1
Date | Name | Task | Start time | End time | Status | Comment
2016-04-11 | Asai | Process in oozaaoo inbound images size croping and Searching | 9:30 | 10:30 | Completed
|  | process in Flash intro animation | 10:30 | 19:30 | Complted
2016-04-11 | Ashok Raj
Absent
2016-04-11 | Barath | Image Resizing for Oozzaaoo | 10.00AM | 10.30AM | Completed
|  | Image Resizing for Happy Journey | 10.30AM | 11.00AM | Completed
|  | ETS PRO REDIESGN | 11.00AM | 6.30PM | Completed
2016-04-11 | Kalai | Xyget: Business User Logo upload | 10.35 AM | 1.30 PM
|  | Implemented the printer concept in node.js for atomicka | 2.15 pm | 8.15 pm
2016-04-11 | Madhi | Daily Report Sheet Updation for Team | 9.45 AM | 10.00 AM | Completed
|  | Typing skills | 10.00 AM | 10.20 AM |  | Session error
|  | Xyget.com testing recheck | 10.20 AM | 10.40 AM |  | Session Error, updated to Sastha
|  | Learning Javascript | 10.40 AM | 1.00 PM
|  | Xyget.com testing recheck | 1.00 PM | 8.00 PM
|  | Daily Report Sheet Updation for Team | 8.00 PM
2016-04-11 | Muthu | Printer Concept | 10.00 AM | 2.00 PM | Pending | Handover to kalai
|  | Xyget: Post Advertisement in Admin & fixing Login issue | 3.00 PM | 8.00 PM | Pending | Ajax calling and validation for form
Xyget: Need to view the product & advertisement details(just with non-editable fields) before approve in admin
2016-04-11 | Nithya | Oozaaoo: Inbound & Outbound Responsive Design | 10.00 AM | 6.30 PM
|  | Typing test | 9:30 | 10:15 | Completed
|  | oozaaoo responsive design for outbound | 10:15 | 14:00 | Completed
|  | design and content correction in oozaaoo,responsive for inbound | 15:00 | 20:00 | Pending | inbound responsive is pending
2016-04-11 | Ramya | attended Typing Test | 09.40am | 10.10am | Completed
|  | started to analyze the issues in xyget listed as prioritrized | 10.15 AM | 10.30am | Completed
|  | checked xyget advertisement and product based results and checked db error in live | 10.35pm | 11.30am | Completed
|  | started to fix issue on wct (dob validation) | 11.30am | 1.50pm | Pending | partially completed
|  | test clone content validation | 3.00pm | 6.20pm | completed
|  | proceeded with popup validation for dob(add athletes, create schedule) | 6.30pm | 8.00pm | Pending | partially completed
2016-04-11 | Santosh | wellocity | 11.00am | 6.45pm |  | In processing (completed MASER menu)
|  | wellocity | 9.30am | 1.30pm |  | Functionality testing completed
|  | wellocity | 9.30am | 6.45pm |  | Check the design, functionality testing and read the wellocity requirement document .
|  | wellocity | 8.10am | 8.10pm |  | Full testing in progress
|  | wellocity | 9.30am | 10.30am |  | Flow testing (issue persist)
|  | XYGET.com | 10.30am | 5.30pm |  | Functionality testing (on-hold)
|  | e-learning | 5.30pm | 7.35pm |  | Check with work flow.
2016-04-11 | Siva Rama Kannan | Typing Test | 9.30 AM | 10.15 AM
|  | Printing table in report_action page | 10.15 AM | 12.30 PM | Completed
|  | Fixed issues in teacher_login | 12.30 PM | 1.30 PM | Completed
|  | Show current day based on system date | 1.30 PM | 2.00 PM | Completed
|  | Explain my project to tester | 3.00 PM | 3.30 PM
|  | Changed report page design | 3.30 PM | 4.30 PM | Completed
|  | Test my project and fixed some issues | 5.45 PM | 6.15 PM | Completed
|  | Validation in makeup slots | 5.45 PM | 6.15 PM | In progress
2016-04-11 | Vignesh
Absent