## 23.04.2016
2016-04-22 | Asai
Absent
2016-04-22 | Ashok Raj
Absent
2016-04-22 | Barath | Designing HOME to Xyget | 10.00AM | 12.30PM | Completed
|  | Correction in Evinity Banner | 12.30PM | 1.30PM | Completed
|  | Evinity Broucher Designing | 2.45PM | 6.30PM | Completed
2016-04-22 | Kalai
Not Received
2016-04-22 | Madhi
Leave(Work from home for Atomicka site)
2016-04-22 | Muthu | Typing test | 10.00 AM | 10.40 AM
|  | Xyget –admin-advertisement-edit with ajax | 10.40 AM | 2.00 PM | Pending
|  | evinity correction | 3.10 PM | 5.30 PM | Completed
|  | atomicka correction | 5.30 PM | 8.00 PM | Pending | Mobile Part
2016-04-22 | Nithya
Not Received
2016-04-22 | Ramya
Not Received
2016-04-22 | Santosh
Not Received
2016-04-22 | Siva Rama Kannan
Absent
2016-04-22 | Vignesh | worked in home page for mobile responsive site | 10.20am | 1.30pm | completed
Learned Bootstrap
|  | learned how to download and install bootstrap using various methods | 2.30pm | 4.30pm | completed
|  | Learned about container and its usage | 4.30pm | 5.30pm | completed
|  | Learned about grid structure | 5.30pm | 6.30pm | completed

## 22.04.2016
2016-04-22 | Asai
Absent
2016-04-22 | Ashok Raj
Absent
2016-04-22 | Barath | pick opproprite pages have to design in Xyget | 10.00AM | 10.30AM
|  | Designing HOME to Xyget | 10.30AM | 1.30PM
|  | Correction in Evinity Banner | 4.30PM | 6.10PM
|  | Designing HOME to Xyget | 6.30PM | 6.30PM
2016-04-22 | Kalai | Configured the gmail, facebook for login and share ads in resell | 10.45pm | 1.30 pm | completed
|  | Create ad unit in google adsense, configured the code in resell server and checked it | 2.30 pm | 4.30 pm | pending
|  | General meeting with HR and deepak | 4.45 pm | 8.00 pm
2016-04-22 | Madhi | Typing skills | 10.05 AM | 10.25 AM | Completed
|  | Daily Report Sheet Updation for Team | 10.25 AM | 10.40 AM | Pending
|  | Infom Atomicka Testing Desktop | 10. 40 AM | 11.50 AM | Completed
|  | Infom Atomicka Testing Mobile | 12.00 PM | 4.45 PM | Pending
|  | Team Meeting with Deepak, HR, Sastha & Developers | 4.45 PM | 8.00 PM
|  | Infom Atomicka Testing Mobile | 8.00 PM | 9.00 PM | Pending
|  | Infom Atomicka Testing Mobile | 10.00 PM | 1.30 AM | Pending | Almost over
|  | Daily Report Sheet Updation for Team | 1.30 AM | 2.00 AM | Completed
2016-04-22 | Muthu | Communicate with client | 10.00 AM | 10.20 AM
|  | Typing test | 10.20 AM | 10.40 AM
|  | Xyget admin advertisement refresh issue | 10.40 AM | 2.00 PM | completed
|  | Xyget admin edit and delete option | 3.15 PM | 4.45 PM | pending
|  | Genral meeting | 4.45 PM | 8.00 PM
2016-04-22 | Nithya
Absent
2016-04-22 | Ramya
Absent
2016-04-22 | Santosh | E-learning testing | 9.00am | 1.30pm | Completed
|  | Infom atomicka testing | 2.10pm | 7.50pm | Completed
2016-04-22 | Siva Rama Kannan
Absent
2016-04-22 | Vignesh
Not Received

## 21.04.2016
2016-04-21 | Asai
Absent
2016-04-21 | Ashok Raj
Absent
2016-04-21 | Barath | Taking screen shot for Xygate site | 9.45Am | 10.30AM | Completed
|  | deasiging Login Page | 10.30Am | 1.30PM | Completed
|  | Designing Search Page | 2.30PM | 4.30PM | Completed
|  | Desiging 404 error, 400error,500Error, 403 error page | 6.00Pm | 6.30PM | Completed
|  | Meeting With HR | 4.30Pm | 5.30PM
2016-04-21 | Kalai | Fixed some message validation issues in wellocity (category, user management) | 10.45 am | 11.15 am | completed
|  | Taken Telephone inteview for fresher | 11.15 pm | 11.45 pm
|  | Create the app for facebook share and linked it in resell & read the developer account options for configuration | 11.45 pm | 12.30 pm | completed
|  | Worked in resell and fixed issues in image upload validation, search results | 12.30 pm | 1.45 pm | completed
|  | Worked in resell and fixed issues in myprofile, issues fixed from bug report, discussed django error page with nithya | 2.45 pm | 7.30 pm | completed
|  | Created the resell project in Eteks github and moved in it, Integrated the nithya's design code | 7.30 pm | 8.10 pm | completed
2016-04-21 | Madhi | Daily Report Sheet Updation for Team | 10.10 AM | 10.20 AM | Completed
|  | Wellocity Delivery Process | 10.20 AM | 11.40 AM | Completed
|  | Atomicka Testing Desktop | 11.40 AM | 12.00 PM | Pending
|  | Meeting with individual staff | 12.00 PM | 1.00 PM | Pending
|  | Wellocity Delivered | 1.00 PM | 2.10 PM | Completed
|  | Atomicka Testing Desktop | 3.10 PM | 7.30 PM | Pending
|  | Daily Report Sheet Updation for Team | 7.30 PM | 8.00 PM | Completed
2016-04-21 | Muthu | Typing test | 10.00 AM | 10.30 AM | Completed
|  | Xyget admin advertisement part edit delete and wellocity | 10.30 AM | 11.00 AM | Pending
|  | Interview | 11.00 AM | 11.20 AM | Completed
|  | E-learning Issue fixing | 11.20 AM | 2.00 PM | Pending
|  | E-learning Issue fixing | 3.00 PM | 8.00 PM | Completed
2016-04-21 | Nithya | Typing test | 10:10 | 10:45 | Completed
|  | resell responsive design,evinity design issues | 10:45 | 14:00 | resell is pending
|  | resell design correction | 15:00 | 20:20 | In Progress
2016-04-21 | Ramya | atteded typing test | 10.15am | 10.45am | completed
|  | mail sending after approval | 11.20am | 3.30pm | completed
|  | city based search for products and companies | 3.45pm | 8.30pm | Pending
|  | bugreport issues |  |  | pending
2016-04-21 | Santosh | E-learning Testing | 9.15am | 6.45pm | Pending
2016-04-21 | Siva Rama Kannan
Absent
2016-04-21 | Vignesh | Learnt about bootstrap basics and layout | 9.30am | 10.30am
|  | worked in ETS website home page in mobile responsive | 10.30am | 7.30pm
using bootstrap

## 20.04.2016
2016-04-20 | Asai
Absent
2016-04-20 | Ashok Raj
Absent
2016-04-20 | Barath | Banner Slider Image designing and Correction | 10.00Am | 1.30PM | Completed
|  | ID Card Correction | 2.45PM | 3.15PM | Completed
|  | Banner Slider Image designing and Correction | 3.15PM | 5.30PM | Completed
|  | Analysing XYGET Design | 5.30PM | 6.30PM | ON Process
2016-04-20 | Kalai | taken one interview for fresher person | 10.45 am | 11.30 pm | Completed
|  | Fixed date issues in wellocity with custom validation for jquery dropdown plugin in athlete form (add and edit) | 11.30 pm | 1.30 pm | completed
|  | Implemented the above date validation in create schedule form (add and edit) | 2.30 pm | 5.00 pm | completed
|  | Fixed some suggestions in wellocity given by madhi and santhosh, moved the wellocity code to server | 5.15 pm | 8.15 pm | completed
2016-04-20 | Madhi | Daily Report Sheet Updation for Team | 11.10 AM | 11.20 AM | Completed
|  | Task Updation for Vignesh | 11.20 AM | 11.30 AM | Completed
|  | Wellocity Recheck after Developers cleared the issues | 11.30 AM | 12.40 PM | Completed
|  | Xyget: Details Page, Profile Setup Testing | 12.40 PM | 1.10 PM | Pending
|  | Wellocity Recheck after Developers cleared the issues | 2.15 PM | 4.30 PM | Completed
|  | Xyget knowledge transfer to Barath | 4.30 PM | 4.45 PM | Completed
|  | Wellocity Delivery Process | 5.00 PM | 8.00 PM
2016-04-20 | Muthu | Typing test | 10.00 AM | 10.30 AM | Completed
|  | wellocity issue fixing and xyget admin part advertisment | 10.30 AM | 2.00 PM | Pending
|  | wellocity issue fixing and xyget admin part advertisment | 3.15 PM | 8.00 PM | Pending | wellocity completed.xyget pending
2016-04-20 | Nithya | Typing test | 10:00 | 10:30 | Completed
|  | evinity corrections | 10:30 | 14:00 | Completed
|  | resell responsive design,wellocity design issues | 15:15 | 9.00pm | Pending | Resell is Pending
2016-04-20 | Ramya | attended typing test | 9.50am | 10.45am | completed
|  | started to fix issues in assign schedule popup while submission and adding athletes | 11.05am | 1.30pm | completed
|  | fixed issues in reported by madhivanan and santhosh | 3.05pm | 7.45pm | completed
|  | Proceeded with xyget project issues in mail function | 7.50pm | 8.20pm
2016-04-20 | Santosh | E-learning | 9.00am | 1.30pm | Pending
|  | wellocity | 2.30pm | 8.30pm | Completed
2016-04-20 | Siva Rama Kannan
2016-04-20 | Vignesh | worked in text area and details area in ETS contact page | 10.00am | 2.00pm | Completed
|  | worked in menu hide/show function using jquery in home page | 2.00pm | 5.00pm | Pending | menu is displayed behind the element
|  | worked in mouse hover function in portfolio page | 5.00pm | 7.30pm | Pending

## 19.04.2016
2016-04-19 | Asai
Absent
2016-04-19 | Ashok Raj
Absent
2016-04-19 | Barath
|  | Banner Slider Image designing | 10.00Am | 6.15PM | Completed | 4 Slides
|  | GS Despktop Image Designing | 6.15PM | 6.30PM | Completed
2016-04-19 | Kalai | Discussed the date of birth issues with ramya, Attended standup meeting | 10.45 am | 11.30 pm | completed
|  | Worked in resell and fixed the issues in bug report which is given by madhi and santhosh | 11.45 pm | 1.00 pm | completed
|  | Meeting with sastha about team improvement | 1.00 pm | 2.15 pm
|  | Continued to Work in resell and fixed the issues in bug report (validtion in sign up form, autosuggestion) | 3.15 pm | 4.15 pm | pending
|  | Meeting with deepak and sastha about team improvement, discussed about that with team members and shared our ideas | 4.30 pm | 7.00 pm
|  | Cleared the date issues with ramya in wellocity athlete and create schedule module | 7.00 pm | 8.05 pm | completed
2016-04-19 | Madhi | Assign Task to Barath | 10.20 AM | 10.30 AM | Completed
|  | Assign Task to Santhosh | 10.30 AM | 10.40 AM | Completed
|  | Daily Report Sheet Updation for Team | 10.40 AM | 10.50 AM | Completed
|  | Wellocity Testing | 10.50 AM | 11.20 AM | Completed
|  | Wellocity Project Documentation | 11.20 AM | 2.05 PM | Pending
|  | Wellocity Project Documentation | 3.10 PM | 6.30 PM | Pending
|  | Wellocity Recheck after Developers cleared the issues | 6.30 PM | 7.00 PM | Completed
|  | Daily Report Sheet Updation for Team | 7.00 PM | 7.30 PM
2016-04-19 | Muthu | typing test | 10.00AM | 10.30AM | Completed
|  | xyget post advertisement form creation | 10.30AM | 1.15PM | Pending
|  | meeting with sastha | 1.15PM | 2.15PM
|  | meeting with deepak | 3.15PM | 4.00PM
|  | xyget post advertisement form creation | 4.00PM | 5.30PM | Completed
|  | xyget post advertisement form edit,delete,view option | 5.30PM | 8.00PM | Pending
2016-04-19 | Nithya
Absent
2016-04-19 | Ramya | atteded typing test | 10.15am | 10.45am | completed
|  | tried to fix issues on dob and fixed some corrections in error msg displaying | 10.50am | 1.15pm | completed
|  | had a discussion with team members and Mr.sastha,Mr.Deepak and Mr.Kumaran | 1.20pm | 2.30pm
|  | continued with the dob issue | 3.30pm | 9.00pm | completed
|  | tried to fix issues in assign schedule popup | 9.00pm | 9.20pm | in progress
2016-04-19 | Santosh | E-learning | 11.00am | 8.00pm |  | Functionality testing
2016-04-19 | Siva Rama Kannan | Typing test | 09.30 AM | 10.00 AM
|  | Fixing some design and validation issues in bug report | 10.00 AM | 1.00 PM | Completed
|  | Fixing session problem in adminside | 1.00 PM | 2.00 PM | In progress
|  | Fixing logical issues in studentlogin page | 4.00 PM | 7.00 PM | Completed
|  | Adding seats field in edit option for view_schedules page | 7.00 PM | 8.00 PM | Completed
2016-04-19 | Vignesh | worked in designing ETS portfolio page | 10.00am | 2.00pm | Completed
|  | worked in designing out team page | 3.00pm | 7.30pm | Completed
|  | have to complete contact us page |  |  | Pending

## 18.04.2016
2016-04-18 | Asai
Absent
2016-04-18 | Ashok Raj
Absent
2016-04-18 | Barath | ID CARD Correction | 9.30am | 6.15 pm | Completed
2016-04-18 | Kalai | Configured the python and mysql in nithya's system, worked in resell mobile image gallery | 10.20 am | 11.30 am | completed
|  | General meeting with HR and deepak | 11.30 am | 12.00 pm
|  | Tried to configure the resell website in google ad sense, fixed wellocity issues | 12.15 pm | 2.00 pm | completed
|  | Checked the wellocity updation and moved the ramya code in server and checked the changes | 3.05 pm | 4.05 pm | completed
|  | Fixed some logic functionality issues in mobile, checked the google ad sense account with gmail in windows system | 4.05 pm | 6.30 pm | completed
|  | Taken phone interview and update the report sheet And wellocity status to madhi | 6.30 pm | 8.20 pm | completed
2016-04-18 | Madhi | Daily Report Sheet Updation for Team | 10.20 AM | 10.40 AM | Completed
|  | Wellocity Issues update to Developers and Testing | 10.40 AM | 2.00 PM | Completed
|  | Project Management Sheet Updation | 3.00 PM | 4.00 PM | Pending
|  | Wellocity Recheck after Developers cleared the issues | 4.10 PM | 7.00 PM | Completed
|  | E-learning Concept | 7.10 PM | 8.00 PM | Completed | Explained by Siva
|  | Wellocity Recheck after Developers cleared the issues | 8.00 PM | 8.30 PM | Completed
|  | Daily Report Sheet Updation for Team | 8.30 PM | 9.20 PM | Completed
2016-04-18 | Muthu | Wellcity issue fixing | 10.15 AM | 10.50 AM | Pending
|  | Meeting with HR | 10.50 AM | 11.25 AM
|  | Xyget admin part advertisement module form creation | 11.25 AM | 2.15 PM | Pending
|  | Wellcity issue fixing and Xyget admin part advertisement module form creation | 3.00 PM | 8.00 PM | Completed
2016-04-18 | Nithya | Typing test | 9:40 | 10:15 | Completed
|  | installation process for resell,fixed css issues in resell,evinity design correction | 10:15 | 14:15 | Pending | Resell
|  | evinity design correction | 15:15 | 21:20 | Completed
2016-04-18 | Ramya | Attended typing test | 9.50am | 10.30am | completed
|  | fixed issues listed by madhivanan in wct proect | 10.35am | 9.00pm | completed
2016-04-18 | Santosh
Absent
2016-04-18 | Siva Rama Kannan | Typing test | 09.30 AM | 10.00 AM
|  | Showing popup window during cancellation process | 10.00 AM | 2.00 PM | Completed
|  | Fixing issues in datepicker | 3.00 PM | 4.00 PM | Completed
|  | Validation in class_schedules page | 4.00 PM | 5.00 PM | Completed
|  | Cheking my project and move to the git and Discussed with sastha | 5.00 PM | 7.00 PM | Completed
2016-04-18 | Vignesh | worked in ETS website in home page | 11.30pm | 1.30pm | Completed
|  | worked in about us page | 1.30pm | 5.00pm | Completed
|  | worked in services page | 5.00pm | 8.00pm | Completed
|  | have to complete portfolio page and contact us page |  |  | Pending

## 16.04.2016
2016-04-16 | Asai
Absent
2016-04-16 | Ashok Raj
Absent
2016-04-16 | Barath
Absent
2016-04-16 | Kalai | Discussed the wellocity validation and corrections in result with madhi and sastha, Worked in resell- myprofile edit, view and delete restrict in mobile | 11.00 am | 11.25 am | completed
|  | Fixed Image upload and remove issues with overwrite the code of plugin in resell | 11.40 am | 1.30 pm | completed
|  | Meeting with deepak about team improvement | 2.40 pm | 3.45 pm |  | Net Problem
|  | search by combine with city and search text in resell | 4.00 pm | 7.10 pm | completed
2016-04-16 | Madhi | Daily Report Sheet Updation for Team | 10.50 AM | 11.15 AM | Completed
|  | Wellocity: Full Testing | 11.20 AM | 2.00 PM | Completed | Issues and Suggestiong mailed to Sastha & Developers
|  | Meeting with Deepak | 3.00 PM | 3.45 PM | Completed | Discuss about Team Development
|  | Wellocity: Full Testing | 3.50 PM | 10.30 PM | Completed | Issues and Suggestiong mailed to Sastha & Developers
|  | Daily Report Sheet Updation for Team | 10.30 PM | 10.50 PM | Pending
2016-04-16 | Muthu | Wellocity Issues fixing | 10.15 AM | 2.00 PM | completed
|  | Wellocity Issues fixing | 3.00 PM | 8.00 PM | completed
2016-04-16 | Nithya | Typing test | 9:50 | 10:30 | Completed
|  | Atomicka responsive correction,installed django and phython for resell project | 10:30 | 13:45 | Completed
|  | evinity corrections | 14:50 | 22:15 | Completed
2016-04-16 | Ramya | attended typing test | 9.50am | 10.30am | completed
|  | fixed issues listed in bugreport(wct) & fixed issues reported by madhivanan | 10.30am | 10.50pm | completed
2016-04-16 | Santosh
Absent
2016-04-16 | Siva Rama Kannan | Typing test | 09.30 AM | 10.00 AM
|  | Request for new schedules in student in student_login | 10.00 AM | 1.00 PM | Completed
|  | Php validation for edit page of student,teacher,admin,class,subject,branch | 2.00 PM | 7.00 PM | Completed
|  | Fixing issues in report page | 7.00 PM | 8.00 PM | Completed
|  | Fixing issues in datepicker | 8.00 PM | 8.30 PM | In progress
2016-04-16 | Vignesh | worked in issues in oozaaoo site to give path to images | 9.50am | 12.30pm | Completed
|  | worked in happi journey site to add close buttons to pop | 12.30pm | 6.00pm | Completed
up windows in each page
|  | worked in menu bar to change on click function. | 6.00pm | 7.30pm | Pending | will complete on Monday before 2pm

## 15.04.2016
2016-04-15 | Asai
Not Received
2016-04-15 | Ashok Raj
Absent
2016-04-15 | Barath | Image resizing to OOZZAAOO | 10.00AM | 10.30AM | Completed
|  | wall motion iamge deigning | 10.30AM | 1.30PM | Completed | 2 sample done
|  | ID CARD correction | 3.00PM | 3.30PM | Completed
|  | wall motion iamge deigning |  |  | Completed | 2 sample done
2016-04-15 | Kalai | Fixed autosuggestion filter option issues in wellocity result module | 11.00 am | 12.00 pm | completed
|  | shared the wellocity logic and functionalities to madhi and santhosh in meeting hall | 12.00 pm | 1.00 pm | completed
|  | Worked in resell detail page image gallery | 1.00 pm | 1.40 pm | completed
|  | Tried to fix resell image upload issues in post ad for both mobile and desktop in resell | 2.40 pm | 5.00 pm | pending
|  | discussed validation and result module category fetch with madhi & sastha, then implemented the concept after confirmation from bala | 5.15 pm | 8.15 pm | completed
2016-04-15 | Madhi | Daily Report Sheet Updation for Team | 10.10 AM | 10.25 AM | Completed
|  | Typing skills | 10.25 AM | 11.00 AM | Completed
|  | Meeting with Sastha | 11.00 AM | 12.00 PM | Completed | Testing Issues, Process with documentation
|  | Meeting with Kalai | 12.15 PM | 12. 35 PM | Completed | About Wellocity Module explaination
|  | Meeting with Muthu | 12.35 PM | 01.15 PM | Completed | About Wellocity Module explaination
|  | Meeting with Deepak | 2.30 PM | 3.15 PM | Completed | Explaination about project and how to handle it
|  | Wellocity Re-Testing full site | 3.20 PM | 9.00 PM | Completed | Need to recheck with issues updated codes
2016-04-15 | Muthu | Typing test | 10.05 AM | 10.30 AM | Completed
|  | Printer concept working with remote site | 10.30 AM | 2.00 PM | Pending | Client does not responding
|  | wellocity issue fixing and printer concept | 3.00 PM | 8.00 PM | Completed
2016-04-15 | Nithya | Typing test | 9:40 | 10:15 | Completed
|  | Oozaaoo design correction | 10:15 | 12:30 | Completed
|  | Atomicka responsive design for index page | 12:30 | 13:30 | Completed
|  | Atomicka responsive correction and wellocity design correction | 14:30 | 21:40 | Pending | joinourhub focus part is pending
2016-04-15 | Ramya | attended typing test | 9.45am | 10.30am | completed
|  | Fixed the results in related search based on company with out city match | 10.35am | 1.30pm | completed
|  | started to correct the results in related search based on company | 3.40pm | 6.30pm | completed
|  | fixed issues in wct validation | 6.40pm | 9.40pm | completed
|  | dob calidation |  |  | in progress
2016-04-15 | Santosh
Not Received
2016-04-15 | Siva Rama Kannan | Typing test | 09.30 AM | 10.00 AM
|  | Cancellation of student_schdules | 10.00 AM | 3.00 PM | Completed
|  | Request for new schedules in student in student_login | 3.00 PM | 8.00 PM | In progress
2016-04-15 | Vignesh | worked in issue in happi journey site | 9.30pm | 11.30pm | Completed
|  | worked on issue in oozaoo site mobile number field | 11.30pm | 1.30pm | Completed
|  | worked in issue link to go to home page | 2.30pm | 4.00pm | Completed
|  | worked in issues to give links to social sites | 4.00pm | 5.00pm | Completed
|  | worked in menu bar to change on click function. | 5.00pm | 7.00pm | Pending | have some difficulty in jquery function
to modify mouse on click.

## 13.04.2016
Date | Name | Task | Start time | End time | Status | Comment
2016-04-13 | Asai | PROCESS IN XYGET ANALYISED | 9:30 | 13:30 | Pending
|  | Process in felizzoo logo completed | 1:30 | 19:14 | Completed
2016-04-13 | Ashok Raj
Absent
2016-04-13 | Barath | happy journey image resizing | 10.00Am | 10.30AM | Completed
|  | ID Card Designing and correction | 10.30Am | 1.40PM | Completed
|  | wall motion iamge deigning | 2.45Pm | 4.30Pm | Completed
|  | Promo add designing and correction | 4.30Pm | 6.30Pm | Completed
|  | Seraching animation template for ETS | 6.30Pm | 6.48Pm
2016-04-13 | Kalai
Absent
2016-04-13 | Madhi | Daily Report Sheet Updation for Team | 10.10 AM | 10.30 AM | Completed
|  | Xyget Modules details | 10.30 AM | 10.45 AM | Completed
|  | Daily Report Sheet Updation for Team | 10.45 AM | 11.20 AM | Completed
|  | Xyget Testing after search option updated by Ramya | 11.30 AM | 12.45 PM | Pending | Need to Continue
|  | Eventswat Name Searching | 12.45 PM | 2.00 PM | Completed
|  | ETS Project Portfolio | 3.00 PM | 7.00 PM | Pending
|  | Wellocity Issues update | 7.00 PM | 7.25 PM | Completed
|  | Daily Report Sheet Updation for Team | 7.30 PM | 8.30 PM | Completed
2016-04-13 | Muthu | Typing test | 10.00 AM | 10.30 AM | Completed
|  | Printer Concept | 10.30 AM | 2.00PM | Pending
|  | Printer Concept | 3.00 PM | 8.30 PM | Pending | Partially completed
2016-04-13 | Nithya | Typing test | 9:45 | 10:15AM | Completed
|  | Standup meeting,Atomicka responsive design | 10:15AM | 1:45PM | Pending
|  | Atomicka responsive design | 2:45PM | 8:35PM | Pending | index page responsive is pending
2016-04-13 | Ramya | attended typing test | 9.45 AM | 10.15 AM
|  | attended standup meeting | 10.15 AM | 10.20 AM
|  | started to produce result in product based results | 10.30 AM | 1.30 PM
|  | worked in related searches in company based search | 3.00 PM | 8.00 PM
2016-04-13 | Santosh | Happijourney | 9.30 AM | 1.30 PM | Completed | Full testing completed
|  | e-learning functionality testing | 2.30 PM | 6.30 PM | Pending | in progress
2016-04-13 | Siva Rama Kannan | Typing test | 09.30 AM | 10.00 AM
|  | Fixing issues in evinity | 10.00 AM | 10.30 AM | Completed
|  | Fixing issues in validation of teacher_login page | 10.30 AM | 11.30 AM | Completed
|  | Adding multiple selectbox in teacher_registration page | 11.30 AM | 12.30 PM | Completed
|  | Explaining my project to tester testing | 12.30 PM | 1.00 PM
|  | Adding week class in student_login page and devolping new page for this | 2.00 PM | 4.30 PM | Completed
|  | Integrating style file evinity | 4.30 PM | 5.00 PM | Completed
|  | Adding detail option in student login page | 5.00 PM | 6.00 PM | Completed
|  | Adding alternate class in student_login page | 5.00 PM | 7.00 PM | In progress
2016-04-13 | Vignesh | worked in happi journey website to fix issues
|  | worked in giving link in home page | 10.00am | 12.00am | Completed
|  | worked in error message bugs | 12.00am | 12.30pm | Completed
|  | worked in alignment issue | 12.30pm | 4.00pm | Completed
|  | worked in validation message errors | 4.00pm | 5.00pm | Completed
|  | worked in field validation error messages | 5.00pm | 7.30pm | Completed

## 12.04.2016
Date | Name | Task | Start time | End time | Status | Comment
2016-04-12 | Asai | Process in flash animation | 9:30 | 6:45:PM | Completed
2016-04-12 | Ashok Raj
Absent
2016-04-12 | Barath | ETS PRO FILE RE Creation | 10.00Am | 11.30AM | Completed
|  | PhotoShoot | 12.00PM | 1.30PM | Completed
|  | ID Card Designing | 2.30PM | 6.40PM | Completed
2016-04-12 | Kalai | taken one interview for fresher person | 11.00 am | 11.30 am | completed
|  | Worked in xyget image upload process for business user module | 11.30 am | 1.40 pm | completed
|  | Worked in xyget image upload process in Advertisement Module | 2.40 pm | 5.30 pm | completed
|  | Discussed the XYGET future version in python with deepak and sastha | 5.30 pm | 6.00pm | completed
|  | Integrated the ramya and my code, then moved in server | 6.15 pm | 7.50 pm | completed
2016-04-12 | Madhi | Daily Report Sheet Updation for Team | 10.40 AM | 11.10 AM
|  | Xyget Bug Report updation and mail sent to Sastha, Ramya | 11.10 AM | 11.40 AM | Completed | Session Error, updated to Sastha
|  | Xyget Testing creating new product and updating | 11.40 AM | 2.00 PM
|  | Xyget image Upload Module Testing | 3.10 PM | 6.30 PM
|  | Printer Concept | 6.30 PM | 8.10 PM
|  | Daily Report Sheet Updation for Team | 8.25 PM | 9.00 PM
2016-04-12 | Muthu | Typing test | 10.00 AM | 10.30 AM | Completed
|  | Printer Concept apply to atomicka | 10.30 am | 1.45 pm | Pending | cross platform issue
|  | Printer Concept apply to client machine | 1.45 AM | 7.00 PM | Pending | Network slow in cilent side
|  | Get the full thalappakattu code from atomicka | 7.00 PM | 9.00 PM
2016-04-12 | Nithya | Typing test | 9:40 | 10:15 | Completed
|  | standup meeting,oozaaoo responsive design for inbound | 10:!5 AM | 13:50 | Completed
|  | Atomicka responsive design | 14:50 | 21:30 | In Progress
2016-04-12 | Ramya | attended Typing Test | 9.45am | 10.30am | completed
|  | fixed issues in bugreport | 10.35am | 12.15pm | completed
|  | attended standup meeting | 12.15pm | 12.30pm
|  | corrected mail template code | 12.45pm | 3.55pm
|  | worked with search results listing and advertisement redirection | 4.15pm | 8.40pm
2016-04-12 | Santosh | e-learning functionality testing | 9.00am | 6.20pm | Pending | in progress
2016-04-12 | Siva Rama Kannan | Typing test | 09.30 AM | 10.00 AM
|  | Fixing datepicker issues in elearning | 10.00 AM | 11.00 AM | Completed
|  | Disussed with tester | 11.15 AM | 300:00
|  | Fixing issues in student reg,teacher reg,class,branch page | 12.00 PM | 1.30 PM | Completed
|  | Validation in teacher_dashboard page | 3.00 PM | 4.00 PM | In progress
|  | Changing content in evinity | 4.30 PM | 8.00 PM | Completed
2016-04-12 | Vignesh | worked in happi journey website to upload new images and | 10.00am | 2.00pm | Completed
remove repeated images
|  | worked on giving path to the uploaded new images | 3.00pm | 5.00pm | Completed
|  | worked in footer area to provide link for the footer menus | 5.00pm | 7.00pm | Completed | had issue with searching the desired
|  | and aligned the footer section |  |  |  | css file and giving link.

## 11.04.2016
Date | Name | Task | Start time | End time | Status | Comment
2016-04-11 | Asai | Process in oozaaoo inbound images size croping and Searching | 9:30 | 10:30 | Completed
|  | process in Flash intro animation | 10:30 | 19:30 | Complted
2016-04-11 | Ashok Raj
Absent
2016-04-11 | Barath | Image Resizing for Oozzaaoo | 10.00AM | 10.30AM | Completed
|  | Image Resizing for Happy Journey | 10.30AM | 11.00AM | Completed
|  | ETS PRO REDIESGN | 11.00AM | 6.30PM | Completed
2016-04-11 | Kalai | Xyget: Business User Logo upload | 10.35 AM | 1.30 PM
|  | Implemented the printer concept in node.js for atomicka | 2.15 pm | 8.15 pm
2016-04-11 | Madhi | Daily Report Sheet Updation for Team | 9.45 AM | 10.00 AM | Completed
|  | Typing skills | 10.00 AM | 10.20 AM |  | Session error
|  | Xyget.com testing recheck | 10.20 AM | 10.40 AM |  | Session Error, updated to Sastha
|  | Learning Javascript | 10.40 AM | 1.00 PM
|  | Xyget.com testing recheck | 1.00 PM | 8.00 PM
|  | Daily Report Sheet Updation for Team | 8.00 PM | 8.30 PM
2016-04-11 | Muthu | Printer Concept | 10.00 AM | 2.00 PM | Pending | Handover to kalai
|  | Xyget: Post Advertisement in Admin & fixing Login issue | 3.00 PM | 8.00 PM | Pending | Ajax calling and validation for form
Xyget: Need to view the product & advertisement details(just with non-editable fields) before approve in admin
2016-04-11 | Nithya | Oozaaoo: Inbound & Outbound Responsive Design | 10.00 AM | 6.30 PM
|  | Typing test | 9:30 | 10:15 | Completed
|  | oozaaoo responsive design for outbound | 10:15 | 14:00 | Completed
|  | design and content correction in oozaaoo,responsive for inbound | 15:00 | 20:00 | Pending | inbound responsive is pending
2016-04-11 | Ramya | attended Typing Test | 09.40am | 10.10am | Completed
|  | started to analyze the issues in xyget listed as prioritrized | 10.15 AM | 10.30am | Completed
|  | checked xyget advertisement and product based results and checked db error in live | 10.35pm | 11.30am | Completed
|  | started to fix issue on wct (dob validation) | 11.30am | 1.50pm | Pending | partially completed
|  | test clone content validation | 3.00pm | 6.20pm | completed
|  | proceeded with popup validation for dob(add athletes, create schedule) | 6.30pm | 8.00pm | Pending | partially completed
2016-04-11 | Santosh | wellocity | 11.00am | 6.45pm |  | In processing (completed MASER menu)
|  | wellocity | 9.30am | 1.30pm |  | Functionality testing completed
|  | wellocity | 9.30am | 6.45pm |  | Check the design, functionality testing and read the wellocity requirement document .
|  | wellocity | 8.10am | 8.10pm |  | Full testing in progress
|  | wellocity | 9.30am | 10.30am |  | Flow testing (issue persist)
|  | XYGET.com | 10.30am | 5.30pm |  | Functionality testing (on-hold)
|  | e-learning | 5.30pm | 7.35pm |  | Check with work flow.
2016-04-11 | Siva Rama Kannan | Typing Test | 9.30 AM | 10.15 AM
|  | Printing table in report_action page | 10.15 AM | 12.30 PM | Completed
|  | Fixed issues in teacher_login | 12.30 PM | 1.30 PM | Completed
|  | Show current day based on system date | 1.30 PM | 2.00 PM | Completed
|  | Explain my project to tester | 3.00 PM | 3.30 PM
|  | Changed report page design | 3.30 PM | 4.30 PM | Completed
|  | Test my project and fixed some issues | 5.45 PM | 6.15 PM | Completed
|  | Validation in makeup slots | 5.45 PM | 6.15 PM | In progress
2016-04-11 | Vignesh
Absent

## 09.04.2016
Date | Name | Task | Start time | End time | Status | Comment
2016-04-09 | Asai | Process in Home page design alter | 9:30 | 10:30 | Completed
|  | Process in Pricing , Signup, login page design completed | 10:30 | 15:30 | Complted
|  | Process in Pricing , Signup, login page Responsive design completed | 15:30 | 18:51 | Completed
2016-04-09 | Ashok Raj
Absent
2016-04-09 | Barath | OOZZAAO Image Resizing | 9.40AM | 10.00AM | Completed
|  | Animation Templates Seraching | 10.00Am | 2.00PM | Completed
|  | Animation for ETS(2 PART) | 3.00PM | 6.30PM | Completed | Remaining in process
2016-04-09 | Kalai | Checked the wellocity website design issues and inform to nithya, discussed logic functionalities with mathi and santhosh | 10:55 | 11:45 | Completed
|  | Started to work on resell and configured the crm project for ozzaaoo via teamviewer | 11:45 | 13:30 | Completed
|  | Moved the wellocity, XYGET code in server and checked the logical concepts in range by entering test data in all modules | 2.30 pm | 4.00 pm | Completed
|  | Started to work on resell and fixed the view, edit and delete issues in my account mobile responsive | 4.15 pm | 6.00 pm | Completed
|  | installed the node.js and npm packages to generate pdf for printer in both windows and ubuntu | 6.00 pm | 8.15 pm | pending
2016-04-09 | Madhi | Wellocity: Testing and bugs reported to Muthu and Kalai | 10.00AM | 8.30 PM | Completed | Bug Sheet updated & issues are intimated to developers
|  | Daily Report Sheet Updation for Team | 8.30 PM | 9.15 PM | Completed | Send Mail to Sastha
2016-04-09 | Muthu | check on php printer.dll in windows 8.1 machine and communicate with atomick team.Fixing issues in wellocity | 10.45AM | 2.00PM | Completed | php_printer.dll not working in windows 8.1
|  | work with clinent machine | 3.00 PM | 4.00 PM | completed
|  | Start printer concept using node js | 4.00 PM | 199:12 | In Progress
2016-04-09 | Nithya | Typing test | 9:50 | 10:20 | Completed
|  | Fixed css issues in wellocity | 10:20 | 14:00 | In Progress
|  | Fixed css issues in wellocity,oozaaoo responsive design integration with vignesh | 15:00 | 20:30 | Completed
2016-04-09 | Ramya | Attended typing test | 10:00 | 10.15 AM | Completed
|  | made some css corrections in oozaaoo | 10.15 AM | 11.45 AM | Completed
|  | Started to fix issues in wct validation(test and parameter) | 12.00 PM | 3.45 PM | Completed
|  | Started to fix issues in wct validation(assign schedule and add athletes) | 15:55 | 4.10 PM | Completed
|  | Started to fix issues in xyget bug report | 4.15pm | 6.20pm | in progress
|  | helped to integrate Oozaaoo corrections | 6.25pm | 8.20pm | Completed
2016-04-09 | Santosh | wellocity | 8.10am | 8.10pm | Full testing | in progress
2016-04-09 | Siva Rama Kannan | Typing Test | 9.30 AM | 10.00 AM
|  | Show the upcoming classes for 14days | 10.00 AM | 12.00 AM | Completed
|  | Creating delete option in class_schedules for student | 0:00 | 1.30 PM | Completed
|  | Validating the checkbox based on number of seats availability | 2.30 PM | 4.30 PM | Completed
|  | Added class field in student_registration and doubt clarification | 4.30 PM | 5.30 PM | Completed
|  | Validating the checkbox based on number of seats availability in edit_schedules | 5.30 PM | 6.30 PM | Completed
|  | Printing schdule based on given image | 6.30 PM | 7.00 PM | In progress
2016-04-09 | Vignesh | worked in responsive outbound page | 10.00am | 2.00pm | Pending | alignment issue
|  | Worked in responsive inbound page | 4.00pm | 7.00pm | Pending | image not aligned using responsive
|  | worked in responsive outbound for empty sapce clearing | 2.00pm | 4.00pm | Completed

## 08.04.2016
Date | Name | Task | Start time | End time | Status | Comment
2016-04-08 | Asai | Process in Invoice generator website Template page completed | 9:30 | 12:50 | Completed
|  | Process in Invoice generator website Template page completed Responsive page | 12:50 | 2:00 | Completed
|  | Process in Invoice generator website Blogs page completed | 15:00 | 17:00 | Completed
|  | Process in Invoice generator website Blogs page completed Responsive page | 17:00 | 18:56
2016-04-08 | Ashok Raj | Typing test | 9.45 am | 10.00 am | completed
|  | inbound responsive design | 10.00 am | 12.30 am | Inprogress
|  | corrections in inbound design | 12.30 pm | 2.00 pm | Inprogress
|  | Studying media queries and bootstrap | 3.15 pm | 4.30 pm | Inprogress
|  | Studying media queries and bootstrap | 4.45 pm | 7.00 pm | Inprogress
2016-04-08 | Barath | E-mail Signature to ETS | 10.AM | 11.30AM | Completed
|  | ETS PRO Poster for FB | 11.30am | 1.00PM | Pending
|  | ETS PRO Poster for FB | 9.30AM | 10.50AM | Completed | Waiting for approval to upload
|  | ETS PRO Poster for Linked in | 10.50AM | 12.12PM | Completed | Waiting for approval to upload
|  | ETS BUSINESS PROFILE COVER PAGE | 12.12PM | 3.30PM | Completed
|  | Wall motivation Designing sample one done | 3.30PM | 6.30PM | in process | Waiting for approval
2016-04-08 | Kalai | Fixed some issues in wellocity grid formation | 11.00 am | 11.45 am | Completed
|  | Shared Wellocity concepts of some module dependency and their output to santhosh and madhivanan | 12.00 pm | 12.50 pm | Completed
|  | Prepared the task document for atomicka intent which is given by sastha | 12.50 pm | 1.30 pm | Completed
|  | Fixed some issues in wellocity Autosuggestion input and range module dependency | 2.30 pm | 4.00 pm | Completed
|  | Observe the design issues which was fixed by deepak in wellocity and shared the wellocity concepts with madhivanan | 4.00 pm | 7.45 pm
2016-04-08 | Madhi | Wellocity: Testing and bugs reported to Muthu and Kalai | 10.00AM | 7.30 PM | Completed | Concept having been discussed with Deepak, Sastha, Muthu & Kalai
|  | Daily Report Sheet Updation for Team | 7.30 PM | 8.00 PM | Completed
2016-04-08 | Muthu | printer concept made remote site and fixing issue in wellocity | 10.00 AM | 7.30 PM | Pending | Wellocity issue fixed . Cannot handle remote side for printer concept
2016-04-08 | Nithya
Absent
2016-04-08 | Ramya
Absent
2016-04-08 | Santosh | wellocity | 9.30am | 6.45pm | Completed | Check the design, functionality testing and read the wellocity requirement document .
2016-04-08 | Siva Rama Kannan | Typing Test | 9.30 AM | 10.00 AM
|  | Analysed the new requirements of e-learning | 10.00 AM | 10.30 AM | Completed
|  | Added extra field in class_schedules form and Stored into db | 10.30 AM | 12.00 PM | Completed
|  | Show the upcoming classes | 12:00 | 1.30 PM | In progress
|  | Mentioned date in student login | 2.30 PM | 3.00 PM | Completed
|  | Creating delete option in class_schedules and Validating the checkbox based on number of seats availability | 03.00 PM | 06.30 PM | In progress
2016-04-08 | Vignesh | Worked in responsive outbound page for all mobiles & | 9.30am | 11.00am | Pending | supporting but getting issue in slider
|  | tabs |  |  |  | image
|  | worked in inbound page for image alignment | 11.00am | 2.00pm | Completed
|  | worked in inbound page for issue in empty space | 3.00pm | 7.00pm | Pending | have difficulty in clearing empty space

## 07.04.2016
Date | Name | Task | Start time | End time | Status | Comment
2016-04-07 | Asai | Process in glass design completed | 9:30 | 12:45 | Completed
|  | Process in Invoice generator website completed | 12:45 | 18:00 | Completed
|  | Process in Invoice generator RESPONSIVE website completed | 18:00 | 19:05 | Completed
2016-04-07 | Barath | E-mail Signature to ETS | 10.AM | 11.30AM | Completed
|  | ETS PRO Poster for FB | 11.30am | 1.00PM | Pending
|  | Wall motivation Image Searching | 1.00PM | 1.45PM | Completed | Waiting for approval
|  | ETS BUSINESS PRO DESIGN | 3.00PM | 6.50PM | Completed
2016-04-07 | Kalai | Gave Resell knowledge transfer to santhosh for testing | 10.45 am | 11.15 am | completed
|  | Implemented Dependecy queries for state, district module and discussed with muthu about that query relationship | 11.30 pm | 1.45 pm | completed
|  | Implemented Dependecy queries for create schedule, athletes and range module | 2.45 pm | 7.30 pm | pending | pending only in range module
2016-04-07 | Madhi | Daily Task Scheduling to Team | 288:00 | 1.00 AM | Completed
|  | Resell Product Updation & Error Documentation | 10.30 AM | 2.00 PM
|  | Daily Task Sheet updation | 3.00 PM | 4.00 PM | Completed
|  | Printer Concept | 4.00 PM | 5.15 PM
|  | Resell Product Updation & Error Documentation | 10.30 AM | 2.00 PM | Completed | Bug Sheet mailed to Sastha and Kalai
|  | Report Sheet Updation | 7.00 PM | 8.00 PM | Pending | Santosh and vignesh report not yet received
2016-04-07 | Muthu | E-Learning: Discuss with clint and do the updation, before that get suggestion with Sastha | 10.15 AM | 11.00 AM | Completed | Sent mail to Sastha
|  | Wellocity Dependency | 11.15 AM | 7.30 PM | Completed
|  | Xyget Issues Fixing |  |  | Hold | Printer concept has high priority
|  | Printer Concept | 7.30 PM | 8.00 PM | Pending
2016-04-07 | Santosh | Wellocity Testing | 9.30am | 1.30pm | completed
|  | Resell Testing | 3.00pm | 4.00pm | pending | on-hold(because again start with wellocity testing)
|  | Wellocity Testing | 4.00pm | 7.00pm | in progress
Xyget Testing
Atomicka Mobile Testing
2016-04-07 | Vignesh | Worked in responsive outbound page | 10.00am | 2.00pm | Completed
|  | Worked in responsive inbound page | 3.00pm | 7.00pm | Pending | not supporting in other devices
|  | Had issue in empty space | 11.00am | 12.30pm | Completed
|  | Have issue in inbound image responsive to be aligned | 5.00pm | 8.30pm | Pending
in proper responsive manner.

## 06.04.2016
Date | Name | Task | Star time | End time | Status | Comment
2016-04-06 | Asai | Atomicka Logo |  |  | Completed
|  | ID Card for Kumaran, Barath, Vignesh & Ramalingam |  |  | asking for photos
|  | Cotton House Logo |  |  | Waiting for Clint reply
|  | Eventswat Logo & Color Corrections |  |  | Working
|  | Online Mobile Invoice |  |  | Invoice Layout postpond to tomorrow
| Barath | Id Card for staffs Design | 10.00 AM | 11.00 AM | Photo insertion is pending, other details are completed.
|  | Logo design to where eventz.. One sample | 11.00 AM | 1.40 PM | Completed
|  | Seraching ae templates for animation | 3.00 PM | 6.00 PM | Completed
| Kalai | Resell: Mobile & Desktop Issues fixing |  |  | Before 09.04.2016 7.00 PM
|  | Wellocity: 4 Issues assigned | 11.00 AM | 1.30 PM | Completed
|  | Wellocity: ramya validation part | 3.50 PM
Site function explaination to Santosh
| Madhi | Daily Task Scheduling to Team | 9.30 AM | 10.30 AM | Completed and System arrangement to Santosh
|  | Daily Task Sheet updation | 10.30 AM | 11.30 AM | Formate updation and Task updated
|  | Collecting all Design issues | 11.30 AM | 288:00
|  | Discussion with Muthu & Kalai about code extraction | 12.00 PM | 12.30 PM
|  | Discussion with Deepak and Asai about Domain Name for Eventswat | 12.30 PM | 1.00 PM
|  | Discussion with Deepak and Vignesh about Xampp | 1.00 PM | 1.30 PM
|  | Chennai Folder | 2.30 PM | 6.20 PM
|  | Resell Product Updation | 6.20 PM | 8.00 PM
Getting Tomorrow Task details for Team
| Muthu | Wellocity: 6 Issues assigned |  |  | Completed
|  | E-Learning: Discuss with clint and update |  |  | Clint not responding
|  | Assign Wellocity testing to Santosh |  |  | Completed
| Santosh | Wellocity Testing |  |  | Working
Resell Testing
Xyget Testing
Atomicka Mobile Testing
| Vignesh | Oozaaoo: Inbond Responsive | 9.30 AM | 1.00 PM | Working
|  | Oozaaoo: Outbond Responsive | 2.00 PM | 7.00 PM
|  | Chennai Folder |  |  | Postpond after completing Oozaaoo