## Team Task Today
Date | Name | Task | Start time | End time | Status | Comment
2016-04-07 | Asai | Online Mobile Invoice: 15 days work should be deliver first
Website Animation
Cotton House Logo
Eventswat Logo & Color Corrections
Evinity Template (Add more Photo Slides)
ETS Profile need in PDF formate
Wall motivation theme
Glass design stickers
Facebook & Linkedin, add related post and promote
Mail Signature for Deepak, HR, Sastha
2016-04-07 | Barath
Asai will assign
2016-04-07 | Kalai | Resell Issues
Wellocity Dependency
Resell Scenario explaination to Santosh(Tester) Both Mobile & Desktop
2016-04-07 | Madhi | Daily Task Scheduling to Team | 288:00 | 1.00 AM | Completed
|  | Daily Task Sheet updation | 3.00 PM | 4.00 PM | Completed
|  | Chennai Folder |  |  | Pending | Not yet start
|  | Evinity |  |  | Pending | Not yet start
|  | Etekchnoservices Site |  |  | Pending | Not yet start
|  | Resell Product Updation & Error Documentation | 10.30 AM | 2.00 PM | Pending
|  | Printer Concept | 4.00 PM | 5.15 PM
2016-04-07 | Muthu | E-Learning: Discuss with clint and do the updation, before that get suggestion with Sastha | 10.15 AM | 11.00 AM | Completed | Sent mail to Sastha
|  | Wellocity Dependency | 11.15 AM | 4.30 PM | Completed | Sent mail to Sastha
|  | Xyget Issues Fixing |  |  | Hold | Printer concept has high priority
|  | Printer Concept | 4.30 PM |  | High Priority
2016-04-07 | Santosh | Wellocity Testing
Resell Testing
Xyget Testing
Atomicka Mobile Testing
2016-04-07 | Vignesh | Oozaaoo: Inbond Responsive | 10.00 AM | 4.00 PM
|  | Oozaaoo: Outbond Responsive full completion | 4.00 PM | 5.00 PM
Chennai Folder
Etekchnoservices Site
2016-04-07 | Deepak | Events Domain name suggestion 5
Wellocity Design Issues 3
Atomicka Mobile (Deadline 8th April)
Oozaaoo Templates

## Asai
Date | Name | Task | Start time | End time | Status | Comment
2016-04-07 | Asai | Online Mobile Invoice: 15 days work should be deliver first
Website Animation
Cotton House Logo
Eventswat Logo & Color Corrections
Evinity Template (Add more Photo Slides)
ETS Profile need in PDF formate
Wall motivation theme
Glass design stickers
Facebook & Linkedin, add related post and promote
Mail Signature for Deepak, HR, Sastha

## Barath
Date | Name | Task | Start time | End time | Status | Comment
2016-04-07 | Barath | E-mail Signature to ETS | 10.AM | 11.30AM | Completed
|  | ETS PRO Poster for FB | 11.30am | 1.00PM | Pending
|  | Wall motivation Image Searching | 1.00PM | 1.45PM | Completed | Waiting for approval
|  | ETS BUSINESS PRO DESIGN | 3.00PM | 6.50PM | Completed
2016-08-04 | BARATH | ETS PRO Poster for FB | 9.30AM | 10.50AM | Completed | Waiting for approval to upload
|  | ETS PRO Poster for Linked in | 10.50AM | 12.12PM | Completed | Waiting for approval to upload
|  | ETS BUSINESS PROFILE COVER PAGE | 12.12PM | 3.30PM | Completed
|  | Wall motivation Designing sample one done | 3.30PM | 6.30PM | in process | Waiting for approval
2016-09-04 | BARATH | OOZZAAO Image Resizing | 9.40AM | 10.00AM | Completed
|  | Animation Templates Seraching | 10.00Am | 2.00PM | Completed
|  | Animation for ETS(2 PART) | 3.00PM | 6.30PM | Completed | Remaining in process
2016-11-04 | Barath | Image Resizing for Oozzaaoo | 1.00AM | 10.30AM | Completed
|  | Image Resizing for Happy Journey | 10.30AM | 11.00AM | Completed
|  | ETS PRO REDIESGN | 11.00AM | 6.30PM | Completed
2016-12-04 | Barath | ETS PRO FILE RE Crection | 10.00Am | 11.30AM | Completed
|  | PhotoShoot | 12.00PM | 1.30PM | Completed
|  | ID Card Designing | 2.30PM | 6.40PM | Completed
13-4-2016 | Barath | happy journey image resizing | 10.00Am | 10.30AM | Completed
|  | ID Card Designing and correction | 10.30Am | 1.40PM | Completed
|  | wall motion iamge deigning | 2.45Pm | 4.30Pm | Completed
|  | Promo add designing and correction | 4.30Pm | 6.30Pm | Completed
|  | Seraching animation template for ETS | 6.30Pm | 6.48Pm
15-4-2016 | Barath | Image resizing to OOZZAAOO | 10.00AM | 10.30AM | Completed
|  | wall motion iamge deigning | 10.30AM | 1.30PM | Completed | 2 sample done
|  | ID CARD correction | 3.00PM | 3.30PM | Completed
|  | wall motion iamge deigning | 5.00pm | 6.30pm | Completed | 2 sample done
18-4-2016 | Barath | ID CARD Correction | 9.3am | 6.15 pm | Completed
19-4-2016 | Barath | Banner Slider Image designing | 10.00Am | 6.15PM | Completed | 4 Slides
|  | GS Despktop Image Designing | 6.15PM | 6.30PM | Completed
20-4-2016 | Barath | Banner Slider Image designing and Correction | 10.00Am | 1.30PM | Completed | 3 New Sample
|  | ID Card Correction | 2.45PM | 3.15PM | Completed
|  | Banner Slider Image designing and Correction | 3.15PM | 5.30PM | Completed
|  | Analysing XYGET Design | 5.30PM | 6.30PM | ON Process
21-4-2016 | Barath | Taking screen shot for Xygate site | 9.45Am | 10.30AM | Completed
|  | deasiging Login Page | 10.30Am | 1.30PM | Completed
|  | Designing Search Page | 2.30PM | 4.30PM | Completed
|  | Desiging 404 error, 400error,500Error, 403 error page | 6.00Pm | 6.30PM | Completed
|  | Meeting With HR | 4.30Pm | 5.30PM
22-4-2016 | Barath | pick opproprite pages have to design in Xyget | 10.00AM | 10.30AM | Completed
|  | Designing HOME to Xyget | 10.30AM | 1.30PM
|  | Correction in Evinity Banner | 4.30PM | 6.10PM | Completed
|  | Designing HOME to Xyget | 6.30PM | 6.30PM | in process
23-4-2016 | Barath | Designing HOME to Xyget | 10.00AM | 12.30PM | Completed
|  | Correction in Evinity Banner | 12.30PM | 1.30PM | Completed
|  | Evinity Broucher Designing | 2.45PM | 6.30PM | Completed

## Kalai
Date | Name | Task | Start time | End time | Status | Comment
2016-04-07 | Kalai | Resell Issues
Wellocity Dependency
Resell Scenario explaination to Santosh(Tester) Both Mobile & Desktop

## Madhi
Date | Name | Task | Start time | End time | Status | Comment
2016-04-07 | Madhi | Daily Task Scheduling to Team | 288:00 | 1.00 AM | Completed
|  | Resell Product Updation & Error Documentation | 10.30 AM | 2.00 PM | Pending
|  | Chennai Folder |  |  | Pending | Not yet start
|  | Evinity |  |  | Pending | Not yet start
|  | Etekchnoservices Site |  |  | Pending | Not yet start
|  | Daily Task Sheet updation | 3.00 PM | 4.00 PM | Completed
|  | Printer Concept | 4.00 PM | 5.15 PM
|  | Resell Product Updation & Error Documentation | 5.15 PM | 6.30 PM

## Muthu
Date | Name | Task | Start time | End time | Status | Comment
2016-04-07 | Muthu | E-Learning: Discuss with clint and do the updation, before that get suggestion with Sastha | 10.15 AM | 11.00 AM | Completed | Sent mail to Sastha
|  | Wellocity Dependency | 11.15 AM | 4.30 PM | Completed
|  | Xyget Issues Fixing |  |  | Hold | Printer concept has high priority
|  | Printer Concept | 4.30 PM |  | High Priority

## Santosh
Date | Name | Task | Start time | End time | Status | Comment
2016-04-07 | Santosh | Wellocity Testing
Resell Testing
Xyget Testing
Atomicka Mobile Testing

## Vignesh
Date | Name | Task | Start time | End time | Status | Comment
2016-04-07 | Vignesh | Oozaaoo: Inbond Responsive | 10.00 AM | 4.00 PM
|  | Oozaaoo: Outbond Responsive full completion | 4.00 PM | 5.00 PM
Chennai Folder
Etekchnoservices Site

## Sheet1
ADMIN PART | ESTABLISHMENT PROFILE PAGE | 2 DAY
Xygate Admin Authentication
Xygate Admin Country MAster
Xygate Admin module category
Xygate Admin module list
Xygate Admin Resigter user
Xygate Admin user role
Xygate Admin General City MAster
Xygate Admin General State MAster
Xygate Admin Page
Xygate Admin Sector
Xygate AdminProduct Category
END USER PART and Business Client PArt | Advertisement create Edit Existing create new Adv page | 6day
Advertisement create Edit Existing page
Advertisement create new page
Advertisement page
BUSINESS CLIENT OWNER DETAILS PAGE
BUSINESS CLIENT PROFILE FULL VIEW
BUSINESS CLIENT PROFILE PAGE
BUSINESS LOGIN PAGE
CHAT PAGE
Contact Info page
Content Mangement Activities Page
Content Mangement Profile Page
HOME PAGE
image Management Gallery page
image Management Header Settings
Image Management Logo Upload page
Product page
Register Business Details Page
Register Page
Setting Page
Tearms And condition page
DEFAULT PART | ERROR 404
ERROR 403
ERROR 500
ERROR 400