## Sheet1
Date | Name | Task | Star time | End time | Status | Comment
2016-04-06 | Santhosh | wellocity | 11.00am | 6.45pm | In processing (completed MASER menu)
2016-04-07 |  | wellocity | 9.30am | 1.30pm | Functionality testing completed
2016-04-08 |  | wellocity | 9.30am | 6.45pm | Check the design, functionality testing and read the wellocity requirement document .
2016-04-09 |  | wellocity | 8.10am | 8.10pm | Full testing
2016-04-11 |  | wellocity | 9.30am | 10.30am | Flow testing (issue persist)
2016-04-11 |  | XYGET.com | 10.30am | 5.30pm | Functionality testing (on-hold)
2016-04-11 |  | e-learning | 5.30pm | 7.35pm | Check with work flow.
2016-04-12 |  | e-learning functionality testing | 9.00am | 6.20pm | in progress
2016-04-13 |  | Happijourney | 9.30am | 1.30pm | Full testing completed
2016-04-13 |  | e-learning functionality testing | 2.30pm | 6.30pm | in progress
2016-04-15 |  | wellocity | 9.10am | 9.50pm | Full testing
2016-04-19 |  | E-learning | 11.00am | 8.00pm | Functionality testing
2016-04-20 |  | E-learning | 9.00am | 1.30pm | Not completed
2016-04-20 |  | wellocity | 2.30pm | 8.30pm | in progress
2016-04-21 |  | E-learning | 9.15am | 7.00pm | in progress in logical testing | issues persist
2016-04-22 |  | E-learning testing | 9.00am | 1.30pm | Completed
2016-04-22 |  | Infom atomicka testing | 2.10pm | 7.50pm | Completed
2016-04-23 |  | Infom atomicka testing in windows | 8.30am | 1.30pm | completed | issues persist
2016-04-23 |  | Infom atomicka responsive testing | 3.00pm | 8.45pm | completed | issues persist
2016-04-25 |  | Infom atomicka regression testing windows and mobile | 9.30am | 5.30pm | completed | issues persist
2016-04-25 |  | Resell - overview of the site | 5.30pm | 6.25pm | Pending
2016-04-26 |  | Typing test | 9.30am | 10.00am | completed
2016-04-26 |  | e-vinity full testing | 10.00am | 5.00pm | completed
2016-04-26 |  | Infom atomicka mobile testing | 5.00pm | 7.30pm | Pending