## Sheet1
DATE | NAME | TASK | START TIME | END TIME | STATUS
2016-09-04 | Ramya | Attended typing test | 10:00:00 AM | 10.15 AM | Completed
|  | made some css corrections in oozaaoo | 10.15 AM | 11.45 AM | Completed
|  | Started to fix issues in wct validation(test and parameter) | 12.00 PM | 3.45 PM | Completed
|  | Started to fix issues in wct validation(assign schedule and add athletes) | 15:55 | 4.10 PM | Completed
|  | Started to fix issues in xyget bug report | 4.15pm | 6.20pm | in progress
|  | helped to integrate Oozaaoo corrections | 6.25pm | 8.20pm | Completed
2016-11-04 | Ramya | attended Typing Test | 09.40am | 10.10am | Completed
|  | started to analyze the issues in xyget listed as prioritrized | 10.15 AM | 10.30am | Completed
|  | checked xyget advertisement and product based results and checked db error in live | 10.35am | 11.30am | Completed
|  | started to fix issue on wct (dob validation) | 11.30am | 1.50pm | partially completed
|  | test clone content validation | 3.00pm | 6.20pm | completed
|  | proceeded with popup validation for dob(add athletes, create schedule) | 6.30pm | 8.00pm | partially completed
2016-12-04 | Ramya | attended Typing Test | 9.45am | 10.30am | completed
|  | fixed issues in bugreport | 10.35am | 12.15pm | completed
|  | attended standup meeting | 12.15pm | 12.30pm
|  | corrected mail template code | 12.45pm | 3.55pm
|  | worked with search results listing and advertisement redirection | 4.15pm | 8.40pm
04/13/16 | Ramya | attended typing test | 9.45am | 10.15 AM
|  | attended standup meeting | 11.15 AM | 11.25am
|  | started to produce result in product basedresults | 11.30am | 1.30pm
|  | worked in related searches in company based search | 3.00pm | 8.00pm
04/15/16 | Ramya | attended typing test | 9.45am | 10.30am | completed
|  | Fixed the results in related search based on company with out city match | 10.35am | 1.30pm | completed
|  | started to correct the results in related search based on company | 3.40pm | 6.30pm | completed
|  | fixed issues in wct validation | 6.40pm | 9.40pm | completed
|  | dob calidation |  |  | in progress
04/16/16 | Ramya | attended typing test | 9.50am | 10.30am | completed
|  | fixed issues listed in bugreport(wct) & fixed issues reported by madhivanan | 10.30am | 10.50pm | completed
04/18/16 | ramya | atteded typing test | 9.50am | 10.30am | completed
|  | fixed issues listed by madhivanan in wct proect | 10.35am | 9.00pm | completed
04/19/04 | ramya | atteded typing test | 10.15am | 10.45am | completed
|  | tried to fix issues on dob and fixed some corrections in error msg displaying | 10.50am | 1.15pm | completed
|  | had a discussion with team members and Mr.sastha,Mr.Deepak and Mr.Kumaran | 1.20pm | 2.30pm
|  | continued with the dob issue | 3.30pm | 9.00pm | completed
|  | tried to fix issues in assign schedule popup | 9.00pm | 9.20pm | in progress
04/20/16 | ramya | attended typing test | 9.50am | 10.45am | completed
|  | started to fix issues in assign schedule popup while submission and adding athletes | 11.05am | 1.30pm | completed
|  | fixed issues in reported by madhivanan and santhosh | 3.05pm | 7.45pm | completed
|  | Proceeded with xyget project issues in mail function | 7.50pm | 8.20pm
| ramya | atteded typing test | 10.15am | 10.45am | completed
|  | mail sending after approval | 11.20am | 3.30pm | completed
|  | city based search for products and companies | 3.45pm | 8.30pm | partially completed
|  | bugreport issues |  |  | pending
04/26/16 | ramya | typing test | 10.50am | 11.30am | completed
|  | fixed issues in bug report (atomicka) joinus and reach us page | 11.45am | 5.30pm | completed
|  | analyzed code for sms sending | 5.30PM | 6.30PM | in progress
|  | started to work on xyget search part based on city | 6.30PM | 7.00pm | in progress
|  | captcha validation in joinus page | 7.00pm | 7.40pm | completed
04/27/16 | ramya | attended typing test | 10.10am | 10.50am | completed
|  | attended standup meeting and fixed city based company search | 10.55am | 11.45am | completed
|  | tested atomicka reachus and join us form validations | 11.50am | 1.30pm | completed
|  | atomicka mobile (joinus ) validation | 3.10pm | 8.30pm | in progress
04/25/16 | ramya | atteded typing test | 9.45am | 10.30am | completed
|  | added validation code in evinity | 10.40am | 1.30pm | completed
|  | atomicka joinus form validation | 3.00pm | 5.20pm | completed
04/28/16 | ramya | attended typing test and standup meeting | 10.20am | 10.50am | completed
|  | fixed atomicka mobile (joinus form validation) | 11.40am | 1.10pm | completed
|  | fixed city based product search | 3.30pm | 4.10pm | completed
|  | refered about jquery buttons defaults actions | 4.20pm | 4.40pm
|  | proceeded with city based search implementation in advanced search | 4.50pm | 6.40pm | in progress
04/29/16 | ramya | attended typing test | 10.00am | 10.40am | completed
|  | fixed issue while displaying auto suggestion for the first time after the page was get refreshed. | 10.45am | 11.20am | completed
|  | proceeded with xyget city based advanced search | 11.25am | 1.30pm | completed
|  | fixed issue while displaying products related to the city. | 3.10pm | 5.15pm | completed
|  | related search based on products | 5.20pm | ila | in progress
04/30/16 | ramya | attended typing test and standup meeting | 10.00am | 10.40am
|  | refered for sms code integration | 10.45am | 11.20am | completed
|  | integrated sms code after product was posted | 11.30am | 1.30pm | in progress
2016-02-05 | ramya | atteded typing test and statndup meeting | 10.10am | 11.20am | completed
|  | fixed wct issues | 11.30am | 1.30pm | completed
|  | did some minor corrections and proceeded with xyget sms code integration after product was posted and after admin approval for products | 3.20pm, | 8.00pm | completed