## 06.05.2016
Date | Name | Task | Start time | End time | Status | Comment
2016-05-06 | Akila | Typing test | 09:35am | 10.15am | Completed
|  | Meeting with Nithya,Standup meeting | 10.30am | 11.40am | Completed
|  | Continued working on task assigned | 11.40am | 01.55pm | Pending
|  | KT from Deepak | 02.50pm | 03.50pm | Completed
|  | Continued working on task assigned | 04.00pm | 07.00pm | Pending | Facing design issue in structure, rectifying again from starting
|  | KT from Deepak | 07.00pm | 08.15pm
2016-05-06 | Balasubramaniam | Typing Test | 9:15AM | 10:45AM
|  | Meeting | 10:46AM | 11:30AM
|  | logo making | 11:33AM | 12:03AM
|  | set logo on the web page | 12:30PM | 1:15PM
|  | set the padding and morgin for this page | 1:30PM | 2:00PM
|  | form arrangements and set the page formats | 3:00PM | 4:30PM
|  | study CSS | 4:45PM | 6:30PM
|  | Meeting | 6:45PM | 8:15PM
2016-05-06 | Barath | Designing ETS PROFILE | 10.00Am | 1.45PM | COMPLETED
|  | DESIGNING ETS PORTFOLLIO | 2.40PM | 7.40PM | Pending
2016-05-06 | Kalai | Fixed issues in resell chat history appending process for each and every product | 11.00 am | 2.00 pm | completed
|  | Fixed image cropping issues in post ad form using server side code, moved the updated resell code in server | 3.05 pm | 6.00 pm | completed
|  | tried to fetch the chat history throughout all pages | 6.00 pm | 8.05 pm | pending
2016-05-06 | Madhivanan | Daily sheet report updation | 10.30 AM | 10.50 AM
|  | Typing skills | 10.50 AM | 11.20 AM | Completed
|  | Standup Meeting | 11.20 AM | 11.45 AM | Completed
|  | Mail sent to Vinoth | 11.45 AM | 12.40 PM | Completed | Function flow confirmation for thalapakattu
|  | Search for Roadmap concept | 12.45 PM | 1.00 PM | Completed
|  | ICICI Bank account open | 1.00 PM | 1.45 PM | Completed | About Roadmap and ETS site content
|  | Discussion with Deepak | 1.45 PM | 2.30 PM | Completed
|  | Multi page profile for ETS | 3.15 AM | 3.40 PM | Pending
|  | Name Suggestion for Invoice generator | 3.40 PM | 4.10 PM | Completed
|  | Multi page profile content searching | 4.20 PM | 5.30 PM | Completed | Mail sent to Devi Mam
|  | E-learning and Resell requirement & issues collected | 5.45 PM | 7.00 PM | Completed | Mail sent to Prabhu
|  | Daily sheet report updation | 7.10 PM | 7.35 PM | Pending
|  | Meeting with Deepak | 8.15 PM | 9.30 PM | Completed | About Fixido function flow phase 1
2016-05-06 | Muthu | typing test | 9.30 AM | 10.00AM | Completed
|  | Thalapakattu restaurant flow code analysing | 10.00 AM | 2.00 AM | Completed
|  | Workout restaurant flow as per mail | 3.00 PM | 0:00 | Completed
2016-05-06 | Nithya | meeting with intent about ui | 10:20 | 11:30
|  | Standup meeting,portfolio html design(ETS) | 11:30 | 14:00 | In Progress
|  | Helped siva for ets home page html design,Removed gl animation in Atomicka desktop,portfolio html design | 15:15 | 19:50 | Pop up part is pending
2016-05-06 | Ramya | attended typing test | 10.05am | 10.45am
|  | proceeded to fix issues listed in bugreport | 10.50am | 11.20am | completed
|  | attended standup meeting | 11.20am | 11.45am
|  | continued with issues listed in bugreport | 12.00pm | 8.00pm | Pending | out of 5 issues fixed 4(multiple file uploading is pending)
2016-05-06 | Santosh | XYGET site testing | 9.00am | 1.30pm | Pending
|  | Try to create a document for XYGET | 3.00pm | 7.45pm | Pending
2016-05-06 | Siva Rama Kannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Meeting with nithya | 10.00 AM | 10.30 AM | Completed
|  | Creating portfolio module in index page of ETS | 10.30 AM | 4.45 PM | Completed
|  | Adding hover function to particular images in portfolio page | 5.00 PM | 6.30 PM | In progress
|  | Meeting with Deepak | 6.30 PM | 8.00 PM | Completed
2016-05-06 | Velpandi | Typing Test | 9:30 | 10:30 | Completed
|  | Meeting | 10:30 | 11:30 | Completed
|  | set a sesson for my task | 11:30 | 13:30 | Completed
|  | Adding a navigation blocks for each sesson | 14:40 | 16:30 | Completed
|  | Adding a links to an buttons | 16:30 | 18:40 | Completed
|  | Meeting | 18:40 | 20:15 | Completed
2016-05-06 | Vignesh | worked in ETS slider functions | 10.00am | 1.30pm | completed
|  | attended meeting with nithya | 10.30am | 11.00am | completed
|  | worked in menu on click function in ets home page | 2.30pm | 4.00pm | completed
|  | permission | 4.00pm | 6.30pm

## 05.05.2016
Date | Name | Task | Start time | End time | Status | Comment
2016-05-05 | Akila | Typing Test | 09.40am | 10.30am | Completed
|  | Meeting with Nithya,Standup Meeting | 10:40am | 11:40am | Completed
|  | Tea Break,Continued working on Task | 11.50am | 01.00pm | Pending
|  | Meeting with Madhivanan | 01.00pm | 01.20pm | Completed
|  | Fixed issues noted by madhivanan & continued task | 01:20pm | 07.00pm | Pending | Working on
|  | Meeting with HR & Madhivanan | 07:00pm | 07:40pm | Completed
2016-05-05 | Balasubramaniam | Typing Test | 9:15AM | 10:45AM | Completed
|  | Meeting | 10:46AM | 11:30AM | Completed
|  | logo making | 11:33AM | 12:03AM | Completed
|  | set logo on the web page | 12:30 | 1:15PM | Completed
|  | allign the nav bar | 1:27PM | 2:00PM | Completed
|  | change the button color | 3:00PM | 3:30PM | Completed
|  | set the padding and morgin for this page | 3:30PM | 4:10PM | Completed
|  | form arrangements and set the page formats | 4:30PM | 6:30PM | Completed
|  | Meeting | 6:30PM | 7:30PM | Completed
2016-05-05 | Barath | Designing ETS PROFILE | 11.30AM | 6.00PM | COMPLETED | NEW DESIGN
|  | DESIGNING LETTERPAD to GTS | 6.00PM | 6.30PM | COMPLETED
2016-05-05 | Kalai | Worked in resell and fixed the issues in post ad form and detail page | 10.45 am | 1.30 pm | completed
|  | Worked in thalapakattu and traced out the menu generate issues while click and enter combobox | 2.30 pm | 8.10 pm | pending
2016-05-05 | Madhivanan | Discuss with Sastha about tasks for today | 10.30 AM | 11.00 AM | Completed
|  | Created account in Computerworld, for latest update | 11.00 AM | 11.30 AM | Completed
|  | Ets Profile content | 11.30 AM | 11.50 AM | Pending
|  | Conduct Interview to Shanmugam | 11.50 AM | 12.10 PM | Pending | Task assign for quality check(Designing Logo for Cotton House)
|  | Mail sent to Prabhu | 12.10 PM | 12.20 PM | Completed | About E-Learning issues
|  | Ets Profile Content | 12.20 PM | 1.40 PM | Pending
|  | Conduct Interview to Shanmugam | 1.40 PM | 2.15 PM | Completed
|  | Name suggestion for fixido and mobile invoice | 3.15 PM | 4.10 PM | Completed
|  | Portfolio Content preperation | 4.10 PM | 6.30 PM | Pending
|  | Meeting with Intent & Akila | 7.00 PM | 7.30 PM | Completed
|  | Discussion with Sastha and Deepak | 7.30 PM | 8.30 PM
|  | Function flow KT for thalapakattu from Vinoth through Call | 8.30 PM | 9.00 PM | Completed
|  | Daily report sheet updation | 9.00 PM | 9.30 PM | Pending
2016-05-05 | Muthu | Typing Test | 9.30. AM | 10.45 AM | Completed
|  | Thalapakattu updation previous day corrction | 10.45 AM | 12.55 PM | Pending
|  | Went to atomicka for thalapakattu demo | 2.00 PM | 7.00 PM
|  | Thalapakattu corrction | 7.00 PM | 8.45 PM | Pending
2016-05-05 | Nithya | Typing test | 9:50 | 10:30 | Completed
|  | meeting with intent about ui | 10:45 | 11:25
|  | Standup meeting,Resell responsive design issues(bug list) | 11:45 | 13:40 | In Progress
|  | Resell bug list issues,helped the intent for design issues(ui) | 15:00 | 19:10 | Completed
2016-05-05 | Ramya | attended typing test | 9.45am | 10.30am | completed
|  | started to fix issues while sending sms after admin approval for product as well as advertisement | 10.35am | 1.30am | completed
|  | attended standup meeting | 11.30am | 11.45am
|  | proceeded to fix issues listed in bugreport | 3.00pm | 7.00pm | out of 23 issues fixed 18 (5 is in progress)
2016-05-05 | Santosh | Resell Responsive testing in Validation part. | 9.30am | 1.30pm | completed
|  | Name suggestion for new site | 3.00pm | 4.00pm | completed
|  | XYGET site analyze for testing purpose | 4.15pm | 6.30pm | Pending
2016-05-05 | Siva Rama Kannan
2016-05-05 | Velpandi | Typing Test | 9:30 | 10:30AM | Completed
|  | Meeting | 10:30 | 11:30 | Completed
|  | Adding division blogs for my task | 11:30 | 13:30 | Completed
|  | Align a text for my task fonts require | 14:30 | 4:30 | Completed
|  | Design a button on my blogs | 17:00 | 18:30 | Completed
|  | Meeting | 18:30 | 19:30 | Completed
2016-05-05 | Vignesh | worked in ETS site home page for responsive in menu bar | 9.45am | 1.30pm | completed
|  | Attended meeting with nithya | 11.00am | 11.30am | completed
|  | worked in home page slider function for responsive | 2.30pm | 6.30pm | pending((having issue in slider )
|  | Attended meeting with HR | 6.30pm | 7.00pm | completed
|  | Attended meeting with madhivanan | 7.00pm | 7.30pm | completed

## 04.05.2016
Date | Name | Task | Start time | End time | Status | Comment
2016-05-04 | Akila | Typing lessons | 09.30am | 10.30am | Completed
|  | Contuinued task in fixing issues | 10.30am | 11.00am | On process
|  | Standup meeting, Meeting with Madhivanan | 11.00am | 12.10pm | Completed
|  | Contuinued designing | 12.10pm | 02.15pm | On process
|  | Contuinued designing | 03.00pm | 06.30pm | Completed
|  | Meeting with Madhivanan | 06.30pm | 07.30pm | Completed
2016-05-04 | Balasubramaniam | Typing Test | 9:30AM | 10:05 | Completed
|  | Meeting | 10:30AM | 11:30AM | Inprocess
|  | set background Images and forms | 12:00PM | 1:35PM | Completed
|  | Task:design HTML & logo arrange using CSS | 3:00PM | 4:45PM | completed
|  | set navbar and buttons | 4:45PM | 6:30PM | Completed
|  | Meeting | 6:30PM | 7:30PM | Completed
2016-05-04 | Barath | Designing FIXIDO PROFILE | 9.45 am | 6.35 pm | completed | 4 Pages Completed
2016-05-04 | Kalai | Worked in thalapakattu project and checked the condition for printing bill formats in all the scenarios(KOT & Invoice Order,Parcel & Cancel), discussed with muthu about that different bill format concept | 10.05 pm | 2.00 pm | completed
|  | Generated the menu list while press enter button in combobox, And fixed issues in cancel item | 2.30 pm | 4.30 pm | completed
|  | Started to fix issues in resell, Again Continued to trace out the problem in thalapakattu, prepared the document for changes i made today in thalapakattu | 4.45 pm | 8.10 pm | completed
2016-05-04 | Madhivanan | Daily report updation, Place change, Meeting arrangements | 10.00 AM | 11.00 AM | Completed
|  | Py-01.com mail sent to Dev | 11.00 AM | 11.30 AM | Completed
|  | Meeting conduct for intent & Akila, Siva, Vignesh | 11.40 AM | 12.10 PM | Completed | Meeting about task status
|  | Thalapakattu changes mail confirmation | 12.15 PM | 12.50PM | Pending | Content not clear
|  | ETS Profile content correction | 12.50 PM | 1.30 PM | Pending
|  | Thalapakattu Testing | 1.30 PM | 2.30 PM | Completed
|  | Name suggestion for Fixido | 3.15 PM | 3.45 PM | Completed | Not accepted
|  | ETS Profile content searching | 3.45 PM | 6.30 PM | Pending
|  | Meeting conduct for intent & Akila, Siva, Vignesh | 6.30 PM | 7.30 PM | Completed | About task and team Coordination
|  | Daily report sheet updation | 7.30 PM | 8.00 PM | Completed
2016-05-04 | Muthu | Typing Test | 10.00 AM | 10.45 AM
|  | Thalapakattu changes and printer format | 10.45 AM | 3.00 PM | Completed
|  | Went to atomicka for thalapakattu demo | 4.00 PM | 6.25 PM | Pending | Vinoth was not there.
|  | Check thalapakattu printer (Printer code not working when demo) | 6.25 PM | 2.00 AM | Completed
2016-05-04 | Nithya
Absent
2016-05-04 | Ramya
Absent
2016-05-04 | Santosh | Resell Responsive testing | 9.00am | 1.30pm | completed
|  | Resell Windows testing | 2.45pm | 4.30pm | completed
|  | oozaaoo Responsive testing | 4.35pm | 7.00pm | completed
2016-05-04 | Siva Rama Kannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Fixing issues in bug sheet of oozaaoo and Meeting with Mathi | 10.00 AM | 1.30 PM | Completed
|  | Created aboutus page in ETS and Meeting with Mathi | 2.30 PM | 7.00 PM | Completed
|  | Creating service page in ETS | 7.00 PM | 8.00 PM | In progress
2016-05-04 | Velpandi | Typing Test | 9:30 | 10:30 | Completed
|  | Meeting | 10:30 | 11:30 | Completed
|  | HTML Blogs and Pricing in INVOICE:Design a navigation bar for my task | 11:30 | 13:00 | Completed
|  | Set a Background image for my task | 13:00 | 14:00 | In Process
|  | Adding division blogs for my task | 15:00 | 18:30 | In Process
|  | Meeting | 18:30 | 7:30 | Completed
2016-05-04 | Vignesh | Worked in ETS site about us page responsive | 10.30am | 11.30pm | pending
|  | Attended meeting with madhivanan | 11.30am | 12.00pm | completed
|  | worked in ETS site home page for slider and on click | 12.00pm | 2.00pm | completed
function.
|  | Edited home page for responsive design | 3.00pm | 6.30pm | pending
|  | Attended meeting with madhivanan | 6.30pm | 7.30pm | completed

## 03.05.2016
Date | Name | Task | Start time | End time | Status | Comment
2016-05-03 | Akila | Typing Lessons, Standup Meeting | 09.20am | 10.40am | Completed
|  | Tried out designing | 10.45am | 12.30pm | Completed
|  | Project coordinator Meeting | 12.30pm | 12.40pm | Completed
|  | Started Work on task assigned | 01.00pm | 07.00pm | Pending
|  | Hr Meeting | 04.40pm | 05.00pm | Completed
2016-05-03 | Balasubramaniam | Typing Test | 09:30AM | 10:10AM | Completed
|  | prepare HTML and css | 10:15AM | 10:45AM | Completed
|  | prepare HTML links,image,Table,list,blocks | 10:45AM | 11:25AM | Completed
|  | prepare HTML forms,form elements,html input types,html attributes | 11:30AM | 12:06PM | Completed
|  | Task: design HTML & CSS login and register Page | 12:10PM | 6:30PM | Pending
2016-05-03 | Barath | Designing Correction and new Design in Xyget Web page | 10.00AM | 12.30PM | completed
|  | Designing FIXIDO PROFILE | 3.30PM | 6.00PM | completed
|  | discussion with DEEPAK | 6.00PM | 6.30PM
|  | discussion with Ram | 6.30PM | 6.45 PM
2016-05-03 | Kalai | Worked in resell and finished the issues in myprofile image and registration form | 10.30 am | 1.30 pm | completed
|  | Worked in resell and finished the issues image uploading and resizing, guided siva and ramya to fix their issues | 2.05 pm | 6.40 pm | completed
2016-05-03 | Madhivanan | Daily Report sheet Updation | 11.20 AM | 11.30 AM | Completed
|  | Meeting with Sastha & kalai, Santhosh | 11.30 AM | 11.45 AM |  | Regarding Resell Project
|  | Xyget Testing | 11.45 AM | 12.30 PM | Pending
|  | Conduct meeting with Akila & Intent | 12.30 PM | 12.40 PM |  | Task details
|  | Xyget Testing | 12.40 PM | 2.30 PM | Pending
|  | Xyget Testing | 3.30 PM | 7.00 PM | Pending | Mail sent upto completed
|  | Daily Report Sheet Updation | 7.00 PM | 8.00 PM
2016-05-03 | Muthu | Typing Test | 10.00 AM | 10.45 AM | Completed
|  | Thalapakattu remaining issue fixed | 10.45 AM | 2.00 PM | Pending
|  | Went to atomicka for thalalpakattu demo | 3.45 PM | 6.00 PM
|  | Thalapakattu item search issue fixing | 6.00 PM | 9.00 PM | Completed
2016-05-03 | Nithya | Typing test | 9:35 | 10:15 | Completed
|  | Standup meeting,etekchnoservices html conversion | 10:15 | 14:15 | In Progress
|  | etekchnoservices html conversion | 15:15 | 19:20 | Pending | Completed upto to carousel
2016-05-03 | Ramya | attended typing test and standup meeting | 9.40am | 10.20am | completed
|  | started with sms code integration after advertisement posted | 10.30am | 10.50am | completed
|  | did custom combobox functionality | 11.45am | 4.30pm | completed
|  | tried to fix issues after integrated sms code in advertisement module | 4.30pm | 5.45pm | in progress
|  | get kt from kalai about the printing concept in thalapakattu project and proceeded with that task | 5.55pm | 7.00pm | pending
2016-05-03 | Santosh | Resell testing in windows | 9.00am | 1.30pm | completed
|  | oozaaoo full testing - cycle 3 | 3.00pm | 4.30pm | completed
|  | Resell Responsive testing | 5.00pm | 7.15pm | Pending
2016-05-03 | Siva Rama Kannan | Typing test | 09.30 AM | 10.00 AM
|  | Move the oozaaoo code to git and send the report to tester | 10.00 AM | 10.30 AM | Completed
|  | Creating select box and append the html file to the same page for Thalapakattu | 10.30 AM | 3.30 PM | Completed
|  | Implementing autoscrolldown function for Thalapakattu | 3.30 PM | 6.45 PM | Completed
2016-05-03 | Velpandi | Typing Test | 9:30 | 10:30 | Completed
|  | Prepare HTML Colors,HTML CSS,HTML Links,HTML Images | 10:30 | 11:15 | Completed
|  | Prepare HTML Tables,HTML List, HTML Blocks,HTML Classes | 11:15 | 12:00 | Completed
|  | Task:Design BLOGS and PRICING in INVOICE | 12:00 | 18:30 | In Process
2016-05-03 | Vignesh | worked in ETS site respnsive design | 9.45am | 12.00pm | pending
downloaded free bootstrap template and customised it
|  | using ets code for responsive design | 12.00pm | 5.30pm | completed
|  | learned responsive and jquery function from nithya for ets | 5.30pm | 7.30pm | completed
site

## 02.05.2016
Date | Name | Task | Start time | End time | Status | Comment
2016-05-02 | Akila | Installed softwares | 12.00pm | 01.00pm | Completed
|  | KT from Nithya | 01.00pm | 02.00pm | Completed
|  | Learnt Photoshop | 03.00pm | 04.00pm | Completed
|  | HTML5 review | 04.00pm | 05.00pm | Completed
|  | Tried out designing | 05.30pm | 07.15pm | Pending
2016-05-02 | Balasubramaniam | Intent Meeting | 23:30 | 12.30 PM | Completed
|  | Prepare HTML: HTML OVERVIEW,HTML BASIC TAGS,HTML ELEMENTS, | 12:50 | 14:00 | Completed
|  | HTML ATTRIBUTES, HTML FORMATTING | 15:00 | 16:00 | Completed
|  | HTML META TAGS, HTML COMMENTS, HTML IMAGES | 4:15 PM | 18:30 | Completed
2016-05-02 | Barath | Designing Correction and new Design in Xyget Web page | 10.15 AM | 7.00PM | Pending
2016-05-02 | Kalai | Worked in thalapakattu project SMS sending code for different session(complete lunch, dinner and snacks) | 10.40 am | 1.30 pm | completed
|  | Worked in thalapakattu project SMS sending code for different session(end of the day) | 2.30 pm | 8.30 pm | completed
2016-05-02 | Madhivanan | Daily Report Sheet Updation | 10.50 AM | 11.10 AM | Pending
|  | Thalapakattu Testing | 11.10 AM | 12.50 PM | Pending | Partially Completed
|  | Globalen Solutions Testing | 12.50 PM | 2.30 PM | Pending
|  | Globalen Solutions Testing | 3.30 PM | 6.15 PM | Completed
|  | Meeting with Intent & Akila | 6.20 PM | 7.00 PM | Completed
|  | Wellocity Testing | 7.10 PM | 8.00 PM | Completed
2016-05-02 | Muthu | System arrangement | 9.30 AM | 10.20 AM | Completed
|  | Thalapakattu Keypressing issue | 10.20 AM | 1.30 PM | Pending
|  | Thalapakattu Demo to vinoth at atomicka office | 3.00 PM | 5.30 PM | Completed
|  | Thalapakattu new changes | 5.30 PM | 8.30 PM | Pending
2016-05-02 | Nithya | Typing test | 10:00 | 10:40 | Completed
|  | Standup meeting,Resell bug report design corrections | 10:45 | 14:00 | In Progress
|  | Resell design issues and chat design issue in chrome | 15:00 | 20:00 | Completed
2016-05-02 | Ramya | atteded typing test and statndup meeting | 10.10am | 11.20am | completed
|  | fixed wct issues | 11.30am | 1.30pm | completed
|  | did some minor corrections and proceeded with xyget sms code integration after product was posted and after admin approval for products | 3.20pm, | 8.00pm | completed
2016-05-02 | Santosh | Resell testing | 9.30am | 6.30pm | Pending
2016-05-02 | Siva Rama Kannan | Typing test | 9.30 AM | 10.00 AM
|  | Meeting with sastha | 10.00 AM | 11.00AM
|  | Fixing issues in bug sheet of oozaaoo | 11.15 AM | 7.00 PM | Completed
2016-05-02 | Velpandi | Intent Meeting | 23:30 | 12.30 PM | Completed
|  | Prepare HTML: HTML OVERVIEW,HTML BASIC TAGS,HTML ELEMENTS, | 12:50 | 14:00 | Completed
|  | HTML ATTRIBUTES, HTML FORMATTING | 15:00 | 16:00 | Completed
|  | HTML META TAGS, HTML COMMENTS, HTML IMAGES | 16:15 | 18:30 | Completed
2016-05-02 | Vignesh | Learned how to add bootstrap carousal | 10.00am | 12.00pm | completed
|  | leraned two-column blog layout | 12.00pm | 3.30pm | completed
|  | learned bootstrap grids jumbotron | 3.30pm | 7.00pm | completed