## 11.05.2016
Date | Name | Task | Start time | End time | Status | Comment
2016-05-11 | Akila | Typing lesson | 10.00am | 10.45am | Completed
|  | Started review on Bootstrap documentation | 11.00am | 01.45pm | Pending
|  | Tried out some examples in bootstrap | 3.00pm | 07.10pm | Completed
2016-05-11 | Balasubramaniam | Typing Test | 9:30AM | 10:30AM | Completed
|  | some currections for the page | 10:45AM | 11:10AM | Completed
|  | study css | 11:15AM | 12:00PM | Completed
|  | xyget work | 12:30PM | 5:30PM | Completed
|  | xyget work | 5:45PM | 7:15PM | Completed
2016-05-11 | Barath | LOGO DESIGN FOR RICSCO | 10.00Am | 4.00PM
|  | FB POST FOR FRESHERS | 4.00PM
2016-05-11 | Kalai | Fixed issues in post ad form video upload validation and logical issues | 11.00 am | 12.15 pm | completed
|  | Discussed the resell updation with prabhu on phone call and shared about it with sastha | 12.15 pm | 2.00 pm | completed
|  | Analyzed the issues except chat and send the timeline to sastha | 3.00 pm | 3.40 pm | completed
|  | Fixed issues in google banner module and also from bug report which is given by santhosh, Search the document to create webmail in exobytes cpanel for creating resell email account | 3.40 pm | 6.45 pm | pending
2016-05-11 | Madhivanan | Typing Test | 10.30 AM | 10.50 AM | Completed
|  | Xyget Testing | 10.50 AM | 11.40 AM | Pending
|  | Daily Report sheet updation | 11.40 AM | 12.10 PM | Pending
|  | Meeting with Sastha about projects status | 12.10 PM | 12.40 PM | Pending
|  | Xyget Testing | 12.40 PM | 1.45 PM | Pending
|  | Mail sent to Mr. Shunmuga about thalapakattu status | 1.45 PM | 2.15 PM | Completed
|  | Xyget Testing | 3.30 PM | 4.30 PM | Completed
|  | wellocity testing | 4.30 PM | 8.00 PM | Completed
|  | Daily Report sheet updation | 8.00 PM | 8.30 PM | Completed
2016-05-11 | Muthu | Typing Test | 10.00 AM | 10.45 AM | Completed
|  | Thalapakattu admin part analyzing | 10.45 AM | 11.30AM | Completed | Error occurred
|  | Correct Thalapakattu admin side code | 11.30 AM | 1.30 PM | Pending
|  | Correct Thalapakattu admin side code | 2.45 PM | 7.45 PM | Pending
2016-05-11 | Nithya | Typing test | 9:50 | 10:30 | Completed
|  | Stand up meeting,clarified the doubts for akila and verified her code,helped vignesh for design issues,GT html design | 10:30 | 13:45 | Pending | GT is in process
|  | GT html design,helped siva and vignesh,wellocity popup issues | 15:00 | 19:00 | Pending | GT is in process
2016-05-11 | Ramya | attended typing test | 10.05am | 10.30am
|  | fixed issues inbug report | 10.35am | 11.05am | completed
|  | attended standup meeting | 11.10am | 11.20am
|  | procceded with the issues listed by madhivanan in bugreport | 11.20am | 7.10pm | completed
2016-05-11 | Santosh | XYGET document with changes | 9.15am | 4.40pm | completed
|  | Resell testing cycle 2 | 5.15pm | 6.00pm | Pending
|  | wellocity testing for one issue | 6.00pm | 6.30pm | completed
|  | Resell testing cycle 2 | 6.30pm | 7.00pm | Pending
2016-05-11 | Siva Rama Kannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Implemened md5 option in login module for password field | 10.00 AM | 11.00 AM | Completed
|  | Implemented form validation in contactusform of ETS | 11.00 AM | 1.45 PM | Completed
|  | Implemented Mail sending function in contactusform of ETS | 2.45 PM | 6.00 PM | Completed
|  | Implenting ajax calling funtion with jquery | 6.00 PM | 6.30 PM | In progress
2016-05-11 | Velpandi | Typing Test | 9:30 | 10.30 AM | Completed
|  | Study the CSS | 10:30 | 12:00 | Completed
|  | Set the payments parts for pricing in invoice | 12:00 | 13:50 | Completed
|  | Set the freeplan content in pricing in invoice | 15:00 | 16:30 | Completed
|  | Set the footer part for Pricing in invoice | 16:30 | 18:30 | Completed
2016-05-11 | Vignesh | worked in ets site slider function for responsive | 10.00am | 1.00pm | completed
|  | worked on issues in home page | 1.00pm | 2.00pm | completed
|  | worked in about us page responsive using media query | 3.00pm | 7.00pm | completed
|  | Have to work on scroll function in ets site |  |  | pending

## 10.05.2016
Date | Name | Task | Start time | End time | Status | Comment
2016-05-10 | Akila | Typing lessons | 09.55am | 10.55am | Completed
|  | Task completion | 10.56am | 12.40pm | Pending
|  | Meeting with sastha | 12.40pm | 01.40pm | Completed
|  | Working on Task | 03.00pm | 06.30pm | Completed
|  | Meeting with HR | 06.30pm | 07.00pm | Completed
|  | Task completion | 07.00pm | 08.40pm | Completed
2016-05-10 | Balasubramaniam | Typing Test | 9:30AM | 10:30AM | Completed
|  | form creation | 10:45AM | 11:30AM | Completed
|  | 2nd task completed | 11:30AM | 12:15PM | Completed
|  | Meeting | 12:20PM | 1:50PM | Completed
|  | study to html and css | 3:10PM | 6:00PM | Inprocess
|  | change some currections for the tasks | 6:10 | 7:10PM | Completed
2016-05-10 | Barath | DESIGNING ETS PORTFOLLIO | 10.00Am | 7.29PM | completed
|  | Designing Correction on ETS WEBSITE | 11.00Am | 1.30PM | completed
2016-05-10 | Kalai | Fixed issues in resell advertisement own and google ads in all pages | 11.10 am | 1.45 pm | completed
|  | Fixed issues in resell from bug report which is given by santhosh, Fixed the issues in detail page embedded video display | 2.45 pm | 6.30 pm | pending
|  | General Meeting with HR and our team, discussed python and django basics with siva, helped to ramya to fix issues in XYGET, Moved the XYGET updated code in server, continued to fixed the issues in detail page embedded video display | 6.45 pm | 8.10 pm | completed
2016-05-10 | Madhivanan | Thalapakattu Discussion with Sastha & Muthu | 11.15 AM | 11.30 AM | Completed
|  | Xyget Testing | 11.30 AM | 12.30 PM | Pending
|  | Mail sent to Vinoth regarding Thalapakattu | 12.30 PM | 12.40 PM | Completed
|  | Xyget Testing | 12.40 PM | 2.00 PM | Pending
|  | Typing test | 2.30PM | 3.00PM | Completed
|  | Daily Report Sheet Updation | 3.00 PM | 3.40 PM | Completed
|  | Discussion with Deepak about Xyget Documentation | 3.40 PM | 4.30 PM | Completed
|  | Xyget Testing | 4.30 PM | 8.00 PM | Pending
|  | Daily Report Sheet Updation | 8.00 PM | 8.20 PM | Completed
2016-05-10 | Muthu | Typing Test | 10.00 AM | 10.30 AM | Completed
|  | Analysing and Make flow structor thalapakattu restaurent moudle | 10.30 AM | 2.00 PM | Pending
|  | Make DB structor for thalapakattu restaurant module | 3.00 PM | 4.30 PM | Completed
|  | Went to atomicka for meeting about thalapakattu new restaurant module | 5.10 PM | 8.30 PM
2016-05-10 | Nithya | Typing test | 10:00 | 10:40 | Completed
|  | Standup meeting,ETS responsive design | 10:40 | 14:00 | In Progress
|  | ETS responsive design,fixed resell design issues | 15:15 | 20:40 | Completed
2016-05-10 | Ramya | atteded typing test | 10.10am | 10.30am
|  | started to fix issues listed in the bugreport | 10.15am | 12.10pm | completed
|  | attended standup meeting | 12.10pm | 12.30pm
|  | started to fix remaining issues listed in the bugreport | 12.30pm | 5.30pm | completed
|  | proceeded with multiple image uploading | 5.30pm | 6.30pm
|  | attended a meeting with hr and team | 6.30pm | 7.25pm
|  | procceded with the issues listed by madhivanan | 7.30pm | 8.30pm | completed(multiple image uploading is in progress)
2016-05-10 | Santosh | Front end completed for XYGET document | 9.00am | 5.00pm | completed
|  | Starting new document with some changes in XYGET. | 5.00pm | 7.30pm | Pending
2016-05-10 | Siva Rama Kannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Fixing resposive issues in porfolio page of ETS | 10.00 AM | 10.30 AM | Completed
|  | Meeting with sastha and deepak | 10.30 AM | 1.40 PM | Completed
|  | Implementing Admin Login module for Thalapakattu | 2.40 PM | 4.00 PM | Completed
|  | Implementing textbox validation like accepts only alphabet,number | 4.00 PM | 4.45 PM | Completed
|  | Discuss with kalai about python and django | 5.00 PM | 6.30 PM | Completed
2016-05-10 | Velpandi | Typing Test | 9:30 | 10:30
|  | set the header part for my second task | 10:30 | 12:20
|  | Meeting | 12:20 | 13:50
|  | Set the background image for my second task | 15:00 | 16:30
|  | Study HTML | 16:30 | 18:30
2016-05-10 | Vignesh | worked in ets site menu hide/show function using jquery | 9.45am | 1.00pm | completed
|  | attended meeting with Sastha sir | 1.00pm | 2.15pm
|  | worked in service page for alignment and responsive | 3.15pm | 6.30pm | pending

## 09.05.2016
Date | Name | Task | Start time | End time | Status | Comment
2016-05-09 | Akila | Typing test | 09.50am | 10.15am | Completed
|  | Meeting with Nithya | 10.15am | 10.50am | Completed
|  | Standup Meeting | 11.20am | 11.30am | Completed
|  | Working on Task | 10.50am | 01.55pm | Pending
|  | Working on Task | 3.00pm | 07.00pm | Pending
|  | KT from Deepak | 07.00pm | 08.44pm | Completed
2016-05-09 | Balasubramaniam | Typing Test | 9:2AM | 10:00AM | Completed
|  | Meeting | 10:15AM | 10:55 | Completed
|  | remove scroller for the webpage | 11:30AM | 12:15PM | Completed
|  | start new task | 12:30 | 1:30PM | Inprocess
|  | set header page | 3:00PM | 4:00PM | Completed
|  | set background image | 4:00PM | 4:50PM | Completed
|  | form creation | 05:15PM | 6:00PM | Completed
|  | gradient botton creation | 6:00PM | 6:30PM | Completed
2016-05-09 | Barath
Absent
2016-05-09 | Kalai | Fixed issues in resell from bug report which is given by santhosh | 11.00 am | 1.45 pm | completed
|  | Continued to fix the resell logical issues in admin | 2.45 pm | 4.00 pm | completed
|  | Traced and tried to fix the issues on chat history appending process for each and every product in both sender and receiver side | 4.15 pm | 7.40 pm | pending
2016-05-09 | Madhivanan | Daily Report Sheet Updation | 9.35 AM | 9.50 AM
|  | Typing test | 9.50 AM | 10.20 AM | Completed
|  | Thalapakattu Testing | 10.20 AM | 12.15 PM | Pending
|  | Xyget Testing | 12.15 PM | 12.45 PM | Pending
|  | Discussion with Sastha & Deepak | 12.45 PM | 1.15 PM |  | About Thalapakattu & Mobile app
|  | Xyget Testing | 1.15 PM | 2.00 PM | Pending
|  | Xyget Testing | 3.00 PM | 6.00 PM | Pending | Data feed
|  | Wellocity Correction | 6.00 PM | 6.40 PM | Completed
|  | Thalapakattu Testing | 6.40 PM | 8.00 PM | Pending
|  | Daily Report Sheet Updation | 8.00 PM | 8.30 PM | Completed
2016-05-09 | Muthu | Typing test | 10.00 AM | 10.30 AM | Completed
|  | Thalapakattu-Restaurant-Item add issue | 10.30 AM | 1.30 PM | Pending
|  | Thalapakattu-Restaurant-Item add issue and Cancel item issue | 2.30 PM | 8.00 PM | Pending | If I fix add issue, cancel issue is arise, & vice versa
|  | Thalapakattu-Restaurant-Item cancel issue and add item issue | 9.30 PM | 1.00 AM | Pending | If I fix add issue, cancel issue is arise, & vice versa
2016-05-09 | Nithya | Typing test | 9:50 | 10:10 | Completed
|  | meeting with intent about ui | 10:15 | 10:55
|  | Standup meeting,portfolio html design(ETS) | 11:00 | 13:50 | Completed
|  | Home page alignment and contact us part design | 15:00 | 19:30 | responsive is pending
2016-05-09 | Ramya | atteded typing test | 10.00am | 10.35am
|  | fixed issue on saving category based items while adding product | 10.40am | 11.20am | completed
|  | attended standup meeting | 11.25am | 11.45am
|  | fixed issues on related search based on products | 12.00pm | 1.30am | completed
|  | fixed some issues when city based searching for both products and advertisement | 3.05pm | 5.15pm | completed
|  | multiple image uploading(pending process) | 5.20pm | 6.00pm
|  | fixed wct issues | 6.10pm | 8.00pm | completed
2016-05-09 | Santosh
Absent
2016-05-09 | Siva Rama Kannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Meeting with nithya | 10.00 AM | 10.30 AM | Completed
|  | Creating contactus section in index page of ETS | 10.30 AM | 1.30 PM | In progress
|  | Fixing resposive issues in porfolio page of ETS | 1.30 PM | 7.00 PM | Completed
2016-05-09 | Velpandi | Typing Test | 9:30 | 10:30 | Completed
|  | Meeting | 10:30 | 11:30 | Completed
|  | Set a atricle block for my task | 11:30 | 14:00 | Completed
|  | Set a Footer part for my tasks | 15:00 | 18:00 | Completed
2016-05-09 | Vignesh | Attended meeting with nithya | 10.30am | 11.00am | completed
|  | worked in ETS site for responsiveness | 9.45am | 3.30pm | pending( slider responsive is not coming)
|  | worked in about us page responsive | 3.30pm | 7.00pm | pending (issue in text responsive since text
are collapsed during responsive)
|  | attended meeting with deepak sir | 7.00pm | 8.45pm

## 07.05.2016
Date | Name | Task | Start time | End time | Status | Comment
2016-05-07 | Akila | Typing lessons | 09.40am | 10.20am | Completed
|  | Meeting with Nithya | 10.30am | 11.15am | Completed | She insisted me to design again using float property for the task
|  | Continued task again to make changes in design as per basic design structure | 11.30am | 01.45pm | Pending
|  | Continued task again to make changes in design as per basic design structure | 02.50pm | 06.15pm | Pending
2016-05-07 | Balasubramaniam | Typing Test | 9:15AM | 10:50AM | Completed
|  | Meeting | 10:30AM | 11:30AM | Completed
|  | linking to the all buttions and links in html to css | 11:30AM | 12:10AM | Completed
|  | My Laptop taking by HR | 12:15PM | 3:00AM | Completed
|  | currections for the background image | 3:15PM | 4:00PM | Completed
|  | form alignments | 04:15PM | 4:45PM | Completed
2016-05-07 | Barath
Not Received
2016-05-07 | Kalai
Absent
2016-05-07 | Madhivanan | Daily sheet report updation | 10.45 AM | 11.00 AM
|  | Thalapakattu Testing | 11.00 AM | 3.25 PM | Completed
|  | Name searched for Fixido & invoice generator | 4.30 PM | 5.30 PM
|  | Discussion with Deepak & Sastha | 7.00 PM | 8.15 PM |  | about Thalapakattu Issues
2016-05-07 | Muthu | Preparing thalapakattu code for demo and fixing some changes as testing | 11.00 AM | 1.30 PM | Complete
|  | went to atomicka for demo | 2.00 PM | 7.00 PM | Complete | They given 3 changes in thalapakattu
|  | meeting with deepaka,sastha,madhi | 7.00 PM | 8.15 PM | Complete
2016-05-07 | Nithya | Typing test | 9:50 | 10:20 | Completed
|  | meeting with intent about ui | 10:25 | 11:10
|  | Standup meeting,portfolio html design(ETS) | 11:10 | 13:45 | In progress
|  | Helped siva for home page design | 15:00 | 6:30
2016-05-07 | Ramya | attended typing test | 10.05am | 10.45am
|  | started to work on uploading multiple images for products | 10.55am | 1.30pm | Pending | partially completed(while storing ll get some difficulties)
|  | fixed some issues registration form validation | 3.00pm | 3.30pm | completed
|  | searched for multiple image uploading | 3.40pm | 4.00pm
2016-05-07 | Santosh
Not Received
2016-05-07 | Siva Rama Kannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Meeting with nithya | 10.00 AM | 10.30 AM | Completed
|  | Creating our module in index page of ETS and Implementing slider option in this page | 10.30 AM | 6.30 PM | Completed
2016-05-07 | Velpandi | Typing Test | 9:30 | 10:30 | Completed
|  | Meeting | 10:30 | 11:30 | Completed
|  | My laptop used by interview persons | 11:30 | 15:00 | Completed
|  | Set the article sesson for my task | 15:00 | 17:00 | Completed
|  | Study in CSS | 17:00 | 6:00 | Completed
2016-05-07 | Vignesh
using media queries
|  | attended meeting with nithya | 10.30am | 11.00am | completed
|  | worked on issue in scroll function in home page | 12.00pm | 1.30pm | completed
|  | worked in ets about us page | 2.30pm | 7.00pm | pending

## 06.05.2016
Date | Name | Task | Start time | End time | Status | Comment
2016-05-06 | Akila | Typing test | 09:35am | 10.15am | Completed
|  | Meeting with Nithya,Standup meeting | 10.30am | 11.40am | Completed
|  | Continued working on task assigned | 11.40am | 01.55pm | Pending
|  | KT from Deepak | 02.50pm | 03.50pm | Completed
|  | Continued working on task assigned | 04.00pm | 07.00pm | Pending | Facing design issue in structure, rectifying again from starting
|  | KT from Deepak | 07.00pm | 08.15pm
2016-05-06 | Balasubramaniam | Typing Test | 9:15AM | 10:45AM
|  | Meeting | 10:46AM | 11:30AM
|  | logo making | 11:33AM | 12:03AM
|  | set logo on the web page | 12:30PM | 1:15PM
|  | set the padding and morgin for this page | 1:30PM | 2:00PM
|  | form arrangements and set the page formats | 3:00PM | 4:30PM
|  | study CSS | 4:45PM | 6:30PM
|  | Meeting | 6:45PM | 8:15PM
2016-05-06 | Barath | Designing ETS PROFILE | 10.00Am | 1.45PM | COMPLETED
|  | DESIGNING ETS PORTFOLLIO | 2.40PM | 7.40PM | Pending
2016-05-06 | Kalai | Fixed issues in resell chat history appending process for each and every product | 11.00 am | 2.00 pm | completed
|  | Fixed image cropping issues in post ad form using server side code, moved the updated resell code in server | 3.05 pm | 6.00 pm | completed
|  | tried to fetch the chat history throughout all pages | 6.00 pm | 8.05 pm | pending
2016-05-06 | Madhivanan | Daily sheet report updation | 10.30 AM | 10.50 AM
|  | Typing skills | 10.50 AM | 11.20 AM | Completed
|  | Standup Meeting | 11.20 AM | 11.45 AM | Completed
|  | Mail sent to Vinoth | 11.45 AM | 12.40 PM | Completed | Function flow confirmation for thalapakattu
|  | Search for Roadmap concept | 12.45 PM | 1.00 PM | Completed
|  | ICICI Bank account open | 1.00 PM | 1.45 PM | Completed | About Roadmap and ETS site content
|  | Discussion with Deepak | 1.45 PM | 2.30 PM | Completed
|  | Multi page profile for ETS | 3.15 AM | 3.40 PM | Pending
|  | Name Suggestion for Invoice generator | 3.40 PM | 4.10 PM | Completed
|  | Multi page profile content searching | 4.20 PM | 5.30 PM | Completed | Mail sent to Devi Mam
|  | E-learning and Resell requirement & issues collected | 5.45 PM | 7.00 PM | Completed | Mail sent to Prabhu
|  | Daily sheet report updation | 7.10 PM | 7.35 PM | Pending
|  | Meeting with Deepak | 8.15 PM | 9.30 PM | Completed | About Fixido function flow phase 1
2016-05-06 | Muthu | typing test | 9.30 AM | 10.00AM | Completed
|  | Thalapakattu restaurant flow code analysing | 10.00 AM | 2.00 AM | Completed
|  | Workout restaurant flow as per mail | 3.00 PM | 0:00 | Completed
2016-05-06 | Nithya | meeting with intent about ui | 10:20 | 11:30
|  | Standup meeting,portfolio html design(ETS) | 11:30 | 14:00 | In Progress
|  | Helped siva for ets home page html design,Removed gl animation in Atomicka desktop,portfolio html design | 15:15 | 19:50 | Pop up part is pending
2016-05-06 | Ramya | attended typing test | 10.05am | 10.45am
|  | proceeded to fix issues listed in bugreport | 10.50am | 11.20am | completed
|  | attended standup meeting | 11.20am | 11.45am
|  | continued with issues listed in bugreport | 12.00pm | 8.00pm | Pending | out of 5 issues fixed 4(multiple file uploading is pending)
2016-05-06 | Santosh | XYGET site testing | 9.00am | 1.30pm | Pending
|  | Try to create a document for XYGET | 3.00pm | 7.45pm | Pending
2016-05-06 | Siva Rama Kannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Meeting with nithya | 10.00 AM | 10.30 AM | Completed
|  | Creating portfolio module in index page of ETS | 10.30 AM | 4.45 PM | Completed
|  | Adding hover function to particular images in portfolio page | 5.00 PM | 6.30 PM | In progress
|  | Meeting with Deepak | 6.30 PM | 8.00 PM | Completed
2016-05-06 | Velpandi | Typing Test | 9:30 | 10:30 | Completed
|  | Meeting | 10:30 | 11:30 | Completed
|  | set a sesson for my task | 11:30 | 13:30 | Completed
|  | Adding a navigation blocks for each sesson | 14:40 | 16:30 | Completed
|  | Adding a links to an buttons | 16:30 | 18:40 | Completed
|  | Meeting | 18:40 | 20:15 | Completed
2016-05-06 | Vignesh | worked in ETS slider functions | 10.00am | 1.30pm | completed
|  | attended meeting with nithya | 10.30am | 11.00am | completed
|  | worked in menu on click function in ets home page | 2.30pm | 4.00pm | completed
|  | permission | 4.00pm | 6.30pm

## 05.05.2016
Date | Name | Task | Start time | End time | Status | Comment
2016-05-05 | Akila | Typing Test | 09.40am | 10.30am | Completed
|  | Meeting with Nithya,Standup Meeting | 10:40am | 11:40am | Completed
|  | Tea Break,Continued working on Task | 11.50am | 01.00pm | Pending
|  | Meeting with Madhivanan | 01.00pm | 01.20pm | Completed
|  | Fixed issues noted by madhivanan & continued task | 01:20pm | 07.00pm | Pending | Working on
|  | Meeting with HR & Madhivanan | 07:00pm | 07:40pm | Completed
2016-05-05 | Balasubramaniam | Typing Test | 9:15AM | 10:45AM | Completed
|  | Meeting | 10:46AM | 11:30AM | Completed
|  | logo making | 11:33AM | 12:03AM | Completed
|  | set logo on the web page | 12:30 | 1:15PM | Completed
|  | allign the nav bar | 1:27PM | 2:00PM | Completed
|  | change the button color | 3:00PM | 3:30PM | Completed
|  | set the padding and morgin for this page | 3:30PM | 4:10PM | Completed
|  | form arrangements and set the page formats | 4:30PM | 6:30PM | Completed
|  | Meeting | 6:30PM | 7:30PM | Completed
2016-05-05 | Barath | Designing ETS PROFILE | 11.30AM | 6.00PM | COMPLETED | NEW DESIGN
|  | DESIGNING LETTERPAD to GTS | 6.00PM | 6.30PM | COMPLETED
2016-05-05 | Kalai | Worked in resell and fixed the issues in post ad form and detail page | 10.45 am | 1.30 pm | completed
|  | Worked in thalapakattu and traced out the menu generate issues while click and enter combobox | 2.30 pm | 8.10 pm | pending
2016-05-05 | Madhivanan | Discuss with Sastha about tasks for today | 10.30 AM | 11.00 AM | Completed
|  | Created account in Computerworld, for latest update | 11.00 AM | 11.30 AM | Completed
|  | Ets Profile content | 11.30 AM | 11.50 AM | Pending
|  | Conduct Interview to Shanmugam | 11.50 AM | 12.10 PM | Pending | Task assign for quality check(Designing Logo for Cotton House)
|  | Mail sent to Prabhu | 12.10 PM | 12.20 PM | Completed | About E-Learning issues
|  | Ets Profile Content | 12.20 PM | 1.40 PM | Pending
|  | Conduct Interview to Shanmugam | 1.40 PM | 2.15 PM | Completed
|  | Name suggestion for fixido and mobile invoice | 3.15 PM | 4.10 PM | Completed
|  | Portfolio Content preperation | 4.10 PM | 6.30 PM | Pending
|  | Meeting with Intent & Akila | 7.00 PM | 7.30 PM | Completed
|  | Discussion with Sastha and Deepak | 7.30 PM | 8.30 PM
|  | Function flow KT for thalapakattu from Vinoth through Call | 8.30 PM | 9.00 PM | Completed
|  | Daily report sheet updation | 9.00 PM | 9.30 PM | Pending
2016-05-05 | Muthu | Typing Test | 9.30. AM | 10.45 AM | Completed
|  | Thalapakattu updation previous day corrction | 10.45 AM | 12.55 PM | Pending
|  | Went to atomicka for thalapakattu demo | 2.00 PM | 7.00 PM
|  | Thalapakattu corrction | 7.00 PM | 8.45 PM | Pending
2016-05-05 | Nithya | Typing test | 9:50 | 10:30 | Completed
|  | meeting with intent about ui | 10:45 | 11:25
|  | Standup meeting,Resell responsive design issues(bug list) | 11:45 | 13:40 | In Progress
|  | Resell bug list issues,helped the intent for design issues(ui) | 15:00 | 19:10 | Completed
2016-05-05 | Ramya | attended typing test | 9.45am | 10.30am | completed
|  | started to fix issues while sending sms after admin approval for product as well as advertisement | 10.35am | 1.30am | completed
|  | attended standup meeting | 11.30am | 11.45am
|  | proceeded to fix issues listed in bugreport | 3.00pm | 7.00pm | out of 23 issues fixed 18 (5 is in progress)
2016-05-05 | Santosh | Resell Responsive testing in Validation part. | 9.30am | 1.30pm | completed
|  | Name suggestion for new site | 3.00pm | 4.00pm | completed
|  | XYGET site analyze for testing purpose | 4.15pm | 6.30pm | Pending
2016-05-05 | Siva Rama Kannan
2016-05-05 | Velpandi | Typing Test | 9:30 | 10:30AM | Completed
|  | Meeting | 10:30 | 11:30 | Completed
|  | Adding division blogs for my task | 11:30 | 13:30 | Completed
|  | Align a text for my task fonts require | 14:30 | 4:30 | Completed
|  | Design a button on my blogs | 17:00 | 18:30 | Completed
|  | Meeting | 18:30 | 19:30 | Completed
2016-05-05 | Vignesh | worked in ETS site home page for responsive in menu bar | 9.45am | 1.30pm | completed
|  | Attended meeting with nithya | 11.00am | 11.30am | completed
|  | worked in home page slider function for responsive | 2.30pm | 6.30pm | pending((having issue in slider )
|  | Attended meeting with HR | 6.30pm | 7.00pm | completed
|  | Attended meeting with madhivanan | 7.00pm | 7.30pm | completed

## 04.05.2016
Date | Name | Task | Start time | End time | Status | Comment
2016-05-04 | Akila | Typing lessons | 09.30am | 10.30am | Completed
|  | Contuinued task in fixing issues | 10.30am | 11.00am | On process
|  | Standup meeting, Meeting with Madhivanan | 11.00am | 12.10pm | Completed
|  | Contuinued designing | 12.10pm | 02.15pm | On process
|  | Contuinued designing | 03.00pm | 06.30pm | Completed
|  | Meeting with Madhivanan | 06.30pm | 07.30pm | Completed
2016-05-04 | Balasubramaniam | Typing Test | 9:30AM | 10:05 | Completed
|  | Meeting | 10:30AM | 11:30AM | Inprocess
|  | set background Images and forms | 12:00PM | 1:35PM | Completed
|  | Task:design HTML & logo arrange using CSS | 3:00PM | 4:45PM | completed
|  | set navbar and buttons | 4:45PM | 6:30PM | Completed
|  | Meeting | 6:30PM | 7:30PM | Completed
2016-05-04 | Barath | Designing FIXIDO PROFILE | 9.45 am | 6.35 pm | completed | 4 Pages Completed
2016-05-04 | Kalai | Worked in thalapakattu project and checked the condition for printing bill formats in all the scenarios(KOT & Invoice Order,Parcel & Cancel), discussed with muthu about that different bill format concept | 10.05 pm | 2.00 pm | completed
|  | Generated the menu list while press enter button in combobox, And fixed issues in cancel item | 2.30 pm | 4.30 pm | completed
|  | Started to fix issues in resell, Again Continued to trace out the problem in thalapakattu, prepared the document for changes i made today in thalapakattu | 4.45 pm | 8.10 pm | completed
2016-05-04 | Madhivanan | Daily report updation, Place change, Meeting arrangements | 10.00 AM | 11.00 AM | Completed
|  | Py-01.com mail sent to Dev | 11.00 AM | 11.30 AM | Completed
|  | Meeting conduct for intent & Akila, Siva, Vignesh | 11.40 AM | 12.10 PM | Completed | Meeting about task status
|  | Thalapakattu changes mail confirmation | 12.15 PM | 12.50PM | Pending | Content not clear
|  | ETS Profile content correction | 12.50 PM | 1.30 PM | Pending
|  | Thalapakattu Testing | 1.30 PM | 2.30 PM | Completed
|  | Name suggestion for Fixido | 3.15 PM | 3.45 PM | Completed | Not accepted
|  | ETS Profile content searching | 3.45 PM | 6.30 PM | Pending
|  | Meeting conduct for intent & Akila, Siva, Vignesh | 6.30 PM | 7.30 PM | Completed | About task and team Coordination
|  | Daily report sheet updation | 7.30 PM | 8.00 PM | Completed
2016-05-04 | Muthu | Typing Test | 10.00 AM | 10.45 AM
|  | Thalapakattu changes and printer format | 10.45 AM | 3.00 PM | Completed
|  | Went to atomicka for thalapakattu demo | 4.00 PM | 6.25 PM | Pending | Vinoth was not there.
|  | Check thalapakattu printer (Printer code not working when demo) | 6.25 PM | 2.00 AM | Completed
2016-05-04 | Nithya
Absent
2016-05-04 | Ramya
Absent
2016-05-04 | Santosh | Resell Responsive testing | 9.00am | 1.30pm | completed
|  | Resell Windows testing | 2.45pm | 4.30pm | completed
|  | oozaaoo Responsive testing | 4.35pm | 7.00pm | completed
2016-05-04 | Siva Rama Kannan | Typing test | 9.30 AM | 10.00 AM | Completed
|  | Fixing issues in bug sheet of oozaaoo and Meeting with Mathi | 10.00 AM | 1.30 PM | Completed
|  | Created aboutus page in ETS and Meeting with Mathi | 2.30 PM | 7.00 PM | Completed
|  | Creating service page in ETS | 7.00 PM | 8.00 PM | In progress
2016-05-04 | Velpandi | Typing Test | 9:30 | 10:30 | Completed
|  | Meeting | 10:30 | 11:30 | Completed
|  | HTML Blogs and Pricing in INVOICE:Design a navigation bar for my task | 11:30 | 13:00 | Completed
|  | Set a Background image for my task | 13:00 | 14:00 | In Process
|  | Adding division blogs for my task | 15:00 | 18:30 | In Process
|  | Meeting | 18:30 | 7:30 | Completed
2016-05-04 | Vignesh | Worked in ETS site about us page responsive | 10.30am | 11.30pm | pending
|  | Attended meeting with madhivanan | 11.30am | 12.00pm | completed
|  | worked in ETS site home page for slider and on click | 12.00pm | 2.00pm | completed
function.
|  | Edited home page for responsive design | 3.00pm | 6.30pm | pending
|  | Attended meeting with madhivanan | 6.30pm | 7.30pm | completed

## 03.05.2016
Date | Name | Task | Start time | End time | Status | Comment
2016-05-03 | Akila | Typing Lessons, Standup Meeting | 09.20am | 10.40am | Completed
|  | Tried out designing | 10.45am | 12.30pm | Completed
|  | Project coordinator Meeting | 12.30pm | 12.40pm | Completed
|  | Started Work on task assigned | 01.00pm | 07.00pm | Pending
|  | Hr Meeting | 04.40pm | 05.00pm | Completed
2016-05-03 | Balasubramaniam | Typing Test | 09:30AM | 10:10AM | Completed
|  | prepare HTML and css | 10:15AM | 10:45AM | Completed
|  | prepare HTML links,image,Table,list,blocks | 10:45AM | 11:25AM | Completed
|  | prepare HTML forms,form elements,html input types,html attributes | 11:30AM | 12:06PM | Completed
|  | Task: design HTML & CSS login and register Page | 12:10PM | 6:30PM | Pending
2016-05-03 | Barath | Designing Correction and new Design in Xyget Web page | 10.00AM | 12.30PM | completed
|  | Designing FIXIDO PROFILE | 3.30PM | 6.00PM | completed
|  | discussion with DEEPAK | 6.00PM | 6.30PM
|  | discussion with Ram | 6.30PM | 6.45 PM
2016-05-03 | Kalai | Worked in resell and finished the issues in myprofile image and registration form | 10.30 am | 1.30 pm | completed
|  | Worked in resell and finished the issues image uploading and resizing, guided siva and ramya to fix their issues | 2.05 pm | 6.40 pm | completed
2016-05-03 | Madhivanan | Daily Report sheet Updation | 11.20 AM | 11.30 AM | Completed
|  | Meeting with Sastha & kalai, Santhosh | 11.30 AM | 11.45 AM |  | Regarding Resell Project
|  | Xyget Testing | 11.45 AM | 12.30 PM | Pending
|  | Conduct meeting with Akila & Intent | 12.30 PM | 12.40 PM |  | Task details
|  | Xyget Testing | 12.40 PM | 2.30 PM | Pending
|  | Xyget Testing | 3.30 PM | 7.00 PM | Pending | Mail sent upto completed
|  | Daily Report Sheet Updation | 7.00 PM | 8.00 PM
2016-05-03 | Muthu | Typing Test | 10.00 AM | 10.45 AM | Completed
|  | Thalapakattu remaining issue fixed | 10.45 AM | 2.00 PM | Pending
|  | Went to atomicka for thalalpakattu demo | 3.45 PM | 6.00 PM
|  | Thalapakattu item search issue fixing | 6.00 PM | 9.00 PM | Completed
2016-05-03 | Nithya | Typing test | 9:35 | 10:15 | Completed
|  | Standup meeting,etekchnoservices html conversion | 10:15 | 14:15 | In Progress
|  | etekchnoservices html conversion | 15:15 | 19:20 | Pending | Completed upto to carousel
2016-05-03 | Ramya | attended typing test and standup meeting | 9.40am | 10.20am | completed
|  | started with sms code integration after advertisement posted | 10.30am | 10.50am | completed
|  | did custom combobox functionality | 11.45am | 4.30pm | completed
|  | tried to fix issues after integrated sms code in advertisement module | 4.30pm | 5.45pm | in progress
|  | get kt from kalai about the printing concept in thalapakattu project and proceeded with that task | 5.55pm | 7.00pm | pending
2016-05-03 | Santosh | Resell testing in windows | 9.00am | 1.30pm | completed
|  | oozaaoo full testing - cycle 3 | 3.00pm | 4.30pm | completed
|  | Resell Responsive testing | 5.00pm | 7.15pm | Pending
2016-05-03 | Siva Rama Kannan | Typing test | 09.30 AM | 10.00 AM
|  | Move the oozaaoo code to git and send the report to tester | 10.00 AM | 10.30 AM | Completed
|  | Creating select box and append the html file to the same page for Thalapakattu | 10.30 AM | 3.30 PM | Completed
|  | Implementing autoscrolldown function for Thalapakattu | 3.30 PM | 6.45 PM | Completed
2016-05-03 | Velpandi | Typing Test | 9:30 | 10:30 | Completed
|  | Prepare HTML Colors,HTML CSS,HTML Links,HTML Images | 10:30 | 11:15 | Completed
|  | Prepare HTML Tables,HTML List, HTML Blocks,HTML Classes | 11:15 | 12:00 | Completed
|  | Task:Design BLOGS and PRICING in INVOICE | 12:00 | 18:30 | In Process
2016-05-03 | Vignesh | worked in ETS site respnsive design | 9.45am | 12.00pm | pending
downloaded free bootstrap template and customised it
|  | using ets code for responsive design | 12.00pm | 5.30pm | completed
|  | learned responsive and jquery function from nithya for ets | 5.30pm | 7.30pm | completed
site

## 02.05.2016
Date | Name | Task | Start time | End time | Status | Comment
2016-05-02 | Akila | Installed softwares | 12.00pm | 01.00pm | Completed
|  | KT from Nithya | 01.00pm | 02.00pm | Completed
|  | Learnt Photoshop | 03.00pm | 04.00pm | Completed
|  | HTML5 review | 04.00pm | 05.00pm | Completed
|  | Tried out designing | 05.30pm | 07.15pm | Pending
2016-05-02 | Balasubramaniam | Intent Meeting | 23:30 | 12.30 PM | Completed
|  | Prepare HTML: HTML OVERVIEW,HTML BASIC TAGS,HTML ELEMENTS, | 12:50 | 14:00 | Completed
|  | HTML ATTRIBUTES, HTML FORMATTING | 15:00 | 16:00 | Completed
|  | HTML META TAGS, HTML COMMENTS, HTML IMAGES | 4:15 PM | 18:30 | Completed
2016-05-02 | Barath | Designing Correction and new Design in Xyget Web page | 10.15 AM | 7.00PM | Pending
2016-05-02 | Kalai | Worked in thalapakattu project SMS sending code for different session(complete lunch, dinner and snacks) | 10.40 am | 1.30 pm | completed
|  | Worked in thalapakattu project SMS sending code for different session(end of the day) | 2.30 pm | 8.30 pm | completed
2016-05-02 | Madhivanan | Daily Report Sheet Updation | 10.50 AM | 11.10 AM | Pending
|  | Thalapakattu Testing | 11.10 AM | 12.50 PM | Pending | Partially Completed
|  | Globalen Solutions Testing | 12.50 PM | 2.30 PM | Pending
|  | Globalen Solutions Testing | 3.30 PM | 6.15 PM | Completed
|  | Meeting with Intent & Akila | 6.20 PM | 7.00 PM | Completed
|  | Wellocity Testing | 7.10 PM | 8.00 PM | Completed
2016-05-02 | Muthu | System arrangement | 9.30 AM | 10.20 AM | Completed
|  | Thalapakattu Keypressing issue | 10.20 AM | 1.30 PM | Pending
|  | Thalapakattu Demo to vinoth at atomicka office | 3.00 PM | 5.30 PM | Completed
|  | Thalapakattu new changes | 5.30 PM | 8.30 PM | Pending
2016-05-02 | Nithya | Typing test | 10:00 | 10:40 | Completed
|  | Standup meeting,Resell bug report design corrections | 10:45 | 14:00 | In Progress
|  | Resell design issues and chat design issue in chrome | 15:00 | 20:00 | Completed
2016-05-02 | Ramya | atteded typing test and statndup meeting | 10.10am | 11.20am | completed
|  | fixed wct issues | 11.30am | 1.30pm | completed
|  | did some minor corrections and proceeded with xyget sms code integration after product was posted and after admin approval for products | 3.20pm, | 8.00pm | completed
2016-05-02 | Santosh | Resell testing | 9.30am | 6.30pm | Pending
2016-05-02 | Siva Rama Kannan | Typing test | 9.30 AM | 10.00 AM
|  | Meeting with sastha | 10.00 AM | 11.00AM
|  | Fixing issues in bug sheet of oozaaoo | 11.15 AM | 7.00 PM | Completed
2016-05-02 | Velpandi | Intent Meeting | 23:30 | 12.30 PM | Completed
|  | Prepare HTML: HTML OVERVIEW,HTML BASIC TAGS,HTML ELEMENTS, | 12:50 | 14:00 | Completed
|  | HTML ATTRIBUTES, HTML FORMATTING | 15:00 | 16:00 | Completed
|  | HTML META TAGS, HTML COMMENTS, HTML IMAGES | 16:15 | 18:30 | Completed
2016-05-02 | Vignesh | Learned how to add bootstrap carousal | 10.00am | 12.00pm | completed
|  | leraned two-column blog layout | 12.00pm | 3.30pm | completed
|  | learned bootstrap grids jumbotron | 3.30pm | 7.00pm | completed