## Team Task Today
Date | Name | Task | Start time | End time | Status | Comment
2016-04-07 | Asai | Online Mobile Invoice: 15 days work should be deliver first
Website Animation
Cotton House Logo
Eventswat Logo & Color Corrections
Evinity Template (Add more Photo Slides)
ETS Profile need in PDF formate
Wall motivation theme
Glass design stickers
Facebook & Linkedin, add related post and promote
Mail Signature for Deepak, HR, Sastha
2016-04-07 | Barath
Asai will assign
2016-04-07 | Kalai | Resell Issues
Wellocity Dependency
Resell Scenario explaination to Santosh(Tester) Both Mobile & Desktop
2016-04-07 | Madhi | Daily Task Scheduling to Team | 288:00 | 1.00 AM | Completed
|  | Daily Task Sheet updation | 3.00 PM | 4.00 PM | Completed
|  | Chennai Folder |  |  | Pending | Not yet start
|  | Evinity |  |  | Pending | Not yet start
|  | Etekchnoservices Site |  |  | Pending | Not yet start
|  | Resell Product Updation & Error Documentation | 10.30 AM | 2.00 PM | Pending
|  | Printer Concept | 4.00 PM | 5.15 PM
2016-04-07 | Muthu | E-Learning: Discuss with clint and do the updation, before that get suggestion with Sastha | 10.15 AM | 11.00 AM | Completed | Sent mail to Sastha
|  | Wellocity Dependency | 11.15 AM | 4.30 PM | Completed | Sent mail to Sastha
|  | Xyget Issues Fixing |  |  | Hold | Printer concept has high priority
|  | Printer Concept | 4.30 PM |  | High Priority
2016-04-07 | Santosh | Wellocity Testing
Resell Testing
Xyget Testing
Atomicka Mobile Testing
2016-04-07 | Vignesh | Oozaaoo: Inbond Responsive | 10.00 AM | 4.00 PM
|  | Oozaaoo: Outbond Responsive full completion | 4.00 PM | 5.00 PM
Chennai Folder
Etekchnoservices Site
2016-04-07 | Deepak | Events Domain name suggestion 5
Wellocity Design Issues 3
Atomicka Mobile (Deadline 8th April)
Oozaaoo Templates

## DAILY TASH
2016-10-05 | Barath | DESIGNING ETS PORTFOLLIO | 10.00Am | 7.29pm | completed
|  | Designing Correction on ETS WEBSITE | 11.00Am | 1.30PM | completed
2016-11-05 | BARATH | LOGO DESIGN FOR RICSCO | 10.00Am | 4.00PM | completed
|  | FB POST FOR FRESHERS | 40.00PM

## xyget
EBD USER PART
28-29Apr2016 | ADVANCED-SEARCH-PAGE | COMPLETED |  | Pending
28-29Apr2016 | ADVANCE-SEARCH-PAGE | COMPLETED |  | Content Management
28-29Apr2016 | ADVERTISMENT-CREATE-NEW | COMPLETED |  | Profile
28-29Apr2016 | best-deal1 | COMPLETED |  | Activities
28-29Apr2016 | Best-Deal-2 | COMPLETED
28-29Apr2016 | CHAT-MIN | COMPLETED |  | Image Management
28-29Apr2016 | CHAT-WINDOW-MAX | COMPLETED |  | Gallery
28-29Apr2016 | CONTACT-INFO1 | COMPLETED |  | Header Settings
28-29Apr2016 | CONTACT-INFO2 | COMPLETED
28-29Apr2016 | EDITING-EXISTING | COMPLETED
28-29Apr2016 | ESTABLISHMENT-OWNER-DETAILS | COMPLETED
28-29Apr2016 | ESTABLISHMENT-PROFILE-COMPANY-SETUP | COMPLETED
28-29Apr2016 | LOGIN-3 | COMPLETED
28-29Apr2016 | LOGIN-PAGE | COMPLETED
28-29Apr2016 | LOGO-UPLOAD | COMPLETED
28-29Apr2016 | SETTINGS | COMPLETED
28-29Apr2016 | USER-REESGISTER-FORM | COMPLETED
28-29Apr2016 | USER-RESIGTER-FORM2 | COMPLETED
AMIN PART
25-26apr2016 | ESTABLISHMENT PROFILE PAGE | completed
25-26apr2016 | Xygate Admin Authentication | completed |  | `
25-26apr2016 | Xygate Admin Country MAster | completed
25-26apr2016 | Xygate Admin module category | completed
25-26apr2016 | Xygate Admin module list | completed
25-26apr2016 | Xygate Admin Resigter user | completed
25-26apr2016 | Xygate Admin user role | completed
25-26apr2016 | Xygate Admin General City MAster | completed
25-26apr2016 | Xygate Admin General State MAster | completed
25-26apr2016 | Xygate Admin Page | completed
25-26apr2016 | Xygate Admin Sector | completed
25-26apr2016 | Xygate AdminProduct Category | completed
Date | Name | Task | Start time | End time | Status | Comment
2016-04-07 | Barath | E-mail Signature to ETS | 10.AM | 11.30AM | Completed
|  | ETS PRO Poster for FB | 11.30am | 1.00PM | Pending
|  | Wall motivation Image Searching | 1.00PM | 1.45PM | Completed | Waiting for approval
|  | ETS BUSINESS PRO DESIGN | 3.00PM | 6.50PM | Completed
2016-08-04 | BARATH | ETS PRO Poster for FB | 9.30AM | 10.50AM | Completed | Waiting for approval to upload
|  | ETS PRO Poster for Linked in | 10.50AM | 12.12PM | Completed | Waiting for approval to upload
|  | ETS BUSINESS PROFILE COVER PAGE | 12.12PM | 3.30PM | Completed
|  | Wall motivation Designing sample one done | 3.30PM | 6.30PM | in process | Waiting for approval
2016-09-04 | BARATH | OOZZAAO Image Resizing | 9.40AM | 10.00AM | Completed
|  | Animation Templates Seraching | 10.00Am | 2.00PM | Completed
|  | Animation for ETS(2 PART) | 3.00PM | 6.30PM | Completed | Remaining in process
2016-11-04 | Barath | Image Resizing for Oozzaaoo | 1.00AM | 10.30AM | Completed
|  | Image Resizing for Happy Journey | 10.30AM | 11.00AM | Completed
|  | ETS PRO REDIESGN | 11.00AM | 6.30PM | Completed
2016-12-04 | Barath | ETS PRO FILE RE Crection | 10.00Am | 11.30AM | Completed
|  | PhotoShoot | 12.00PM | 1.30PM | Completed
|  | ID Card Designing | 2.30PM | 6.40PM | Completed
13-4-2016 | Barath | happy journey image resizing | 10.00Am | 10.30AM | Completed
|  | ID Card Designing and correction | 10.30Am | 1.40PM | Completed
|  | wall motion iamge deigning | 2.45Pm | 4.30Pm | Completed
|  | Promo add designing and correction | 4.30Pm | 6.30Pm | Completed
|  | Seraching animation template for ETS | 6.30Pm | 6.48Pm
15-4-2016 | Barath | Image resizing to OOZZAAOO | 10.00AM | 10.30AM | Completed
|  | wall motion iamge deigning | 10.30AM | 1.30PM | Completed | 2 sample done
|  | ID CARD correction | 3.00PM | 3.30PM | Completed
|  | wall motion iamge deigning | 5.00pm | 6.30pm | Completed | 2 sample done
18-4-2016 | Barath | ID CARD Correction | 9.3am | 6.15 pm | Completed
19-4-2016 | Barath | Banner Slider Image designing | 10.00Am | 6.15PM | Completed | 4 Slides
|  | GS Despktop Image Designing | 6.15PM | 6.30PM | Completed
20-4-2016 | Barath | Banner Slider Image designing and Correction | 10.00Am | 1.30PM | Completed | 3 New Sample
|  | ID Card Correction | 2.45PM | 3.15PM | Completed
|  | Banner Slider Image designing and Correction | 3.15PM | 5.30PM | Completed
|  | Analysing XYGET Design | 5.30PM | 6.30PM | ON Process
21-4-2016 | Barath | Taking screen shot for Xygate site | 9.45Am | 10.30AM | Completed
|  | deasiging Login Page | 10.30Am | 1.30PM | Completed
|  | Designing Search Page | 2.30PM | 4.30PM | Completed
|  | Desiging 404 error, 400error,500Error, 403 error page | 6.00Pm | 6.30PM | Completed
|  | Meeting With HR | 4.30Pm | 5.30PM
22-4-2016 | Barath | pick opproprite pages have to design in Xyget | 10.00AM | 10.30AM | Completed
|  | Designing HOME to Xyget | 10.30AM | 1.30PM
|  | Correction in Evinity Banner | 4.30PM | 6.10PM | Completed
|  | Designing HOME to Xyget | 6.30PM | 6.30PM | in process
23-4-2016 | Barath | Designing HOME to Xyget | 10.00AM | 12.30PM | Completed
|  | Correction in Evinity Banner | 12.30PM | 1.30PM | Completed
|  | Evinity Broucher Designing | 2.45PM | 6.30PM | Completed
25-4-2016 | Barath | Designing web Mokup to Xyget | 10.00Am | 1.30PM | 8 Page completed in Admin Apart
|  | Designing web Mokup to Chemknowcore | 2.30PM | 6.40PM | 3 Page Completed
26-4-2016 | BARATH | Designing web Mokup to Xyget | 10.00AM | 10.30AM | 2SAMPLE PAGE
|  | Designing web Mokup to Chemknowcore | 10.30AM | 6.40PM | 8Page Completed
|  | Image correction In Atomica | 11 | 11.15 | Completed
27-4-2016 | Barath | Designing Xyget Web Page | 10.00AM | 1.00PM | Almost admin part have completed
|  | Designing CHEMKNOWCORE WEB PAGE | 3.30PM | 6.30OM | on hold
|  | LOGO DESIGNING to Chemknoecore | 6.30PM | 7.50PM | in process
28-4-2016 | Barath | Designing Xyget Web page | 10.00AM | 6.5 | 7 Sample with Login and Search have completed
29-4-2016 | Barath | Designing Xyget Web page | 10.00AM | 12.30PM
|  | Designing Banner For Resell | 12.30PM | 1.30PM | Completed
Designing Xyget Web page
30-4-2016 | BARATH | Designing Xyget Web page | 10.00AM | 1.30PM | on process
2016-02-05 | BARATH | Designing Correction and new Design in Xyget Web page | 10.15 AM | 7.00PM | On process
2016-03-05 | BARATH | Designing Correction and new Design in Xyget Web page | 10.00AM | 12.30PM | completed
|  | Designing FIXIDO PROFILE | 3.30PM | 6.00PM | completed
|  | discussion with DEEPAK | 6.00PM | 6.30PM |  | Regarding NEW Project(like FIXIDO)
|  | discussion with Ram | 6.30PM | 6.45 |  | Regarding Chemknowcore
2016-04-05 | BARATH | Designing FIXIDO PROFILE | 9.45am | 6.35pm | completed | 4 PAGE COMPLETED
2016-05-05 | BARATH | Designing ETS PROFILE | 11.30AM | 6.00PM | COMPLETED | NEW DESIGN
|  | DESIGNING LETTERPAD to GTS | 6.00PM | 6.30PM | COMPLETED
2016-06-05 | Baratah | Designing ETS PROFILE | 10.00Am | 1.45 | COMPLETED
|  | DESIGNING ETS PORTFOLLIO | 2.40PM | 7.40PM | on Process

## Daily task time line
Profile | COMPLETED | content have change
single profile | COMPLETED
portfolio profile | COMPLETED | content have change
Logo
RICSCO | SMAPLE 1 Completed
synclio | Waiting for name Suggestion
invoice generator | Waiting for name Suggestion
staff Id cards | Waiting for camera
fresher welcome / bithday updates | Complete
cotton house | Waiting for input
THALAPAKATTU BRIYANNI